## All Features
Feature ID | Module | Module Name | Feature Name | Description | Priority | Story Points | Phase | Persona | Dependencies | Acceptance Criteria
US-M1-001 | M1 | Core HRIS | Employee 360 Profile | View all employee data in single view | P0 | 8 | 1 | HR Manager | M3,M6,M4 | Given an active employee, when HR views profile, then all data tabs (personal, job, pay, docs) load in < 2s
US-M1-002 | M1 | Core HRIS | Org Chart Navigator | Visual org chart with drill-down | P0 | 8 | 1 | HR Director | M10 | Given org structure data, when director opens org chart, then departments and reporting lines render correctly
US-M1-003 | M1 | Core HRIS | Bulk Employee Import | CSV upload with validation and error report | P0 | 8 | 1 | HR Specialist | M10 | Given a CSV file, when uploaded, then system validates all rows and shows error report with line numbers
US-M1-004 | M1 | Core HRIS | Leave Workflow Engine | Multi-level leave approval with balance tracking | P0 | 13 | 1 | HR Manager | M6 | Given leave request, when submitted, then routes to correct approver and deducts balance atomically on approval
US-M1-005 | M1 | Core HRIS | Self-Service Profile | Employee views and edits own profile | P0 | 5 | 1 | Outsourced Employee | M11 | Given employee login, when accessing profile, then can view all fields and edit permitted fields
US-M1-006 | M1 | Core HRIS | Document Vault | Upload, categorize, and track document expiry | P0 | 8 | 1 | HR Specialist |  | Given document with expiry, when 60/30/7 days remain, then alerts sent to configured recipients
US-M1-007 | M1 | Core HRIS | Contract Management | Create, renew, amend employment contracts | P0 | 8 | 1 | HR Manager | M6 | Given contract creation, when signed, then terms feed to payroll and benefits
US-M1-008 | M1 | Core HRIS | Team Dashboard | View team members and availability | P0 | 5 | 1 | Line Manager | M11 | Given manager login, when viewing team, then sees members, leave status, and availability
US-M1-009 | M1 | Core HRIS | Workforce Analytics Widget | Headcount, turnover, diversity KPIs | P0 | 8 | 1 | HR Director | M9 | Given dashboard access, when loading, then shows real-time headcount, turnover rate, and diversity metrics
US-M1-010 | M1 | Core HRIS | Attendance Tracking | Clock-in/out with geofencing | P0 | 8 | 1 | HR Specialist | M11 | Given geofence configured, when employee clocks in outside boundary, then flagged for review
US-M1-011 | M1 | Core HRIS | Position Management | Create positions with grade and band | P0 | 5 | 1 | HR Manager | M6 | Given position creation, when grade assigned, then salary band auto-populated from compensation structure
US-M1-012 | M1 | Core HRIS | Mobile Leave Request | Request leave from mobile app | P1 | 5 | 1 | Outsourced Employee | M11 | Given mobile app, when requesting leave, then same workflow and validation as web
US-M1-013 | M1 | Core HRIS | Custom Fields Engine | Tenant-configurable employee fields | P1 | 8 | 1 | HR Specialist | M10 | Given admin access, when adding custom field, then field appears on employee forms for that tenant only
US-M1-014 | M1 | Core HRIS | Compliance Dashboard | Labor law compliance status | P1 | 5 | 1 | HR Director | M9 | Given compliance rules, when viewing dashboard, then shows status of each regulation with action items
US-M1-015 | M1 | Core HRIS | Delegation of Authority | Delegate approvals during absence | P1 | 5 | 1 | Line Manager |  | Given manager absence, when delegation set, then delegate receives all approval requests
US-M10-001 | M10 | System Administration | Multi-Tenant Architecture | Isolated data per client tenant | P0 | 13 | 1 | System Admin |  | Given new client, when provisioned, then data isolated and secure at database level
US-M10-002 | M10 | System Administration | User Access Control (RBAC) | Role-based permission system | P0 | 13 | 1 | System Admin |  | Given role assignment, when applied, then user sees only permitted modules and data
US-M10-003 | M10 | System Administration | SSO Integration | Single sign-on via SAML/OAuth | P0 | 8 | 1 | System Admin |  | Given SSO configured, when user logs in, then authenticates via provider seamlessly
US-M10-004 | M10 | System Administration | Audit Logging System | Track all user actions and changes | P0 | 8 | 1 | System Admin |  | Given action, when performed, then logged with user, timestamp, before/after data
US-M10-005 | M10 | System Administration | Data Backup & Recovery | Automated backups with restore | P0 | 8 | 1 | System Admin |  | Given backup schedule, when activated, then daily backups stored with point-in-time restore
US-M10-006 | M10 | System Administration | API Key Management | Create and revoke API keys | P0 | 5 | 1 | System Admin |  | Given API consumer, when creating key, then key issued with rate limits and scopes
US-M10-007 | M10 | System Administration | Webhook Configuration | Subscribe to system events | P0 | 8 | 1 | System Admin |  | Given event type, when subscribing, then webhook triggered on event with payload
US-M10-008 | M10 | System Administration | Data Migration Tools | Import/export tenant data | P0 | 13 | 1 | System Admin |  | Given CSV or export file, when migrating, then data maps and validates before import
US-M10-009 | M10 | System Administration | System Health Monitoring | Monitor uptime and performance | P0 | 8 | 1 | System Admin |  | Given dashboard, when viewing, then shows system uptime, latency, and alerts
US-M10-010 | M10 | System Administration | Feature Flags & Toggles | Enable/disable features per tenant | P0 | 5 | 1 | System Admin |  | Given feature flag, when toggled, then feature enabled/disabled instantly for tenant
US-M10-011 | M10 | System Administration | Email Configuration | Configure SMTP and email templates | P0 | 5 | 1 | System Admin |  | Given email template, when configured, then custom emails send branded correctly
US-M10-012 | M10 | System Administration | Two-Factor Authentication | Require MFA for users | P0 | 5 | 1 | System Admin |  | Given MFA policy, when enforced, then users complete 2FA on login
US-M10-013 | M10 | System Administration | Encryption & Data Security | Encrypt data at rest and transit | P0 | 8 | 1 | System Admin |  | Given data, when stored, then encrypted with AES-256 and TLS in transit
US-M10-014 | M10 | System Administration | System Configuration Dashboard | Admin config and settings UI | P0 | 8 | 1 | System Admin |  | Given admin access, when navigating, then all configs accessible without code
US-M10-015 | M10 | System Administration | Rate Limiting & DDoS Protection | Protect against abuse | P1 | 8 | 1 | System Admin |  | Given attack traffic, when detected, then requests throttled and attacker blocked
US-M11-001 | M11 | Mobile Application | iOS Native App | Native iOS application | P0 | 13 | 3 | Outsourced Employee |  | Given iOS app, when launched, then runs natively with push notifications
US-M11-002 | M11 | Mobile Application | Android Native App | Native Android application | P0 | 13 | 3 | Outsourced Employee |  | Given Android app, when launched, then runs natively with push notifications
US-M11-003 | M11 | Mobile Application | Mobile Authentication | Biometric login (Face/Touch ID) | P0 | 8 | 3 | Outsourced Employee | M10 | Given biometric device, when enabled, then authenticates via fingerprint or face
US-M11-004 | M11 | Mobile Application | Push Notifications | Real-time push alerts | P0 | 8 | 3 | Outsourced Employee |  | Given event, when triggered, then push sent to mobile with deep link
US-M11-005 | M11 | Mobile Application | Offline Sync | Work offline with sync on reconnect | P0 | 13 | 3 | Outsourced Employee |  | Given offline state, when returning online, then queued actions auto-sync
US-M11-006 | M11 | Mobile Application | Mobile Navigation | Bottom tab and drawer navigation | P0 | 5 | 3 | Outsourced Employee |  | Given mobile layout, when navigating, then bottom tabs and drawers work smoothly
US-M11-007 | M11 | Mobile Application | Camera Integration | Document capture via camera | P0 | 5 | 3 | Outsourced Employee | M1 | Given camera, when capturing document, then OCR extracts text automatically
US-M11-008 | M11 | Mobile Application | Location Services | GPS for attendance and geofencing | P0 | 8 | 3 | HR Specialist | M1 | Given geofence, when employee near, then clock-in available
US-M11-009 | M11 | Mobile Application | App Update Management | Over-the-air app updates | P0 | 5 | 3 | System Admin |  | Given new version, when available, then prompts update with changelog
US-M11-010 | M11 | Mobile Application | Mobile Permissions | Handle app permissions (camera, location) | P0 | 5 | 3 | Outsourced Employee |  | Given permission required, when requested, then system permission dialog shown
US-M11-011 | M11 | Mobile Application | Dark Mode Support | Dark theme for mobile app | P1 | 3 | 3 | Outsourced Employee |  | Given dark mode enabled, when viewing, then app uses dark colors
US-M11-012 | M11 | Mobile Application | Mobile Performance | Optimize for slow networks | P1 | 8 | 3 | Outsourced Employee |  | Given 3G connection, when using app, then UI responsive and data loads progressively
US-M11-013 | M11 | Mobile Application | Mobile Analytics | Track mobile usage and crashes | P1 | 5 | 3 | System Admin | M9 | Given crash, when occurring, then automatically reported with stack trace
US-M11-014 | M11 | Mobile Application | App Store Deployment | Deploy to App Store and Play Store | P0 | 8 | 3 | System Admin |  | Given app version, when ready, then submit and manage app store listings
US-M11-015 | M11 | Mobile Application | Mobile Accessibility | WCAG 2.1 AA on mobile | P1 | 5 | 3 | Outsourced Employee |  | Given screen reader, when enabled, then app readable and navigable
US-M12-001 | M12 | Client Portal | Client Portal Home | Client dashboard and overview | P0 | 8 | 3 | Client SPOC | M1 | Given client login, when home accessed, then shows relevant metrics and tasks
US-M12-002 | M12 | Client Portal | Employee Directory Access | View managed employees | P0 | 5 | 3 | Client SPOC | M1 | Given employee managed by client, when viewing, then sees basic profile without sensitive data
US-M12-003 | M12 | Client Portal | Leave Approval Portal | Approve leave requests | P0 | 8 | 3 | Client SPOC | M1,M4 | Given leave request, when reviewing, then approves/rejects with comment
US-M12-004 | M12 | Client Portal | Attendance Reporting | View attendance records | P0 | 5 | 3 | Client SPOC | M1 | Given date range, when viewing, then shows team attendance and flagged absences
US-M12-005 | M12 | Client Portal | Payroll Summary View | View anonymized payroll data | P0 | 5 | 3 | Client SPOC | M6 | Given payroll cycle, when viewing, then shows summary without individual pay rates
US-M12-006 | M12 | Client Portal | Performance Review Submission | Submit manager reviews | P0 | 8 | 3 | Client SPOC | M4 | Given review cycle, when open, then manager fills form and submits
US-M12-007 | M12 | Client Portal | Invoice Tracking | View billing and invoices | P0 | 5 | 3 | Client SPOC | M13 | Given invoice, when viewing, then shows itemized charges and payment status
US-M12-008 | M12 | Client Portal | Support Ticket System | Submit support requests | P0 | 8 | 3 | Client SPOC |  | Given issue, when creating ticket, then routes to Egybell support with SLA tracking
US-M12-009 | M12 | Client Portal | Document Upload Portal | Submit required documents | P0 | 5 | 3 | Client SPOC | M1 | Given document request, when uploading, then document stored securely
US-M12-010 | M12 | Client Portal | Communication Center | Announcements and messages | P0 | 5 | 3 | Client SPOC |  | Given announcement, when posted, then visible to client in portal
US-M12-011 | M12 | Client Portal | Custom Report Access | View pre-built reports | P1 | 5 | 3 | Client SPOC | M9 | Given report library, when accessing, then views org-specific reports
US-M12-012 | M12 | Client Portal | Hiring Request Portal | Submit and track hiring requests | P0 | 8 | 3 | Client SPOC | M2 | Given hiring need, when submitting, then Egybell recruiter notified and tracks SLA
US-M12-013 | M12 | Client Portal | Org Structure Management | Manage your org structure | P1 | 8 | 3 | Client SPOC | M1 | Given client access, when updating structure, then changes reflected in Egybell system
US-M12-014 | M12 | Client Portal | Client Portal Mobile | Mobile access to portal | P1 | 5 | 3 | Client SPOC | M11 | Given mobile, when accessing portal, then key features available responsively
US-M12-015 | M12 | Client Portal | Data Export Requests | Export client data on demand | P1 | 5 | 3 | Client SPOC | M9 | Given export request, when approved, then data delivered securely
US-M13-001 | M13 | Billing & Usage | Billing Engine | Calculate and issue invoices | P0 | 13 | 4 | Billing Admin | M1 | Given billing period, when running, then invoice generated with usage charges and reconciled
US-M13-002 | M13 | Billing & Usage | Usage Tracking | Track module usage and metrics | P0 | 8 | 4 | System Admin |  | Given tenant action, when performed, then usage recorded for billing
US-M13-003 | M13 | Billing & Usage | Subscription Management | Manage client subscriptions | P0 | 8 | 4 | Billing Admin | M1 | Given subscription, when configured, then billing applies per pricing model
US-M13-004 | M13 | Billing & Usage | Add-On Management | Configure and track add-ons | P0 | 5 | 4 | Billing Admin | M1 | Given add-on purchased, when tracked, then charges applied to invoice
US-M13-005 | M13 | Billing & Usage | Pricing Rule Engine | Define pricing tiers and rules | P0 | 8 | 4 | Billing Admin |  | Given pricing rule, when applied, then overrides default per-tenant
US-M13-006 | M13 | Billing & Usage | Payment Processing | Process credit card payments | P0 | 13 | 4 | Billing Admin |  | Given invoice, when due, then payment charged automatically via Stripe/similar
US-M13-007 | M13 | Billing & Usage | Invoice Management Portal | View and download invoices | P0 | 5 | 4 | Client SPOC | M12 | Given invoice, when accessing, then viewable and downloadable as PDF
US-M13-008 | M13 | Billing & Usage | Credit & Refund Processing | Issue credits and refunds | P0 | 8 | 4 | Billing Admin |  | Given refund approved, when processing, then credit applied and payment reversed
US-M13-009 | M13 | Billing & Usage | Discount Management | Create promotional discounts | P0 | 5 | 4 | Billing Admin |  | Given discount code, when applied, then reduces invoice amount
US-M13-010 | M13 | Billing & Usage | Billing Analytics | Revenue and billing metrics | P0 | 8 | 4 | Billing Admin | M9 | Given billing data, when viewing, then shows MRR, ARR, churn, and LTV
US-M13-011 | M13 | Billing & Usage | Dunning Management | Retry failed payments | P0 | 5 | 4 | Billing Admin |  | Given failed payment, when retrying, then attempts with backoff strategy
US-M13-012 | M13 | Billing & Usage | Tax Calculation | Auto-calculate taxes per region | P0 | 13 | 4 | Billing Admin |  | Given client location, when invoicing, then tax calculated and applied correctly
US-M13-013 | M13 | Billing & Usage | Contract Management | Store and manage client contracts | P1 | 8 | 4 | Billing Admin |  | Given contract, when stored, then terms accessible and renewal dates tracked
US-M13-014 | M13 | Billing & Usage | Billing Notifications | Send invoice and payment reminders | P1 | 5 | 4 | Billing Admin |  | Given invoice due, when approaching, then reminder email sent to client
US-M13-015 | M13 | Billing & Usage | Billing Compliance Reporting | Generate billing audit reports | P1 | 5 | 4 | Billing Admin | M1 | Given audit period, when requested, then compliance report generated with all details
US-M2-001 | M2 | Recruitment & ATS | Job Requisition Builder | Create structured job postings | P0 | 8 | 2 | Recruiter | M12 | Given recruiter access, when creating requisition, then all required fields and custom sections capture completely
US-M2-002 | M2 | Recruitment & ATS | Multi-Channel Posting | Post to multiple job boards | P0 | 8 | 2 | Recruiter |  | Given job posting, when submitted, then appears on selected job boards within 24 hours
US-M2-003 | M2 | Recruitment & ATS | AI CV Screening | Parse and rank CVs automatically | P0 | 13 | 2 | Recruiter |  | Given CV upload, when processed, then extracted data and ranked candidates match manual scoring 85%+
US-M2-004 | M2 | Recruitment & ATS | Candidate Pipeline Kanban | Visual pipeline with drag-drop | P0 | 8 | 2 | Recruiter |  | Given candidates, when on pipeline view, then drag-drop between stages updates status in real-time
US-M2-005 | M2 | Recruitment & ATS | Candidate Review Portal | Review and score shortlisted candidates | P0 | 5 | 2 | Client SPOC | M12 | Given shortlist, when accessing portal, then can score and comment without system access
US-M2-006 | M2 | Recruitment & ATS | Interview Scheduler | Calendar integration, availability | P0 | 8 | 2 | Recruiter |  | Given multiple candidates, when scheduling, then finds common availability slots across 3+ calendars
US-M2-007 | M2 | Recruitment & ATS | Offer Generation Engine | Template-based offers with merge fields | P0 | 8 | 2 | Recruiter | M1,M3 | Given candidate selection, when generating offer, then all merge fields populate from M1 data automatically
US-M2-008 | M2 | Recruitment & ATS | E-Signature Integration | Digital offer acceptance | P0 | 5 | 2 | Recruiter |  | Given generated offer, when candidate signs, then signature legally binding and stored with audit trail
US-M2-009 | M2 | Recruitment & ATS | Hiring Request Intake | Submit structured hiring requests | P0 | 5 | 2 | Client SPOC | M12 | Given client portal access, when submitting request, then routes to recruiter with all details captured
US-M2-010 | M2 | Recruitment & ATS | SLA Tracking Dashboard | Monitor recruitment SLAs per client | P0 | 5 | 2 | Recruiter | M9 | Given SLA rules, when viewing dashboard, then shows on-track and at-risk clients with ETAs
US-M2-011 | M2 | Recruitment & ATS | Candidate Communication Hub | Email/SMS templates, tracking | P1 | 5 | 2 | Recruiter |  | Given template library, when sending, then tracks open rates and responses automatically
US-M2-012 | M2 | Recruitment & ATS | Recruitment Analytics | Pipeline metrics, time-to-hire | P1 | 8 | 2 | HR Manager | M9 | Given recruitment data, when viewing dashboard, then shows time-to-hire, cost-per-hire, and conversion rates
US-M2-013 | M2 | Recruitment & ATS | Talent Pool Database | Searchable candidate registry | P1 | 5 | 2 | Recruiter |  | Given candidate history, when searching, then filters by skills, experience, and past roles
US-M2-014 | M2 | Recruitment & ATS | Interview Feedback Forms | Structured evaluation forms | P1 | 5 | 2 | Client SPOC |  | Given interview, when submitting feedback, then form enforces required fields and scales
US-M2-015 | M2 | Recruitment & ATS | LinkedIn Integration | Source directly from LinkedIn | P1 | 8 | 2 | Recruiter |  | Given LinkedIn profile, when importing, then data parses automatically to candidate record
US-M3-001 | M3 | Onboarding & Offboarding | Onboarding Template Builder | Create reusable onboarding templates | P0 | 8 | 2 | HR Manager |  | Given workflow designer, when building template, then can define tasks, dependencies, and triggers
US-M3-002 | M3 | Onboarding & Offboarding | Dual-Lane Workflow Engine | Parallel Egybell + Client task lanes | P0 | 13 | 2 | HR Manager | M10 | Given onboarding started, when in progress, then Egybell and Client tasks run in parallel with sync points
US-M3-003 | M3 | Onboarding & Offboarding | Pre-boarding Portal | Upload docs before day 1 | P0 | 5 | 2 | New Hire |  | Given new hire offer, when portal link sent, then can upload docs and complete forms pre-day-1
US-M3-004 | M3 | Onboarding & Offboarding | Task Assignment Engine | Auto-assign tasks by role/department | P0 | 8 | 2 | HR Specialist |  | Given role and department, when onboarding starts, then tasks auto-assign based on rules
US-M3-005 | M3 | Onboarding & Offboarding | Access Provisioning Trigger | Automated system access requests | P0 | 5 | 2 | IT Admin | M10 | Given employee profile, when onboarding approved, then system access requests auto-generate
US-M3-006 | M3 | Onboarding & Offboarding | Offboarding Workflow Engine | Termination-triggered offboarding | P0 | 8 | 2 | HR Manager | M1,M6 | Given termination date, when offboarding started, then all asset return and access revocation tasks triggered
US-M3-007 | M3 | Onboarding & Offboarding | Exit Interview Module | Structured exit surveys | P0 | 5 | 2 | HR Manager |  | Given departing employee, when exit interview scheduled, then feedback collected and analyzed
US-M3-008 | M3 | Onboarding & Offboarding | Onboarding Progress Tracker | Monitor new hire task completion | P0 | 5 | 2 | Line Manager | M12 | Given onboarding in progress, when manager views, then sees task status and completion timeline
US-M3-009 | M3 | Onboarding & Offboarding | Document Collection Checklist | Track required document submission | P1 | 5 | 2 | HR Specialist |  | Given required documents, when checklist active, then blocks hire date if missing docs
US-M3-010 | M3 | Onboarding & Offboarding | Welcome Kit & Orientation | Digital welcome package | P1 | 3 | 2 | New Hire |  | Given new hire, when portal accessed, then finds company info, policies, and orientation videos
US-M3-011 | M3 | Onboarding & Offboarding | Cross-Lane Dependencies | Task dependencies across lanes | P1 | 8 | 2 | HR Manager |  | Given dual-lane workflow, when Client task complete, then dependent Egybell task auto-triggers
US-M3-012 | M3 | Onboarding & Offboarding | Client Onboarding Dashboard | Client view of onboarding progress | P1 | 5 | 2 | Client SPOC | M12 | Given onboarding underway, when client portal accessed, then sees progress without system access
US-M3-013 | M3 | Onboarding & Offboarding | Equipment Tracking | Track asset assignment and return | P1 | 5 | 2 | HR Specialist |  | Given equipment catalog, when assigning to employee, then tracks assignment and scheduled return
US-M3-014 | M3 | Onboarding & Offboarding | Rehire Workflow | Streamlined re-onboarding | P1 | 5 | 2 | HR Manager | M1 | Given former employee rehire, when starting, then pre-populates M1 data and shortens onboarding
US-M3-015 | M3 | Onboarding & Offboarding | Buddy/Mentor Assignment | Assign onboarding buddy | P2 | 3 | 2 | HR Specialist |  | Given new hire role, when assigning buddy, then buddy receives notifications and checklist
US-M4-001 | M4 | Performance Management | Goal Setting Framework | OKR/KPI goal creation and tracking | P0 | 8 | 3 | HR Manager | M1 | Given goal template, when manager creates goal, then links to KPIs and tracks progress quarterly
US-M4-002 | M4 | Performance Management | 360 Feedback Engine | Multi-rater feedback collection | P0 | 13 | 3 | HR Manager | M1 | Given employee, when 360 launched, then collects feedback from manager, peers, direct reports anonymously
US-M4-003 | M4 | Performance Management | Performance Review Builder | Customizable review templates | P0 | 8 | 3 | HR Manager | M1 | Given review cycle, when building, then defines competencies, rating scales, and sections
US-M4-004 | M4 | Performance Management | Calibration Workshop Module | Guided calibration sessions | P0 | 8 | 3 | HR Director | M1 | Given rated employees, when in calibration, then compares distributions and flags outliers
US-M4-005 | M4 | Performance Management | Competency Framework | Define and assess competencies | P0 | 8 | 3 | HR Manager | M1 | Given competency model, when assessing, then rates proficiency levels linked to development plans
US-M4-006 | M4 | Performance Management | Performance Improvement Plan | Structured PIP management | P0 | 5 | 3 | HR Manager | M1 | Given underperforming employee, when creating PIP, then tracks milestones and deadlines
US-M4-007 | M4 | Performance Management | Peer Recognition | Peer-to-peer recognition engine | P0 | 5 | 3 | Line Manager | M1 | Given employee, when recognizing peer, then creates visible recognition and builds portfolio
US-M4-008 | M4 | Performance Management | Performance Rating Widget | Quick rating capture during review | P0 | 5 | 3 | HR Manager | M1 | Given review open, when rating, then captures rating with mandatory justification
US-M4-009 | M4 | Performance Management | Succession Planning Bench | Identify and groom high-potentials | P0 | 8 | 3 | HR Director | M1 | Given performance data, when viewing bench, then ranks successors and tracks readiness
US-M4-010 | M4 | Performance Management | Development Plan Manager | Create and track development plans | P0 | 8 | 3 | Line Manager | M5 | Given assessment results, when creating plan, then assigns training and tracks completion
US-M4-011 | M4 | Performance Management | Review Cycle Manager | Configure review timelines and deadlines | P1 | 5 | 3 | HR Manager | M1 | Given review year, when setting up, then configures windows and sends reminders
US-M4-012 | M4 | Performance Management | Performance Analytics | Trends and distribution analysis | P1 | 8 | 3 | HR Director | M9 | Given rating data, when viewing analytics, then shows distributions, trends, and bias detection
US-M4-013 | M4 | Performance Management | Confidential Comments | Anonymous feedback and comments | P1 | 5 | 3 | HR Manager | M1 | Given review, when adding comments, then anonymity setting respected throughout process
US-M4-014 | M4 | Performance Management | Mobile Review Experience | Review and rate from mobile | P1 | 5 | 3 | Line Manager | M11 | Given review cycle, when on mobile, then full review functionality matches web
US-M4-015 | M4 | Performance Management | Performance Dispute Resolution | Appeal and challenge rating process | P2 | 5 | 3 | HR Manager | M1 | Given disputed rating, when employee appeals, then routes to HR review with documentation
US-M5-001 | M5 | Training & Development | Learning Management System | Host and assign courses | P0 | 13 | 3 | HR Manager | M1 | Given course library, when assigning, then tracks enrollment, progress, and completion
US-M5-002 | M5 | Training & Development | Course Catalog Builder | Create and manage course library | P0 | 8 | 3 | HR Manager |  | Given content, when building catalog, then organizes by category, level, and duration
US-M5-003 | M5 | Training & Development | Competency-Based Learning Paths | Map courses to competencies | P0 | 8 | 3 | HR Manager | M4 | Given competency gap, when creating path, then sequences courses to address gap
US-M5-004 | M5 | Training & Development | Skills Assessment Module | Test knowledge via quizzes and exams | P0 | 8 | 3 | HR Manager | M1 | Given course, when completing, then quiz validates mastery with immediate feedback
US-M5-005 | M5 | Training & Development | Instructor-Led Training Module | Schedule and manage instructor training | P0 | 8 | 3 | HR Manager | M1 | Given training schedule, when registering, then attendees get reminders and materials
US-M5-006 | M5 | Training & Development | Training Budget Manager | Allocate and track L&D spend | P0 | 5 | 3 | HR Manager | M13 | Given annual budget, when allocating, then tracks spend against limit per employee/department
US-M5-007 | M5 | Training & Development | Training Library Integration | Connect to external course providers | P0 | 8 | 3 | HR Manager |  | Given third-party provider, when integrating, then courses appear in catalog with auto-sync
US-M5-008 | M5 | Training & Development | Certification Tracking | Monitor required certifications | P0 | 5 | 3 | HR Manager | M1 | Given certification requirement, when tracking, then alerts on expiry and renewal deadlines
US-M5-009 | M5 | Training & Development | Training Effectiveness Survey | Post-training feedback and impact | P0 | 5 | 3 | HR Manager |  | Given completed training, when surveyed, then measures satisfaction and on-job application
US-M5-010 | M5 | Training & Development | Mentorship Platform | Pair mentors and mentees | P0 | 8 | 3 | HR Manager | M1 | Given mentee profile, when matching, then pairs with mentor and tracks meetings
US-M5-011 | M5 | Training & Development | Learning Analytics Dashboard | Training ROI and engagement metrics | P1 | 8 | 3 | HR Manager | M9 | Given training data, when viewing dashboard, then shows completion rates, engagement, and ROI
US-M5-012 | M5 | Training & Development | Mobile Learning Experience | Access courses from mobile | P1 | 5 | 3 | Outsourced Employee | M11 | Given enrolled course, when on mobile, then all video and quiz functionality works offline-capable
US-M5-013 | M5 | Training & Development | Tuition Reimbursement | Manage education spending | P1 | 5 | 3 | HR Manager | M6 | Given employee request, when submitting, then HR approves and payroll processes reimbursement
US-M5-014 | M5 | Training & Development | Compliance Training Tracker | Mandatory training enforcement | P1 | 5 | 3 | HR Manager | M1 | Given compliance course, when assigned, then blocks until completion with audit trail
US-M5-015 | M5 | Training & Development | Microlearning Module | Short-form skill-building content | P2 | 3 | 3 | Outsourced Employee |  | Given skill topic, when browsing micro-courses, then completes in under 5 minutes
US-M6-001 | M6 | Payroll & Compensation | Payroll Engine | Process monthly/weekly payroll | P0 | 13 | 1 | Payroll Specialist | M1 | Given employee data, when running payroll, then calculates gross, deductions, and net accurately
US-M6-002 | M6 | Payroll & Compensation | Compensation Structure Builder | Define salary grades and bands | P0 | 8 | 1 | HR Manager | M1 | Given role, when assigning grade, then salary band auto-populated with min/mid/max
US-M6-003 | M6 | Payroll & Compensation | Salary Review Manager | Manage merit increases and promotions | P0 | 8 | 1 | HR Manager | M4 | Given performance rating, when running salary review, then suggested increases calculated
US-M6-004 | M6 | Payroll & Compensation | Deduction Management | Configure tax, insurance, loan deductions | P0 | 8 | 1 | Payroll Specialist | M1 | Given deduction rule, when configured, then applies consistently across payroll runs
US-M6-005 | M6 | Payroll & Compensation | Expense Reimbursement | Process reimbursement requests | P0 | 8 | 1 | HR Manager | M1 | Given receipt submission, when approved, then reimbursement added to next paycheck
US-M6-006 | M6 | Payroll & Compensation | Bonus & Commission Engine | Calculate variable pay | P0 | 13 | 1 | Payroll Specialist | M1,M4 | Given bonus formula, when processing, then calculates and applies to pay accurately
US-M6-007 | M6 | Payroll & Compensation | Salary Benchmarking | Compare internal vs. market rates | P0 | 8 | 1 | HR Manager | M1 | Given market data, when running benchmark, then highlights overpaid/underpaid positions
US-M6-008 | M6 | Payroll & Compensation | Equity Management | Track stock options and RSUs | P0 | 8 | 1 | HR Manager | M1 | Given vesting schedule, when applied, then tracks vesting and vest date calculations
US-M6-009 | M6 | Payroll & Compensation | Tax Compliance Engine | Generate tax forms and filings | P0 | 13 | 1 | Payroll Specialist | M1 | Given payroll data, when generating forms, then produces accurate tax filings (W2s, 1099s, etc)
US-M6-010 | M6 | Payroll & Compensation | Pay Stub Generator | Digital pay stubs with details | P0 | 5 | 1 | Outsourced Employee | M1 | Given payroll processed, when accessing pay stub, then shows gross, deductions, and net
US-M6-011 | M6 | Payroll & Compensation | Currency & Multi-Country Support | Handle multiple currencies and locales | P0 | 13 | 1 | Payroll Specialist | M1 | Given employee in different country, when processing, then applies correct tax and currency rules
US-M6-012 | M6 | Payroll & Compensation | Payroll Analytics | Labor cost and payroll metrics | P1 | 8 | 1 | HR Manager | M9 | Given payroll data, when viewing analytics, then shows labor cost, headcount spend, turnover cost
US-M6-013 | M6 | Payroll & Compensation | Direct Deposit Setup | Manage employee bank accounts | P1 | 5 | 1 | Payroll Specialist | M1 | Given bank details, when configured, then ACH transfers process correctly
US-M6-014 | M6 | Payroll & Compensation | Audit Trail & Compliance | Full payroll audit and compliance logs | P1 | 5 | 1 | Payroll Specialist | M1 | Given payroll processed, when auditing, then shows all changes with user, timestamp, reason
US-M6-015 | M6 | Payroll & Compensation | Mobile Compensation View | View compensation details on mobile | P1 | 3 | 1 | Outsourced Employee | M11 | Given mobile access, when viewing compensation, then shows salary, benefits, and historical data
US-M7-001 | M7 | Benefits Administration | Benefits Enrollment Engine | Annual open enrollment with elections | P0 | 13 | 2 | HR Manager | M1,M6 | Given benefit plans, when opening enrollment, then employees select and system updates M6 deductions
US-M7-002 | M7 | Benefits Administration | Benefits Plan Configurator | Define benefit plans and rates | P0 | 8 | 2 | HR Manager | M1 | Given benefit type, when configuring, then sets eligibility, coverage levels, and costs
US-M7-003 | M7 | Benefits Administration | Insurance Integration | Connect to insurance providers | P0 | 8 | 2 | HR Manager | M1 | Given insurance provider, when integrating, then syncs enrollment and claims data
US-M7-004 | M7 | Benefits Administration | Benefits Communication Hub | Publish plan docs and FAQs | P0 | 5 | 2 | HR Manager | M1 | Given benefit plan, when publishing, then employees see summaries and docs in self-service
US-M7-005 | M7 | Benefits Administration | Dependent Management | Add and manage dependents | P0 | 5 | 2 | Outsourced Employee | M1 | Given dependent info, when submitting, then validates relationship and adds to benefits
US-M7-006 | M7 | Benefits Administration | Life Event Management | Track qualifying life events | P0 | 8 | 2 | HR Manager | M1 | Given life event (marriage, birth), when reported, then opens enrollment window for affected benefits
US-M7-007 | M7 | Benefits Administration | COBRA Administration | Manage COBRA continuation coverage | P0 | 8 | 2 | HR Manager | M1,M3 | Given termination, when offboarding, then COBRA eligibility calculated and notice sent
US-M7-008 | M7 | Benefits Administration | FSA/HSA Management | Flexible spending account handling | P0 | 8 | 2 | HR Manager | M1,M6 | Given FSA election, when processing, then deductions applied and claims processed
US-M7-009 | M7 | Benefits Administration | Wellness Program Manager | Create wellness initiatives | P0 | 8 | 2 | HR Manager | M1 | Given wellness program, when tracking, then records participation and incentive payouts
US-M7-010 | M7 | Benefits Administration | Benefits Portal | Self-service benefits management | P0 | 5 | 2 | Outsourced Employee | M1 | Given employee, when accessing portal, then views coverage, claims, and can make elections
US-M7-011 | M7 | Benefits Administration | Benefits Analytics | Utilization and cost analysis | P1 | 8 | 2 | HR Manager | M9 | Given benefits data, when viewing analytics, then shows enrollment rates, utilization, costs
US-M7-012 | M7 | Benefits Administration | Retirement Plan Admin | Manage 401k/pension plans | P1 | 8 | 2 | HR Manager | M1,M6 | Given retirement plan, when processing, then contributions calculated and submitted to provider
US-M7-013 | M7 | Benefits Administration | Benefits Comparison Tool | Help employees choose plans | P1 | 5 | 2 | Outsourced Employee | M1 | Given benefit options, when comparing, then shows side-by-side costs and coverage
US-M7-014 | M7 | Benefits Administration | Mobile Benefits View | Access benefits on mobile | P1 | 3 | 2 | Outsourced Employee | M11 | Given mobile app, when viewing benefits, then access same portal functionality
US-M7-015 | M7 | Benefits Administration | Compliance Reporting | Generate ACA and benefit compliance reports | P1 | 8 | 2 | HR Manager | M1 | Given compliance rules, when generating report, then produces accurate 5500, 1095-C filings
US-M8-001 | M8 | Contractor Management | Contractor Onboarding | Simplified contractor intake | P0 | 8 | 2 | HR Manager | M3 | Given contractor details, when onboarding, then collects tax info and creates lightweight profile
US-M8-002 | M8 | Contractor Management | Statement of Work Builder | Template and e-sign SOWs | P0 | 8 | 2 | HR Manager |  | Given terms, when creating SOW, then generates doc with merge fields and collects signature
US-M8-003 | M8 | Contractor Management | Contractor Eligibility Check | Verify independent contractor status | P0 | 5 | 2 | HR Manager |  | Given contractor details, when flagged, then shows compliance risk assessment
US-M8-004 | M8 | Contractor Management | Invoice Processing | Receive, approve, and pay invoices | P0 | 8 | 2 | HR Manager | M13 | Given invoice, when submitted, then routes to approver and schedules payment
US-M8-005 | M8 | Contractor Management | Contractor Time Tracking | Log hours and billable time | P0 | 5 | 2 | Outsourced Employee | M1 | Given task, when logging time, then records hours against contractor rate
US-M8-006 | M8 | Contractor Management | Rate Card Management | Define contractor billing rates | P0 | 5 | 2 | HR Manager |  | Given rate card, when applying, then calculates contractor pay automatically
US-M8-007 | M8 | Contractor Management | Contractor Expense Tracking | Collect and reimburse expenses | P0 | 5 | 2 | Outsourced Employee | M1 | Given receipt, when submitting, then expenses add to invoice for approval
US-M8-008 | M8 | Contractor Management | Tax Form Generation (1099) | Auto-generate and file 1099s | P0 | 8 | 2 | HR Manager | M6 | Given contractor payments, when year-end, then 1099 generated with accurate totals
US-M8-009 | M8 | Contractor Management | Contractor Database | Searchable contractor registry | P0 | 5 | 2 | HR Manager |  | Given previous contractors, when searching, then filters by skill, rate, and availability
US-M8-010 | M8 | Contractor Management | Skills & Certifications Tracking | Record contractor skills and certs | P0 | 5 | 2 | HR Manager | M1 | Given contractor profile, when adding skills, then searchable and filters by competency
US-M8-011 | M8 | Contractor Management | Contractor Analytics | Cost and engagement metrics | P1 | 8 | 2 | HR Manager | M9 | Given contractor data, when viewing analytics, then shows spend, engagement, and utilization
US-M8-012 | M8 | Contractor Management | Compliance Monitoring | Monitor contractor compliance | P1 | 5 | 2 | HR Manager | M1 | Given compliance rules, when monitoring, then flags issues (insurance, certifications, etc)
US-M8-013 | M8 | Contractor Management | Background Check Integration | Order and track background checks | P1 | 5 | 2 | HR Manager |  | Given contractor, when ordering check, then results feed to profile with compliance status
US-M8-014 | M8 | Contractor Management | Mobile Invoice Submission | Submit invoices from mobile | P1 | 3 | 2 | Outsourced Employee | M11 | Given mobile app, when submitting invoice, then same workflow as web
US-M8-015 | M8 | Contractor Management | Contractor Self-Service Portal | Access personal contractor info | P1 | 5 | 2 | Outsourced Employee |  | Given contractor login, when accessing portal, then views invoices, payments, and profile
US-M9-001 | M9 | Analytics & Reporting | Analytics Dashboard Hub | Central analytics and reporting | P0 | 8 | 4 | HR Director | M1,M6 | Given HR data, when viewing hub, then displays key metrics and KPIs
US-M9-002 | M9 | Analytics & Reporting | Custom Report Builder | Drag-drop report creation | P0 | 13 | 4 | HR Manager | M1 | Given fields, when building report, then creates custom SQL-free queries
US-M9-003 | M9 | Analytics & Reporting | Data Export (CSV/PDF) | Export reports in multiple formats | P0 | 5 | 4 | HR Manager |  | Given report, when exporting, then generates clean CSV or PDF
US-M9-004 | M9 | Analytics & Reporting | Headcount Analytics | Track headcount over time | P0 | 8 | 4 | HR Director | M1 | Given workforce data, when viewing, then shows headcount trends and forecasts
US-M9-005 | M9 | Analytics & Reporting | Turnover Analytics | Analyze turnover and retention | P0 | 8 | 4 | HR Director | M1,M3 | Given termination data, when analyzing, then shows turnover rate, cost, and trends
US-M9-006 | M9 | Analytics & Reporting | Diversity & Inclusion Metrics | Track D&I statistics | P0 | 8 | 4 | HR Director | M1 | Given demographic data, when viewing, then shows diversity metrics and trends
US-M9-007 | M9 | Analytics & Reporting | Compensation Analytics | Salary, equity, benefits spend | P0 | 13 | 4 | HR Manager | M6 | Given payroll data, when analyzing, then shows spend, equity ratios, and benchmarks
US-M9-008 | M9 | Analytics & Reporting | Engagement Sentiment Analysis | Analyze survey sentiment | P0 | 8 | 4 | HR Director | M1 | Given feedback data, when analyzing, then shows sentiment trends and themes
US-M9-009 | M9 | Analytics & Reporting | Predictive Attrition Model | AI-based turnover prediction | P0 | 13 | 4 | HR Director | M1 | Given employee data, when scoring, then predicts attrition risk with factors
US-M9-010 | M9 | Analytics & Reporting | Org Structure Analytics | Analyze hierarchy and structure | P0 | 8 | 4 | HR Director | M1 | Given org chart, when analyzing, then shows span of control, level distribution
US-M9-011 | M9 | Analytics & Reporting | BI Integration (Tableau/PowerBI) | Connect to BI platforms | P0 | 8 | 4 | HR Director |  | Given BI connector, when syncing, then data updates and visualizations refresh
US-M9-012 | M9 | Analytics & Reporting | Scheduled Report Distribution | Auto-email reports on schedule | P1 | 5 | 4 | HR Manager |  | Given report, when scheduling, then sends to recipients weekly/monthly automatically
US-M9-013 | M9 | Analytics & Reporting | Drill-Down Analytics | Explore data hierarchically | P1 | 8 | 4 | HR Manager | M1 | Given department view, when drilling down, then shows team and individual data
US-M9-014 | M9 | Analytics & Reporting | Compliance Reporting | Generate compliance reports | P1 | 8 | 4 | HR Director | M1 | Given compliance rules, when generating, then shows status of regulations and actions
US-M9-015 | M9 | Analytics & Reporting | Mobile Analytics Dashboard | View analytics on mobile | P1 | 5 | 4 | HR Director | M11 | Given mobile app, when viewing, then displays key dashboards responsively

## Module Summary
Module | Module Name | Phase | Total Features | P0 Count | P1 Count | P2 Count | Total Story Points | Key Dependencies
M1 | Core HRIS | 1 | 15 | 11 | 4 | 0 | 107 | M10, M11, M3, M4, M6, M9
M10 | System Administration | 1 | 15 | 14 | 1 | 0 | 123
M11 | Mobile Application | 3 | 15 | 11 | 4 | 0 | 112 | M1, M10, M9
M12 | Client Portal | 3 | 15 | 11 | 4 | 0 | 93 | M1, M11, M13, M2, M4, M6, M9
M13 | Billing & Usage | 4 | 15 | 12 | 3 | 0 | 117 | M1, M12, M9
M2 | Recruitment & ATS | 2 | 15 | 10 | 5 | 0 | 104 | M1, M12, M3, M9
M3 | Onboarding & Offboarding | 2 | 15 | 8 | 6 | 1 | 91 | M1, M10, M12, M6
M4 | Performance Management | 3 | 15 | 10 | 4 | 1 | 104 | M1, M11, M5, M9
M5 | Training & Development | 3 | 15 | 10 | 4 | 1 | 102 | M1, M11, M13, M4, M6, M9
M6 | Payroll & Compensation | 1 | 15 | 11 | 4 | 0 | 126 | M1, M11, M4, M9
M7 | Benefits Administration | 2 | 15 | 10 | 5 | 0 | 108 | M1, M11, M3, M6, M9
M8 | Contractor Management | 2 | 15 | 10 | 5 | 0 | 88 | M1, M11, M13, M3, M6, M9
M9 | Analytics & Reporting | 4 | 15 | 11 | 4 | 0 | 126 | M1, M11, M3, M6
| TOTALS |  | 195 | 139 | 53 | 3 | 1401

## Priority Matrix
Module | P0 | P1 | P2 | Total
M1 | 11 | 4 | 0 | 15
M10 | 14 | 1 | 0 | 15
M11 | 11 | 4 | 0 | 15
M12 | 11 | 4 | 0 | 15
M13 | 12 | 3 | 0 | 15
M2 | 10 | 5 | 0 | 15
M3 | 8 | 6 | 1 | 15
M4 | 10 | 4 | 1 | 15
M5 | 10 | 4 | 1 | 15
M6 | 11 | 4 | 0 | 15
M7 | 10 | 5 | 0 | 15
M8 | 10 | 5 | 0 | 15
M9 | 11 | 4 | 0 | 15

## Phase Roadmap
PHASE 1: Foundation: Core HRIS, Payroll, System Admin - Go-live
Feature ID | Feature Name | Story Points
US-M1-001 | Employee 360 Profile | 8
US-M1-002 | Org Chart Navigator | 8
US-M1-003 | Bulk Employee Import | 8
US-M1-004 | Leave Workflow Engine | 13
US-M1-005 | Self-Service Profile | 5
US-M1-006 | Document Vault | 8
US-M1-007 | Contract Management | 8
US-M1-008 | Team Dashboard | 5
US-M1-009 | Workforce Analytics Widget | 8
US-M1-010 | Attendance Tracking | 8
US-M1-011 | Position Management | 5
US-M1-012 | Mobile Leave Request | 5
US-M1-013 | Custom Fields Engine | 8
US-M1-014 | Compliance Dashboard | 5
US-M1-015 | Delegation of Authority | 5
US-M10-001 | Multi-Tenant Architecture | 13
US-M10-002 | User Access Control (RBAC) | 13
US-M10-003 | SSO Integration | 8
US-M10-004 | Audit Logging System | 8
US-M10-005 | Data Backup & Recovery | 8
US-M10-006 | API Key Management | 5
US-M10-007 | Webhook Configuration | 8
US-M10-008 | Data Migration Tools | 13
US-M10-009 | System Health Monitoring | 8
US-M10-010 | Feature Flags & Toggles | 5
US-M10-011 | Email Configuration | 5
US-M10-012 | Two-Factor Authentication | 5
US-M10-013 | Encryption & Data Security | 8
US-M10-014 | System Configuration Dashboard | 8
US-M10-015 | Rate Limiting & DDoS Protection | 8
US-M6-001 | Payroll Engine | 13
US-M6-002 | Compensation Structure Builder | 8
US-M6-003 | Salary Review Manager | 8
US-M6-004 | Deduction Management | 8
US-M6-005 | Expense Reimbursement | 8
US-M6-006 | Bonus & Commission Engine | 13
US-M6-007 | Salary Benchmarking | 8
US-M6-008 | Equity Management | 8
US-M6-009 | Tax Compliance Engine | 13
US-M6-010 | Pay Stub Generator | 5
US-M6-011 | Currency & Multi-Country Support | 13
US-M6-012 | Payroll Analytics | 8
US-M6-013 | Direct Deposit Setup | 5
US-M6-014 | Audit Trail & Compliance | 5
US-M6-015 | Mobile Compensation View | 3
Phase 1 Total Story Points: |  | 356
PHASE 2: Expansion (+3 months): Recruitment, Onboarding, Benefits, Contractors
Feature ID | Feature Name | Story Points
US-M2-001 | Job Requisition Builder | 8
US-M2-002 | Multi-Channel Posting | 8
US-M2-003 | AI CV Screening | 13
US-M2-004 | Candidate Pipeline Kanban | 8
US-M2-005 | Candidate Review Portal | 5
US-M2-006 | Interview Scheduler | 8
US-M2-007 | Offer Generation Engine | 8
US-M2-008 | E-Signature Integration | 5
US-M2-009 | Hiring Request Intake | 5
US-M2-010 | SLA Tracking Dashboard | 5
US-M2-011 | Candidate Communication Hub | 5
US-M2-012 | Recruitment Analytics | 8
US-M2-013 | Talent Pool Database | 5
US-M2-014 | Interview Feedback Forms | 5
US-M2-015 | LinkedIn Integration | 8
US-M3-001 | Onboarding Template Builder | 8
US-M3-002 | Dual-Lane Workflow Engine | 13
US-M3-003 | Pre-boarding Portal | 5
US-M3-004 | Task Assignment Engine | 8
US-M3-005 | Access Provisioning Trigger | 5
US-M3-006 | Offboarding Workflow Engine | 8
US-M3-007 | Exit Interview Module | 5
US-M3-008 | Onboarding Progress Tracker | 5
US-M3-009 | Document Collection Checklist | 5
US-M3-010 | Welcome Kit & Orientation | 3
US-M3-011 | Cross-Lane Dependencies | 8
US-M3-012 | Client Onboarding Dashboard | 5
US-M3-013 | Equipment Tracking | 5
US-M3-014 | Rehire Workflow | 5
US-M3-015 | Buddy/Mentor Assignment | 3
US-M7-001 | Benefits Enrollment Engine | 13
US-M7-002 | Benefits Plan Configurator | 8
US-M7-003 | Insurance Integration | 8
US-M7-004 | Benefits Communication Hub | 5
US-M7-005 | Dependent Management | 5
US-M7-006 | Life Event Management | 8
US-M7-007 | COBRA Administration | 8
US-M7-008 | FSA/HSA Management | 8
US-M7-009 | Wellness Program Manager | 8
US-M7-010 | Benefits Portal | 5
US-M7-011 | Benefits Analytics | 8
US-M7-012 | Retirement Plan Admin | 8
US-M7-013 | Benefits Comparison Tool | 5
US-M7-014 | Mobile Benefits View | 3
US-M7-015 | Compliance Reporting | 8
US-M8-001 | Contractor Onboarding | 8
US-M8-002 | Statement of Work Builder | 8
US-M8-003 | Contractor Eligibility Check | 5
US-M8-004 | Invoice Processing | 8
US-M8-005 | Contractor Time Tracking | 5
US-M8-006 | Rate Card Management | 5
US-M8-007 | Contractor Expense Tracking | 5
US-M8-008 | Tax Form Generation (1099) | 8
US-M8-009 | Contractor Database | 5
US-M8-010 | Skills & Certifications Tracking | 5
US-M8-011 | Contractor Analytics | 8
US-M8-012 | Compliance Monitoring | 5
US-M8-013 | Background Check Integration | 5
US-M8-014 | Mobile Invoice Submission | 3
US-M8-015 | Contractor Self-Service Portal | 5
Phase 2 Total Story Points: |  | 391
PHASE 3: Maturity (+3 months): Performance, Training, Mobile, Client Portal
Feature ID | Feature Name | Story Points
US-M11-001 | iOS Native App | 13
US-M11-002 | Android Native App | 13
US-M11-003 | Mobile Authentication | 8
US-M11-004 | Push Notifications | 8
US-M11-005 | Offline Sync | 13
US-M11-006 | Mobile Navigation | 5
US-M11-007 | Camera Integration | 5
US-M11-008 | Location Services | 8
US-M11-009 | App Update Management | 5
US-M11-010 | Mobile Permissions | 5
US-M11-011 | Dark Mode Support | 3
US-M11-012 | Mobile Performance | 8
US-M11-013 | Mobile Analytics | 5
US-M11-014 | App Store Deployment | 8
US-M11-015 | Mobile Accessibility | 5
US-M12-001 | Client Portal Home | 8
US-M12-002 | Employee Directory Access | 5
US-M12-003 | Leave Approval Portal | 8
US-M12-004 | Attendance Reporting | 5
US-M12-005 | Payroll Summary View | 5
US-M12-006 | Performance Review Submission | 8
US-M12-007 | Invoice Tracking | 5
US-M12-008 | Support Ticket System | 8
US-M12-009 | Document Upload Portal | 5
US-M12-010 | Communication Center | 5
US-M12-011 | Custom Report Access | 5
US-M12-012 | Hiring Request Portal | 8
US-M12-013 | Org Structure Management | 8
US-M12-014 | Client Portal Mobile | 5
US-M12-015 | Data Export Requests | 5
US-M4-001 | Goal Setting Framework | 8
US-M4-002 | 360 Feedback Engine | 13
US-M4-003 | Performance Review Builder | 8
US-M4-004 | Calibration Workshop Module | 8
US-M4-005 | Competency Framework | 8
US-M4-006 | Performance Improvement Plan | 5
US-M4-007 | Peer Recognition | 5
US-M4-008 | Performance Rating Widget | 5
US-M4-009 | Succession Planning Bench | 8
US-M4-010 | Development Plan Manager | 8
US-M4-011 | Review Cycle Manager | 5
US-M4-012 | Performance Analytics | 8
US-M4-013 | Confidential Comments | 5
US-M4-014 | Mobile Review Experience | 5
US-M4-015 | Performance Dispute Resolution | 5
US-M5-001 | Learning Management System | 13
US-M5-002 | Course Catalog Builder | 8
US-M5-003 | Competency-Based Learning Paths | 8
US-M5-004 | Skills Assessment Module | 8
US-M5-005 | Instructor-Led Training Module | 8
US-M5-006 | Training Budget Manager | 5
US-M5-007 | Training Library Integration | 8
US-M5-008 | Certification Tracking | 5
US-M5-009 | Training Effectiveness Survey | 5
US-M5-010 | Mentorship Platform | 8
US-M5-011 | Learning Analytics Dashboard | 8
US-M5-012 | Mobile Learning Experience | 5
US-M5-013 | Tuition Reimbursement | 5
US-M5-014 | Compliance Training Tracker | 5
US-M5-015 | Microlearning Module | 3
Phase 3 Total Story Points: |  | 411
PHASE 4: Advanced (+3 months): Analytics, Billing
Feature ID | Feature Name | Story Points
US-M13-001 | Billing Engine | 13
US-M13-002 | Usage Tracking | 8
US-M13-003 | Subscription Management | 8
US-M13-004 | Add-On Management | 5
US-M13-005 | Pricing Rule Engine | 8
US-M13-006 | Payment Processing | 13
US-M13-007 | Invoice Management Portal | 5
US-M13-008 | Credit & Refund Processing | 8
US-M13-009 | Discount Management | 5
US-M13-010 | Billing Analytics | 8
US-M13-011 | Dunning Management | 5
US-M13-012 | Tax Calculation | 13
US-M13-013 | Contract Management | 8
US-M13-014 | Billing Notifications | 5
US-M13-015 | Billing Compliance Reporting | 5
US-M9-001 | Analytics Dashboard Hub | 8
US-M9-002 | Custom Report Builder | 13
US-M9-003 | Data Export (CSV/PDF) | 5
US-M9-004 | Headcount Analytics | 8
US-M9-005 | Turnover Analytics | 8
US-M9-006 | Diversity & Inclusion Metrics | 8
US-M9-007 | Compensation Analytics | 13
US-M9-008 | Engagement Sentiment Analysis | 8
US-M9-009 | Predictive Attrition Model | 13
US-M9-010 | Org Structure Analytics | 8
US-M9-011 | BI Integration (Tableau/PowerBI) | 8
US-M9-012 | Scheduled Report Distribution | 5
US-M9-013 | Drill-Down Analytics | 8
US-M9-014 | Compliance Reporting | 8
US-M9-015 | Mobile Analytics Dashboard | 5
Phase 4 Total Story Points: |  | 243

## Dependencies
Module Dependencies | M1 | M10 | M11 | M12 | M13 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9
M1 | bar: M10 to M11; M3 to M4; M6; M9
M10
M11 | bar: M1 to M10; M9
M12 | bar: M1; M11; M13 to M2; M4; M6; M9
M13 | bar: M1; M12; M9
M2 | bar: M1; M12; M3; M9
M3 | bar: M1 to M10; M12; M6
M4 | bar: M1; M11; M5; M9
M5 | bar: M1; M11; M13; M4; M6; M9
M6 | bar: M1; M11; M4; M9
M7 | bar: M1; M11; M3; M6; M9
M8 | bar: M1; M11; M13; M3; M6; M9
M9 | bar: M1; M11; M3; M6