## Slide 1
PRAXION HROS
Project Organization & Stakeholders
Roles, Responsibilities & Module Ownership
April 2026

## Slide 2
PROJECT GOVERNANCE STRUCTURE
STEERING COMMITTEE
Chairman, CEO, HR Director
PROJECT SPONSOR
Executive accountability
PRODUCT OWNER
Sabry — Requirements & delivery
TECHNICAL LEAD
Architecture & code
UX/UI LEAD
Design & experience
QA LEAD
Quality & testing
CHANGE MGMT
Training & adoption
Dev Team
3–7 Developers + 1 Mobile Dev
Design Team
2 Designers (UX + UI)
Test Team
2–3 QA Engineers
Training Team
Communications
Note: Role-level structure shown. Specific names to be confirmed during Phase 1 kickoff. Team scales from ~5 in Phase 1 to ~10–12 by Phase 3.
SCRUM MASTER
Sprint facilitation & impediments

## Slide 3
CORE PROJECT TEAM ROLES
Product Owner
Defines product vision, prioritizes backlog, writes acceptance criteria, makes scope decisions, represents business stakeholders in sprint ceremonies. Owns the product roadmap.
Technical Lead
Makes architecture decisions, conducts code reviews, mentors developers, ensures technical quality, manages tech debt, and maintains development standards.
UX/UI Lead
Owns the design system, creates wireframes and prototypes, conducts usability testing, ensures WCAG accessibility, and manages the master layout approach.
QA Lead
Defines test strategy, creates test plans and automation, manages bug tracking, conducts regression testing, and gates releases for quality.
Scrum Master
Facilitates sprint ceremonies (planning, standups, reviews, retros), removes impediments, tracks velocity, and coaches the team on agile practices.
Change Management Lead
Develops training materials, manages stakeholder communications, tracks adoption metrics, handles resistance, and ensures smooth organizational transition.

## Slide 4
MODULE STAKEHOLDERS — FOUNDATION MODULES
Module
Primary Stakeholder
Business Owner
Technical Owner
Subject Matter Expert
M1: Core HRIS
HR Director
HR Ops Manager
Technical Lead
HR Specialist
M10: System Admin
IT Director
IT Manager
Technical Lead
Security Officer

## Slide 5
MODULE STAKEHOLDERS — PEOPLE MODULES
Module
Primary Stakeholder
Business Owner
Technical Owner
Subject Matter Expert
M2: Recruitment & ATS
HR Director
TA Lead
Technical Lead
Recruiter
M3: Onboarding/Offboarding
HR Director
HR Ops Manager
Technical Lead
HR Specialist
M4: Performance & KPIs
HR Director
L&D Manager
Technical Lead
HR Business Partner
M5: Training & LMS
HR Director
L&D Manager
Technical Lead
Trainer / Facilitator

## Slide 6
MODULE STAKEHOLDERS — MONEY MODULES
Module
Primary Stakeholder
Business Owner
Technical Owner
Subject Matter Expert
M6: Payroll & Compensation
Finance Director
Payroll Manager
Technical Lead
Payroll Specialist
M7: Benefits & Expenses
HR Director
Benefits Admin
Technical Lead
HR Specialist
M8: Contractor Management
Operations Director
Contractor Mgr
Technical Lead
Legal Counsel

## Slide 7
MODULE STAKEHOLDERS — INTELLIGENCE & ACCESS
Module
Primary Stakeholder
Business Owner
Technical Owner
Subject Matter Expert
M9: Analytics & Reporting
CEO / COO
Data Analyst
Technical Lead
Business Analyst
M11: Mobile App
HR Director
Product Owner
Mobile Dev Lead
UX Designer
M12: Client Portal
CEO
Client Services Mgr
Technical Lead
Account Manager
M13: Billing & Invoicing
Finance Director
Finance Manager
Technical Lead
Accountant

## Slide 8
RACI MATRIX
Responsibility Assignment for Key Decision Areas
R = Responsible (does the work) A = Accountable (final decision) C = Consulted (provides input) I = Informed (kept in the loop)
Decision Area
Steering Committee
Project Sponsor
Product Owner
Technical Lead
UX/UI Lead
QA Lead
Scope Changes / Feature Prioritization
A
C
R
C
I
I
Architecture & Technology Decisions
I
A
C
R
I
I
Budget Allocation & Spend Approval
A
R
C
I
I
I
UI/UX Design & User Experience
I
I
C
I
A
C
Release Go / No-Go Decisions
I
C
A
C
C
R
Sprint Planning & Backlog Priority
I
I
R
C
C
I
Quality Gates & Bug Severity
I
I
C
C
I
R
Vendor & Tool Selection
A
C
C
R
I
I
Data Security & Compliance
A
R
I
R
I
C

## Slide 9
COMMUNICATION PLAN
Meeting Cadence and Stakeholder Communication Framework
Meeting
Frequency
Attendees
Purpose
Output
Steering Committee
Monthly
Chairman, CEO, HR Director, Sponsor
Strategic direction, budget review, escalations, phase gates
Decision log, meeting minutes
Sprint Review & Demo
Bi-weekly
Core team, module stakeholders
Demo completed work, collect feedback, validate direction
Sprint report, feedback log
Sprint Planning
Bi-weekly
Product Owner, Tech Lead, Dev team
Define sprint scope, estimate stories, assign tasks
Sprint backlog, commitments
Daily Standup
Daily (15 min)
Dev team, Scrum Master
Progress updates, blockers, coordination
Updated task board
Stakeholder Update
Weekly (email)
All stakeholders, module owners
Status summary, risks, metrics, upcoming milestones
Status report (1-page)
Architecture Review
As needed
Tech Lead, Product Owner, Security Officer
Technical decisions, design reviews, security assessments
Architecture decision records

## Slide 10
TEAM FORMATION — NEXT STEPS
Actions to Finalize Project Organization
1
Confirm stakeholder names for each module role position
Fill placeholder roles with actual team members. Ensure each module has an identified Primary Stakeholder, Business Owner, and SME.
Week of Apr 28
2
Schedule Phase 1 kickoff meeting with confirmed team
Bring together the Core HRIS (M1) and System Admin (M10) stakeholders for a detailed requirements walkthrough.
May 5, 2026
3
Set up project communication channels
Create dedicated Slack/Teams channels: #praxion-general, #praxion-dev, #praxion-design. Set up weekly status email distribution list.
May 2026
4
Establish project tracking tools
Set up Jira/Linear for sprint management, Confluence for documentation, Figma for design collaboration.
May 2026
5
Begin Phase 1 sprint planning
Product Owner and Tech Lead collaborate on Sprint 1 backlog. Define first 2-week sprint scope and acceptance criteria.
June 2026