## Slide 1
Praxion
PHASE-1 MOBILIZATION PLAN · TECH LEAD SESSION · APRIL 2026
Let's build
Praxion HROS.
11 months · 10 modules · 6 squads · 5 functional tiers
KICK-OFF
15 May 2026
GO-LIVE
14 Mar 2027
GATES
8 · P0 → P7
OWNER
Sabry M.
PRX-MOB-P1-001 · v1.0 · Internal — Restricted
1 / 20

## Slide 2
01 · MOBILIZATION AT A GLANCE
The plan in numbers
11
MONTHS
15 May '26 → 14 Mar '27
10
MODULES
Phase-1 scope
8
GATES
P0 Mobilise → P7 Go-live
6
SQUADS
Cross-functional delivery
5
TIERS
Functional architecture
WHAT WE COMMIT TO
Functional delivery
One integrated HR operating system — Foundation · People · Money · Intelligence · Access
Statutory-correct payroll
SIA, ETA and PDP Law 151/2020 built in, not bolted on
Mobile-first for field
Arabic + English ESS on day one — 60% of workforce unlocked
Compliance by design
Audit trail · RBAC · DPIA on every module before go-live
Three golden threads throughout Phase-1: 1) Ship monthly, learn weekly 2) Real payroll is the pacemaker 3) Field-worker test = go/no-go
PRAXION HROS · Phase-1 Mobilization · PRX-MOB-P1-001 v1.0
2 / 20

## Slide 3
02 · PLATFORM ARCHITECTURE
13 integrated modules — grouped by function
FOUNDATION
M1
Core HRIS
Employee records · org · docs · audit
M10
System Admin
Users · roles · SSO · MFA · security
PEOPLE
M2
Recruitment & ATS
Job postings · interviews · offers
M3
Onboarding
Checklists · provisioning · offboarding
M4
Performance
Goals · reviews · 360 · KPIs
M5
Training & LMS
Courses · compliance · certificates
MONEY
M6
Payroll
Salary · tax · SIA · payslips · bank
M7
Benefits & Expenses
Enrolment · claims · reimbursement
M8
Contractors
Contracts · timesheets · invoices (P2)
INTELLIGENCE
M9
Analytics
Dashboards · KPIs · predictive · workforce planning
ACCESS
M11
Mobile App (ESS)
Self-service · approvals · notifications
M12
Client Portal
Multi-tenant · white-label (P2)
M13
Billing & Invoicing
Usage · invoices · subscriptions
Phase-1 scope = 10 modules (M1, M10, M2, M3, M4, M5, M6, M7, M9, M11) · M8, M12, M13 sequenced to Phase-2
PRAXION HROS · Phase-1 Mobilization · PRX-MOB-P1-001 v1.0
3 / 20

## Slide 4
03 · DESIGN PRINCIPLE
Why we group by function, not by build order
OLD VIEW — BUILD SEQUENCE
Tier 1 Foundations
M1, M10
Tier 2 Core Build
M6, M2, M3, M11
Tier 3 Module Build
M4, M5, M7, M9
Tier 4 Scale
M8, M12, M13
NEW VIEW — FUNCTIONAL TIERS
FOUNDATION
M1 · M10
PEOPLE
M2 · M3 · M4 · M5
MONEY
M6 · M7 · M8
INTELLIGENCE
M9
ACCESS
M11 · M12 · M13
01
Matches operating model
HR leaders already think in People / Money / Experience — our system mirrors their mental model.
02
Squads own tiers end-to-end
A tier-aligned squad owns data model, UI, workflow and compliance for their domain — not a horizontal slice.
03
Speaks to executives
CFO owns Money tier outcomes. CHRO owns People tier. CIO owns Foundation. Clean accountability.
Build order inside each tier is still Phase-1 → Phase-2. Functional grouping is how we think. Sequencing is how we ship.
PRAXION HROS · Phase-1 Mobilization · PRX-MOB-P1-001 v1.0
4 / 20

## Slide 5
04 · PHASE-1 JOURNEY
8 gates over 11 months — P0 Mobilise → P7 Go-live
P0
MOBILISE
Apr – May '26
4w
P1
DESIGN
May – Jul '26
8w
P2
FOUNDATION
Jul – Sep '26
8w
P3
MONEY
Sep – Nov '26
8w
P4
PEOPLE
Nov '26 – Jan '27
8w
P5
ACCESS + INTEL
Jan – Feb '27
4w
P6
HARDEN
Feb – Mar '27
3.5w
P7
GO-LIVE
14 Mar '27
D-Day
GATE OUTCOMES
P0
MOBILISE
Charter · RACI · squads · environments
P1
DESIGN
Functional spec · data model · UX · NFRs
P2
FOUNDATION
M1 Core HRIS · M10 System Admin · SSO
P3
MONEY
M6 Payroll parallel run · M7 Benefits
P4
PEOPLE
M2 ATS · M3 Onboarding · M4 Perf · M5 LMS
P5
ACCESS + INTEL
M11 Mobile ESS · M9 Analytics
P6
HARDEN
UAT · pen-test · DPIA · load · dry-run
P7
GO-LIVE
Cutover · hypercare · 30-day warranty
PRAXION HROS · Phase-1 Mobilization · PRX-MOB-P1-001 v1.0
5 / 20

## Slide 6
05 · FOUNDATION TIER
M1 Core HRIS + M10 System Admin — the platform spine
FOUNDATION
M1
Core HRIS
P2 · 15 Jul – 15 Sep '26
OWNER
HRIS Lead · 2 eng, 1 QA
OUTPUTS
Employee / org / position / contract / doc / audit entities · JML workflows · import from Excel + paper · HRIS API v1
M10
System Admin
P2 · 15 Jul – 15 Sep '26
OWNER
CISO + HRIS Lead
OUTPUTS
Identity · RBAC roles & permissions · SSO (SAML+OIDC) · MFA · audit log · backup/restore · observability
INTEGRATIONS
Active Directory / SSO IdP · email relay · file store (S3-compatible) · observability stack
RISKS TO WATCH
Data migration from legacy Excel/paper · role model too permissive · SSO IdP not ready on time
TIER KPI
M1: 100% employee data loaded with < 0.5% error
M10: SSO live · RBAC audited · zero P1 security issues
PRAXION HROS · Phase-1 Mobilization · PRX-MOB-P1-001 v1.0
6 / 20

## Slide 7
06 · PEOPLE TIER
M2 – M5 — talent lifecycle end-to-end
PEOPLE
M2
Recruitment & ATS
P4 · Nov – Dec '26
OWNER
Talent & Dev Lead
OUTPUTS
Requisition → offer · careers page · interview scorecards · offer letters · talent pool
M3
Onboarding
P4 · Nov – Dec '26
OWNER
Talent & Dev Lead
OUTPUTS
Day-1 journeys · checklist · provisioning triggers · digital document pack · offboarding checklist
M4
Performance
P4 · Dec '26 – Jan '27
OWNER
Talent & Dev Lead
OUTPUTS
Goals/OKRs · check-ins · annual review · 360 feedback · calibration · competency library
M5
Training & LMS
P4 · Dec '26 – Jan '27
OWNER
Talent & Dev Lead + Product
OUTPUTS
Course catalogue · enrolments · completions · certificates · compliance training tracking
INTEGRATIONS
Job boards (LinkedIn, Wuzzuf) · e-signature for offers · video interview · SCORM for LMS content · email + SMS
RISKS TO WATCH
Scope creep on M4 (360 is big) · SCORM content sourcing delays · email deliverability
TIER KPI
Offer → Day-1 onboarding ready: 15d → 7d
100% compliance training tracked with certificates
PRAXION HROS · Phase-1 Mobilization · PRX-MOB-P1-001 v1.0
7 / 20

## Slide 8
07 · MONEY TIER
M6 Payroll + M7 Benefits / Expenses — the pacemaker
MONEY
M6
Payroll
P3 · 15 Sep – 15 Nov '26
OWNER
Payroll Lead · 2 eng + external auditor
OUTPUTS
Egyptian statutory payroll · SIA + ETA filing · payslip generation · bank transfer files · variable pay · parallel run x3
M7
Benefits & Expenses
P3 · 15 Oct – 15 Nov '26
OWNER
Payroll Lead + HR Ops
OUTPUTS
Benefit enrolment · plan library · expense claims · reimbursement workflow · receipt capture (mobile)
M8
Contractors
P2 (Phase 2, 2027)
OWNER
Deferred
OUTPUTS
Contracts · timesheets · invoices · misclassification controls — NOT in Phase 1 scope
INTEGRATIONS
SIA API (statutory filings) · ETA e-receipts · banking file formats (CIB, NBE, QNB) · mobile OCR for receipts
RISKS TO WATCH
SIA API availability uncertain · bank file format sign-off per bank · ETA schema changes · parallel run reveals legacy errors
TIER KPI
Payroll accuracy ≥ 99.9% at cut-over
Cycle time per entity: 6d → 1d
0 late statutory filings / month
PRAXION HROS · Phase-1 Mobilization · PRX-MOB-P1-001 v1.0
8 / 20

## Slide 9
08 · INTELLIGENCE + ACCESS TIERS
M9 Analytics + M11 Mobile — how the org sees and reaches HR
INTELLIGENCE · M9 ANALYTICS
Dashboards · KPIs · workforce planning
P5 · Jan – Feb '27
Delivery window
Dashboards v1
12 pre-built HR dashboards (heads, costs, attrition, attendance, diversity, comp, training, ESS, payroll, onboarding, perf, recruitment)
Self-serve reports
Report builder — drag-drop fields, save, schedule, email distribution
Workforce planning
Heads by unit + scenario planning (±% headcount, ±% comp) — planning cycle
Predictive (stretch)
Attrition risk score per employee — if we have 6+ months of historical data
ACCESS · M11 MOBILE + M13 BILLING
Arabic-first mobile ESS · the 60% unlock
P5 · Jan – Feb '27
Delivery window
iOS + Android
Native-shell + RN core · biometric unlock · push notifications · Arabic & English
ESS MVP
Payslips · leave balances · leave request · attendance punch · directory · profile
Manager actions
Approve / reject · team view · absence overview · comp statement
Field-worker mode
Low-literacy UI · offline timesheet + expense · photo-first · voice notes (stretch)
M13 Billing (internal)
Usage tracking · subscription accounting — goes with M11 to enable internal invoicing
PRAXION HROS · Phase-1 Mobilization · PRX-MOB-P1-001 v1.0
9 / 20

## Slide 10
09 · TEAM STRUCTURE
6 squads, tier-aligned, shared platform spine
PLATFORM SQUAD
HRIS Lead / Architect
M1 · M10 · shared data model · API · observability
3 eng · 1 QA
TALENT SQUAD
Talent & Dev Lead
M2 Recruitment · M3 Onboarding
2 eng · 1 QA
GROWTH SQUAD
Talent & Dev Lead (shared)
M4 Performance · M5 Training / LMS
2 eng · 1 QA
PAYROLL SQUAD
Payroll Lead
M6 Payroll · M7 Benefits & Expenses · SIA/ETA/bank
3 eng · 1 QA · external auditor
INSIGHTS SQUAD
Product + UX (shared)
M9 Analytics · dashboards · reporting infra
1 eng · 1 data eng
EXPERIENCE SQUAD
Product + UX
M11 Mobile ESS · design system · M13 Billing
2 eng · 1 designer · 1 QA
SHARED SERVICES
Delivery + QA
Sprint cadence · release train · UAT
Security + Privacy
RBAC · DPIA · pen-test · audit log
Change + Training
Comms · champions · training pathways
Data + Migration
Legacy extract · cleanse · load · reconcile
HEADCOUNT
Core
13 FTE
Leads
5
Eng
13
QA
5
UX
2
Ext
+3
PRAXION HROS · Phase-1 Mobilization · PRX-MOB-P1-001 v1.0
10 / 20

## Slide 11
10 · RACI
Who does what across the programme
ACTIVITY
Board
Sponsor/CEO
PD (Sabry)
HRIS Lead
Payroll Lead
Talent Lead
Ext
Charter & scope
A
R
R
C
C
C
I
Data migration
I
I
A
R
C
C
C
Payroll cut-over
I
A
A
C
R
I
R
Statutory filings
I
A
C
C
R
I
C
DPIA + security
I
A
A
C
C
C
R
SSO / identity
I
C
A
R
C
I
C
Module UAT
I
I
A
C
C
C
C
Training & change
I
A
A
C
C
R
C
Budget & burn
A
A
R
I
I
I
I
Steerco reporting
I
A
R
C
C
C
I
R = Responsible · A = Accountable · C = Consulted · I = Informed (standard RACI — one A per activity)
PRAXION HROS · Phase-1 Mobilization · PRX-MOB-P1-001 v1.0
11 / 20

## Slide 12
11 · WAYS OF WORKING — CADENCE
Ceremonies · meetings · reporting rhythm
DAILY
15 min
09:15 Cairo
Squad stand-up
Each squad · blockers · focus for the day
WEEKLY
1 hr
Mon 10:00
Programme sync
All leads + PD · cross-squad dependencies · risks
WEEKLY
30 min
Fri 17:00
Exec summary
PD → CEO + sponsors · one-pager · by Friday EOD
BI-WEEKLY
2 hr
Alternating Thu
Sprint review + planning
Demo · retro · next-sprint commitments · per squad
MONTHLY
2 hr
Last Wed
Steerco
CEO · CFO · CHRO · CIO · decisions + escalations
MONTHLY
1 hr
Second Tue
Architecture council
HRIS Lead · Payroll Lead · CISO · cross-cutting design
QUARTERLY
3 hr
End of quarter
Review board
External HR + payroll + legal reviewers · compliance read
PRAXION HROS · Phase-1 Mobilization · PRX-MOB-P1-001 v1.0
12 / 20

## Slide 13
12 · ENVIRONMENTS & TOOLING
How we build, test, ship — and what runs it
DEV
Per-squad sandboxes
Ephemeral · fast feedback · feature branches
INT
Integration
Shared · cross-squad wiring · contract tests
UAT
User acceptance
Business verification · signed-off scripts
PRE-PROD
Dry-run
Mirror of prod · parallel payroll runs · data drills
PROD
Live
Cutover 14 Mar '27 · hypercare 30 days
STACK — PROPOSED (for tech-lead review)
Backend
Node.js + TypeScript · NestJS framework
Frontend
React + TypeScript · Tailwind · shadcn/ui
Mobile
React Native (shared core) · native shell for biometrics
Database
PostgreSQL 16 · row-level RBAC · partitioning for payroll
Cache / queue
Redis · BullMQ for async workflows
Storage
S3-compatible (MinIO on-prem option)
Identity
Keycloak (SSO / SAML / OIDC) · MFA · SCIM
Observability
Grafana + Loki + Tempo · Sentry for errors
CI / CD
GitHub Actions · ArgoCD · preview envs per PR
Code quality
ESLint · Prettier · SonarQube · Trivy · Snyk
Docs
Backstage for service catalogue · ADRs in-repo
PM / issues
Jira (aligned to Phase-1 Tracker WBS)
PRAXION HROS · Phase-1 Mobilization · PRX-MOB-P1-001 v1.0
13 / 20

## Slide 14
13 · DATA STRATEGY
Legacy → Praxion HROS — one reconciled source of truth
1
EXTRACT
Excel · paper · WhatsApp
Scanning · OCR · CSV export · interview-led gap fill
2
STANDARDISE
Canonical schemas
Employee ID · unit · contract · pay element taxonomy
3
CLEANSE
Fix before load
Dupes · missing fields · format · cross-field rules
4
LOAD
Staging → Praxion
Per-module loaders · idempotent · dry-run + commit phases
5
RECONCILE
Validate + sign-off
Reconciliation reports · owner sign-off · error log
MIGRATION REHEARSAL SCHEDULE — 3 DRY RUNS
Dry run 1
15 Dec 2026
Extract → load · 1 small entity · fix gaps
Dry run 2
15 Jan 2027
All entities · parallel payroll run · reconcile
Dry run 3
15 Feb 2027
Full rehearsal · cutover script · rollback drill
DATA VOLUMES — ESTIMATED
Employees
~50,000
Pay elements
~150 per entity
Historical payroll
24 months
Documents
~400,000
Entities
~30
PRAXION HROS · Phase-1 Mobilization · PRX-MOB-P1-001 v1.0
14 / 20

## Slide 15
14 · INTEGRATION LANDSCAPE
External systems we connect to — with owners and deadlines
MONEY
Q4 2026
SIA API
Legal + Payroll
Statutory social-insurance filings (Form 2, Form 6)
MONEY
Q4 2026
ETA e-receipts
Finance
Electronic tax receipts · withholding integration
MONEY
Q1 2027
Banking files
Finance
Salary transfer file formats (CIB, NBE, QNB, HSBC)
FOUNDATION
Q1 2027
PDP DPIA
Legal + CISO
Data Protection Impact Assessment · Law 151/2020
FOUNDATION
Feb 2027
Pen-test vendor
CISO
External security assessment before go-live
FOUNDATION
Q3 2026
SSO IdP
CIO
SAML/OIDC identity provider (Azure AD / Okta)
PEOPLE
Q4 2026
Job boards
Talent Lead
LinkedIn · Wuzzuf · indeed API integration
PEOPLE
Q4 2026
E-signature
Talent Lead
DocuSign or equivalent for offers + contracts
PEOPLE
Q1 2027
SCORM content
Talent Lead
LMS-standard compliance training content
ACCESS
Q1 2027
SMS / push
Product
Notification channels for mobile ESS
PRAXION HROS · Phase-1 Mobilization · PRX-MOB-P1-001 v1.0
15 / 20

## Slide 16
15 · WAYS OF WORKING
Definition of Ready · Definition of Done · PR standards
DEFINITION OF READY
User story has acceptance criteria written
Dependencies identified + green-lit
Designs attached (where UI involved)
Test cases outlined
Estimate agreed by squad
Compliance touchpoints flagged (PII, audit, statutory)
DEFINITION OF DONE
Code merged to main · passing CI
Unit + integration tests green
Accessibility check passed (WCAG 2.1 AA)
Arabic + English strings in place
Observability instrumentation added
Docs updated · changelog entry · demo'd in review
PR STANDARDS
Conventional commits · semantic PR titles
< 400 LOC per PR · else break up
≥ 2 approvals · 1 from another squad for cross-cut
All checks green before merge
Squashed commit on merge · auto-linked to Jira ticket
ADR filed for architectural decisions
PRAXION HROS · Phase-1 Mobilization · PRX-MOB-P1-001 v1.0
16 / 20

## Slide 17
16 · 30 / 60 / 90 DAYS
The first 90 days of Phase-1 — P0 Mobilise + start of P1 Design
FIRST 30 DAYS
15 May – 15 Jun '26
ALIGN · TEAM · ENVIRONMENTS
Charter & RACI signed by all leads
6 squads staffed · leads in seat
Dev + Int environments stood up
Jira project live · WBS loaded
Kick-off all-hands (Cairo, onsite)
Vendor contracts signed (pen-test, auditor)
Decision log started · ADR #1-5 filed
DAYS 31 – 60
15 Jun – 15 Jul '26
DESIGN · DATA MODEL · DEPENDENCIES
Functional spec for M1, M10 signed
Canonical data model v1 reviewed
SSO IdP procurement kicked off
SIA API access request raised
Migration extract scripts drafted
Design system v1 live in Figma
First customer councils (pilot entity)
DAYS 61 – 90
15 Jul – 15 Aug '26
FOUNDATION BUILD STARTS
M1 Core HRIS sprint 1-2 complete
M10 SSO + RBAC sprint 1 complete
First internal demo (week 8)
Dry-run migration in staging
Compliance kick-off: DPIA scoping
Field-worker journey prototyped
First steerco reporting cycle complete
PRAXION HROS · Phase-1 Mobilization · PRX-MOB-P1-001 v1.0
17 / 20

## Slide 18
17 · RISKS & DEPENDENCIES
What could derail Phase-1 — and how we're pre-empting it
Data migration from legacy
HIGH · HIGH
Excel + paper + WhatsApp → structured HRIS; dirty data is the default
MITIGATION
3 dry runs · staging reconciliation · owner sign-off per entity
Payroll accuracy at cut-over
MED · HIGH
Legacy calculations may have undocumented quirks
MITIGATION
3 parallel runs · external auditor sign-off · rollback plan
Field-worker adoption
HIGH · MED
60% of users have no desktop, mixed literacy, Arabic-only
MITIGATION
Mobile-first ESS · voice notes · champions on the ground · multilingual
Scope aggression vs. team size
HIGH · HIGH
6-lead programme delivering 10 modules in 11 months
MITIGATION
Ruthless scope discipline · stretch items clearly marked · fortnightly reprioritisation
External API availability
MED · HIGH
SIA, ETA, banking: if any of these slip, payroll slips
MITIGATION
Raise access requests in P0 · mock layers + adapters · escalation via Legal/Finance sponsors
Key-person concentration
MED · MED
Small team · illness or attrition in core squad delays gates
MITIGATION
Cross-training plan · pair-programming · external bench agreements
PRAXION HROS · Phase-1 Mobilization · PRX-MOB-P1-001 v1.0
18 / 20

## Slide 19
18 · SUCCESS CRITERIA
How we'll know Phase-1 worked — KPIs by tier
DELIVERY
Go-live date
14 Mar 2027
No slip > 2 weeks
Scope completion
100% of Phase-1
All 10 modules live
Defect escape
< 2 P1 / month
After 30-day hypercare
MONEY TIER
Payroll accuracy
≥ 99.9%
vs. parallel-run baseline
Cycle time
6d → 1d
Per entity, per month
Statutory
0 late
SIA + ETA filings / month
PEOPLE TIER
Offer → Day-1
15d → 7d
Onboarding time-to-ready
Training
≥ 95%
Core-role completion pre-GL
Manager adoption
≥ 75%
Requests via system, not email
ACCESS TIER
ESS activation
≥ 85%
Within 90d post-go-live
Arabic usage
≥ 40%
Of mobile sessions
Uptime
99.9%
Excluding planned maintenance
Full KPI register with monthly targets lives in /Roadmap/Praxion-Phase1-Tracker.xlsx · updated each steerco cycle.
PRAXION HROS · Phase-1 Mobilization · PRX-MOB-P1-001 v1.0
19 / 20

## Slide 20
20 · DECISION & NEXT STEPS
Let's align, then mobilise.
WHAT WE'RE ASKING
From Head of Technicals
Endorse tech stack & environments
Or flag deltas before kick-off
Confirm squad model + leads
6 squads · tier-aligned · shared services
Green-light P0 Mobilise
Charter · RACI · vendors · 15 May kick-off
Sign off data + integration plan
3 dry runs · SIA/ETA/bank early access
WHAT HAPPENS NEXT
Next 14 days
This week
Tech-lead session · capture deltas · finalise stack
Week of 22 Apr
Board sign-off meeting · endorse Phase-1 plan
Week of 29 Apr
Hiring + vendor contracts finalised
15 May 2026
Phase-1 kick-off · all-hands Cairo
PRX-MOB-P1-001 · v1.0 · Owner: Project Director — Praxion HROS
20 / 20