## Slide 1
EXECUTIVE ROADMAP · BOARD REVIEW · APRIL 2026
From discovery to
go-live in 11 months.
13 modules · 11 phase gates · Target production launch 14 March 2027
KICK-OFF
15 Apr 2026
GO-LIVE
14 Mar 2027
STABILISATION
Through Jun '27
PORTAL GA
30 Sep 2027
PRX-ROAD-001 · v2.0 · Internal — Restricted
1 / 7

## Slide 2
01 · PLATFORM ARCHITECTURE
Five functional tiers — 13 modules regrouped by operating model
FOUNDATION
Identity · records · platform admin
M1
Core HRIS
M10
System Admin
PEOPLE
Hire · onboard · develop · retain
M2
Recruitment / ATS
M3
Onboarding
M4
Performance
M5
Training / LMS
MONEY
Pay · benefits · contractors
M6
Payroll & Comp
M7
Benefits & Expenses
M8
Contractor Mgmt
INTELLIGENCE
Analytics · reporting · insight
M9
Analytics & Reports
ACCESS
How users reach the platform
M11
Mobile ESS
M12
Client Portal
M13
Billing & Invoicing
Tiers reflect how the platform operates day-to-day — not the order we build them. Build sequencing is on the next slide.
PRAXION HROS · Executive Roadmap · PRX-ROAD-001 v2.0
2 / 7

## Slide 3
02 · PROGRAMME AT A GLANCE
11 phase gates from mobilisation to scaled operation
13
MODULES
All user stories written
11
PHASE GATES
Each with exit criteria
11 MO
KICK-OFF → GO-LIVE
15 Apr '26 → 14 Mar '27
Q3 '27
CLIENT PORTAL GA
3 external clients live
PHASE GATES · TIER-1 DELIVERABLE · TARGET DATE
P0
Mobilise
15 Apr '26
P1
Discover
15 Jun '26
P2
Foundations
15 Aug '26
P3
Core build
30 Nov '26
P4
Module build
31 Jan '27
P5
Harden
15 Feb '27
P6
UAT
07 Mar '27
P7
GO-LIVE
14 Mar '27
P8
Hypercare
14 Apr '27
P9
Optimise
30 Jun '27
P10
Scale
30 Sep '27
TIER-1 DELIVERABLES BY PHASE
P0–P1
Charter · Functional spec · Data model · NFRs
P2
Identity · API gateway · CI/CD · Observability
P3
Core HRIS · Payroll · Onboarding · ESS web + mobile
P4
ATS · Performance · LMS · Benefits · Contractor · Analytics v1
P5–P6
Pen-test · DR drill · UAT · 3× migration rehearsal
P8–P10
Hypercare · Perf tuning · Analytics v2 · Client Portal GA
PRAXION HROS · Executive Roadmap · PRX-ROAD-001 v2.0
3 / 7

## Slide 4
03 · MODULE SWIM LANES
13 modules · grouped by tier · sequenced across 7 quarters
Build
Launch
Enhance
Future
MODULE
Q2 '26
Q3 '26
Q4 '26
Q1 '27
Q2 '27
Q3 '27
Q4 '27
GO-LIVE 14 Mar '27
M1
Core HRIS
M10
System Admin
M2
Recruitment / ATS
M3
Onboarding / Offboard
M4
Performance / KPIs
M5
Training / LMS
M6
Payroll & Comp
M7
Benefits & Expenses
M8
Contractor Mgmt
M9
Analytics & Reports
M11
Mobile App (ESS)
M12
Client Portal
M13
Billing & Invoicing
Grouped by functional tier: Foundation (M1/M10) · People (M2–M5) · Money (M6–M8) · Intelligence (M9) · Access (M11–M13). Post go-live enhancement runs continuous across all lanes.
PRAXION HROS · Executive Roadmap · PRX-ROAD-001 v2.0
4 / 7

## Slide 5
04 · PRODUCT PRIORITIES
What the platform will do for users — by time horizon
NOW
Apr 2026 – Mar 2027
Employee system of record + org chart + JML workflows
Monthly Egyptian payroll + statutory reports + payslips
ATS: requisitions → offer · Onboarding journeys
Performance / OKRs · Learning catalogue · Benefits & expenses
Pre-built HR dashboards · ESS web + mobile
NEXT
Apr 2027 – Dec 2027
Client Portal GA · multi-tenant client onboarding
Multi-country payroll (GCC) · variable pay · comp-review
Self-serve report builder · scheduled distribution
Continuous check-ins · calibration · competency frameworks
Offline mobile for timesheets / expenses · biometric unlock
LATER
2028 and beyond
AI-assisted org design · predictive attrition · skills graph
AI screening & ranking · video-interview analytics
Talent marketplace · succession planning · equity / LTI
Natural-language analytics · benchmarking datasets
Agentic HR chatbot · life-event journeys · voice
12 product pillars · 55+ capabilities in NOW · Pillar detail: PRX-ROAD-001 Sheet 3 (Product)
PRAXION HROS · Executive Roadmap · PRX-ROAD-001 v2.0
5 / 7

## Slide 6
05 · WHAT COULD MOVE THE DATE
Top programme risks & external dependencies
PROGRAMME RISKS
LIKELIHOOD · IMPACT
Scope aggression vs. team size
6 people delivering 13 modules in 11 months — velocity assumption must hold
HIGH
HIGH
Data migration from legacy
Excel + paper + WhatsApp → structured HRIS; 3 rehearsals scheduled
MED
HIGH
Payroll accuracy at cut-over
2–3 parallel-run cycles vs. legacy before statutory sign-off
MED
HIGH
Change management / adoption
Field workers with no desktop; multilingual ESS + roadshow + training paths
HIGH
MED
Key-person concentration
Small team — illness or attrition in Core/Payroll squad delays P3
MED
MED
EXTERNAL DEPENDENCIES
OWNER · NEEDED BY
Social Insurance Authority API
Required for Payroll statutory filings (Form 2 / Form 6)
LEGAL · PAYROLL
Q4 2026
Egyptian Tax Authority filing
e-receipt & withholding tax integration
FINANCE
Q4 2026
Banking disbursement files
Partner bank(s) file-format sign-off for salary transfer
FINANCE
Q1 2027
PDP Law 151/2020 DPIA
Data Protection Impact Assessment approval
LEGAL · CISO
Q1 2027
External pen-test vendor
Pre-go-live security assessment + remediation
CISO
Feb 2027
PRAXION HROS · Executive Roadmap · PRX-ROAD-001 v2.0
6 / 7

## Slide 7
06 · DECISION & NEXT STEPS
We're asking the board to
endorse this roadmap.
WHAT WE'RE ASKING FOR
Approvals
Endorse 11-month delivery plan
Phase gates P0–P7, go-live 14 March 2027 fixed
Ring-fence team capacity
Core squad of 6 + domain squads protected through P8 hypercare
Approve external dependencies ask
Legal/Finance to secure API access with SIA, ETA, and banks by Q4 2026
WHAT HAPPENS NEXT
Next 60 days
P0 Mobilise · Apr – May 2026
Charter, RACI, governance approved by steerco
P1 Discover kick-off · 15 May 2026
Functional spec + data model + NFRs in progress
Monthly steerco + weekly exec summary
Standard template; first update 30 Apr 2026
PRX-ROAD-001 · v2.0 · Owner: Project Director — Praxion HROS
7 / 7