## Overview
Praxion HROS — Phase-1 Tracker | [5 empty] | PRX-TRK-P1-001 · v1.0
Kick-off 15 May 2026 · Go-live 14 Mar 2027 · 11 months | [5 empty] | Generated · 2026-04-19
KICK-OFF | FOUNDATION | MONEY CUT | PEOPLE LIVE | HARDEN END | GO-LIVE
15 May 2026 | 15 Sep 2026 | 15 Nov 2026 | 15 Jan 2027 | 10 Mar 2027 | 14 Mar 2027
TIER STATUS
Tier | Modules | Owner | Target gate | Status | % complete | Notes
FOUNDATION | M1 · M10 | HRIS Lead + CISO | P2 · 15 Sep '26 | GREEN | 0% | Mobilisation on track
PEOPLE | M2 · M3 · M4 · M5 | Talent & Dev Lead | P4 · 15 Jan '27 | GREEN | 0% | Kick-off pending
MONEY | M6 · M7 | Payroll Lead | P3 · 15 Nov '26 | AMBER | 0% | SIA/ETA integrations gating
INTELLIGENCE | M9 | Product + Data | P5 · 15 Feb '27 | GREEN | 0% | Dependent on M1/M6 data
ACCESS | M11 | Product + UX | P5 · 15 Feb '27 | GREEN | 0% | Mobile design kicks off P2
HEADLINE KPIs
KPI | Baseline | Target | Current | Gap | Owner | Tier
Payroll accuracy | 97.5% | 99.9% | — | 99.9% | Payroll Lead | MONEY
Offer → Day-1 | 15d | 7d | — | 7d | Talent Lead | PEOPLE
ESS mobile activation | 0% | 85% | — | 85% | Product | ACCESS
Dashboards live | 0 | 12 | — | 12 | Product+Data | INTELLIGENCE
Scope completion | 0% | 100% | — | 100% | PD (Sabry) | FOUNDATION
Uptime (prod) | — | 99.9% | — | 99.9% | CISO | FOUNDATION
Live tracker — update weekly. Status colours: GREEN = on track · AMBER = watch · RED = off-track.
PRX-TRK-P1-001 · v1.0 · Owner: Sabry M.

## Master WBS
Master Work Breakdown Structure | [5 empty] | PRX-TRK-P1-001 · v1.0
~120 tasks · Phase-1 · kick-off to go-live | [5 empty] | Generated · 2026-04-19
WBS | Tier | Module | Workstream | Task | Owner | Start | End | Dur (d) | Gate | Status | % comp | Notes / Dependencies
P0-001 | FOUNDATION | P0 | Charter | Sign off Phase-1 scope + success criteria | PD | 2026-04-15 | 2026-04-22 | 7 | P0 | NOT STARTED | 0%
P0-002 | FOUNDATION | P0 | Charter | Publish RACI + decision log | PD | 2026-04-22 | 2026-04-29 | 7 | P0 | NOT STARTED | 0%
P0-003 | FOUNDATION | P0 | Squads | Confirm 6 squad leads + hiring needs | PD + HRIS Lead | 2026-04-19 | 2026-04-30 | 11 | P0 | NOT STARTED | 0%
P0-004 | FOUNDATION | P0 | Squads | Issue offers for all net-new roles | Talent Lead | 2026-04-25 | 2026-05-10 | 15 | P0 | NOT STARTED | 0%
P0-005 | FOUNDATION | P0 | Environments | Provision DEV/INT/UAT + CI/CD baseline | HRIS Lead | 2026-04-25 | 2026-05-15 | 20 | P0 | NOT STARTED | 0%
P0-006 | FOUNDATION | P0 | Environments | Wire Keycloak + SSO integrations | CISO | 2026-05-01 | 2026-05-15 | 14 | P0 | NOT STARTED | 0%
P0-007 | FOUNDATION | P0 | Tooling | Jira set-up aligned to WBS | PD | 2026-04-20 | 2026-05-05 | 15 | P0 | NOT STARTED | 0%
P0-008 | FOUNDATION | P0 | Tooling | Confluence / knowledge-base structure | PD | 2026-04-22 | 2026-05-05 | 13 | P0 | NOT STARTED | 0%
P0-009 | FOUNDATION | P0 | Vendors | Pen-test + auditor contracts signed | CISO + Finance | 2026-04-25 | 2026-05-15 | 20 | P0 | NOT STARTED | 0%
P0-010 | FOUNDATION | P0 | Kick-off | All-hands kick-off + tech-lead design session | PD | 2026-05-14 | 2026-05-15 | 1 | P0 | NOT STARTED | 0%
P1-011 | FOUNDATION | M1 | Data model | Entity-relationship: employee/org/position/contract | HRIS Lead | 2026-05-15 | 2026-06-15 | 31 | P1 | NOT STARTED | 0% | Inputs from 30 legal entities
P1-012 | FOUNDATION | M1 | Data model | JML workflow state-machine design | HRIS Lead | 2026-05-22 | 2026-06-20 | 29 | P1 | NOT STARTED | 0%
P1-013 | FOUNDATION | M10 | Security | RBAC role catalogue + permission matrix | CISO | 2026-05-15 | 2026-06-15 | 31 | P1 | NOT STARTED | 0%
P1-014 | FOUNDATION | M10 | Security | DPIA draft — Law 151/2020 | Legal + CISO | 2026-06-01 | 2026-06-30 | 29 | P1 | NOT STARTED | 0%
P1-015 | PEOPLE | M2 | Functional spec | ATS requisition → offer flows | Talent Lead | 2026-05-15 | 2026-06-15 | 31 | P1 | NOT STARTED | 0%
P1-016 | PEOPLE | M3 | Functional spec | Onboarding journey patterns | Talent Lead | 2026-05-22 | 2026-06-20 | 29 | P1 | NOT STARTED | 0%
P1-017 | PEOPLE | M4 | Functional spec | Performance cycle + 360 design | Talent Lead | 2026-06-01 | 2026-07-01 | 30 | P1 | NOT STARTED | 0%
P1-018 | PEOPLE | M5 | Functional spec | LMS + SCORM catalogue design | Talent + Prod | 2026-06-01 | 2026-07-01 | 30 | P1 | NOT STARTED | 0%
P1-019 | MONEY | M6 | Functional spec | Egyptian payroll element taxonomy | Payroll Lead | 2026-05-15 | 2026-06-10 | 26 | P1 | NOT STARTED | 0%
P1-020 | MONEY | M6 | Functional spec | SIA + ETA filing formats | Payroll Lead | 2026-05-20 | 2026-06-15 | 26 | P1 | NOT STARTED | 0%
P1-021 | MONEY | M6 | Functional spec | Bank file formats (CIB, NBE, QNB) | Payroll Lead | 2026-05-25 | 2026-06-20 | 26 | P1 | NOT STARTED | 0%
P1-022 | MONEY | M7 | Functional spec | Benefits + expenses workflow design | Payroll + HR Ops | 2026-06-01 | 2026-07-01 | 30 | P1 | NOT STARTED | 0%
P1-023 | INTELLIGENCE | M9 | Functional spec | 12 pre-built dashboards backlog | Product + Data | 2026-06-01 | 2026-07-15 | 44 | P1 | NOT STARTED | 0%
P1-024 | ACCESS | M11 | Functional spec | Mobile ESS flows — payslip, leave, attendance | Product + UX | 2026-05-15 | 2026-06-30 | 46 | P1 | NOT STARTED | 0%
P1-025 | ACCESS | M11 | Functional spec | Arabic-first IA + UI principles | UX | 2026-05-22 | 2026-06-20 | 29 | P1 | NOT STARTED | 0%
P1-026 | FOUNDATION | ALL | NFRs | Non-functional requirements — perf, scale, SLOs | HRIS Lead | 2026-06-01 | 2026-07-15 | 44 | P1 | NOT STARTED | 0%
P1-027 | FOUNDATION | ALL | UX | Design system v1 (tokens, components, patterns) | UX | 2026-05-15 | 2026-07-15 | 61 | P1 | NOT STARTED | 0%
P2-028 | FOUNDATION | M1 | Build | Core entities + CRUD + audit | Platform squad | 2026-07-15 | 2026-08-31 | 47 | P2 | NOT STARTED | 0%
P2-029 | FOUNDATION | M1 | Build | JML workflows + position management | Platform squad | 2026-08-01 | 2026-09-10 | 40 | P2 | NOT STARTED | 0%
P2-030 | FOUNDATION | M1 | Build | Excel/paper import loader + reconcile report | Platform squad | 2026-08-15 | 2026-09-15 | 31 | P2 | NOT STARTED | 0%
P2-031 | FOUNDATION | M1 | Build | HRIS API v1 + API docs | Platform squad | 2026-08-20 | 2026-09-15 | 26 | P2 | NOT STARTED | 0%
P2-032 | FOUNDATION | M10 | Build | Identity + RBAC implementation | Platform squad | 2026-07-15 | 2026-08-31 | 47 | P2 | NOT STARTED | 0%
P2-033 | FOUNDATION | M10 | Build | SSO (SAML + OIDC) + MFA | Platform squad | 2026-08-01 | 2026-09-05 | 35 | P2 | NOT STARTED | 0%
P2-034 | FOUNDATION | M10 | Build | Audit log + observability hooks | Platform squad | 2026-08-10 | 2026-09-15 | 36 | P2 | NOT STARTED | 0%
P2-035 | FOUNDATION | M10 | Build | Backup / restore + DR drill | Platform squad | 2026-08-20 | 2026-09-15 | 26 | P2 | NOT STARTED | 0%
P2-036 | FOUNDATION | M1 | Data migration | Legacy extract — Excel + paper + interviews | Data team | 2026-07-20 | 2026-09-10 | 52 | P2 | NOT STARTED | 0%
P2-037 | FOUNDATION | M1 | Data migration | Canonical schema + pay-element taxonomy | Data team | 2026-08-01 | 2026-09-15 | 45 | P2 | NOT STARTED | 0%
P2-038 | FOUNDATION | M1 | QA | Test harness + contract tests | QA | 2026-07-20 | 2026-09-10 | 52 | P2 | NOT STARTED | 0%
P2-039 | FOUNDATION | M1 | QA | P2 UAT scripts + gate review | QA + HR Ops | 2026-09-01 | 2026-09-15 | 14 | P2 | NOT STARTED | 0%
P3-040 | MONEY | M6 | Build | Payroll engine — elements, proration, variable pay | Payroll squad | 2026-09-15 | 2026-11-01 | 47 | P3 | NOT STARTED | 0%
P3-041 | MONEY | M6 | Build | SIA API integration — Form 2 + Form 6 | Payroll squad | 2026-09-20 | 2026-10-31 | 41 | P3 | NOT STARTED | 0% | SIA API beta access
P3-042 | MONEY | M6 | Build | ETA e-receipts integration | Payroll squad | 2026-09-25 | 2026-10-31 | 36 | P3 | NOT STARTED | 0%
P3-043 | MONEY | M6 | Build | Bank file generators (CIB, NBE, QNB) | Payroll squad | 2026-10-01 | 2026-11-01 | 31 | P3 | NOT STARTED | 0%
P3-044 | MONEY | M6 | Build | Payslip generation + distribution | Payroll squad | 2026-10-10 | 2026-11-10 | 31 | P3 | NOT STARTED | 0%
P3-045 | MONEY | M6 | Parallel run | Parallel run #1 — 1 entity, 1 cycle | Payroll Lead + Ext auditor | 2026-10-01 | 2026-10-15 | 14 | P3 | NOT STARTED | 0%
P3-046 | MONEY | M6 | Parallel run | Parallel run #2 — 3 entities, 1 cycle | Payroll Lead + Ext auditor | 2026-10-15 | 2026-10-31 | 16 | P3 | NOT STARTED | 0%
P3-047 | MONEY | M6 | Parallel run | Parallel run #3 — all entities, reconcile | Payroll Lead + Ext auditor | 2026-11-01 | 2026-11-14 | 13 | P3 | NOT STARTED | 0%
P3-048 | MONEY | M7 | Build | Benefits enrolment + plan library | Payroll squad | 2026-10-01 | 2026-11-10 | 40 | P3 | NOT STARTED | 0%
P3-049 | MONEY | M7 | Build | Expense claims + receipt capture | Payroll squad | 2026-10-15 | 2026-11-15 | 31 | P3 | NOT STARTED | 0%
P3-050 | MONEY | M7 | Build | Mobile receipt OCR + manager approval | Payroll + UX | 2026-10-20 | 2026-11-15 | 26 | P3 | NOT STARTED | 0%
P3-051 | MONEY | M6 | QA | Statutory filings test cases | QA + External auditor | 2026-10-01 | 2026-11-10 | 40 | P3 | NOT STARTED | 0%
P3-052 | MONEY | M6 | QA | P3 UAT + gate review | QA + Finance | 2026-11-01 | 2026-11-14 | 13 | P3 | NOT STARTED | 0%
P4-053 | PEOPLE | M2 | Build | Requisition → offer flow + scorecards | Talent squad | 2026-11-15 | 2026-12-20 | 35 | P4 | NOT STARTED | 0%
P4-054 | PEOPLE | M2 | Build | Careers page + LinkedIn/Wuzzuf integrations | Talent squad | 2026-11-20 | 2026-12-31 | 41 | P4 | NOT STARTED | 0%
P4-055 | PEOPLE | M2 | Build | E-signature integration (offers/contracts) | Talent squad | 2026-12-01 | 2027-01-10 | 40 | P4 | NOT STARTED | 0%
P4-056 | PEOPLE | M3 | Build | Onboarding journey engine + checklists | Talent squad | 2026-11-15 | 2026-12-20 | 35 | P4 | NOT STARTED | 0%
P4-057 | PEOPLE | M3 | Build | Provisioning triggers + digital document pack | Talent squad | 2026-12-01 | 2027-01-10 | 40 | P4 | NOT STARTED | 0%
P4-058 | PEOPLE | M4 | Build | Goals / OKRs + check-ins | Growth squad | 2026-11-20 | 2026-12-31 | 41 | P4 | NOT STARTED | 0%
P4-059 | PEOPLE | M4 | Build | Review cycle + calibration + 360 | Growth squad | 2026-12-10 | 2027-01-15 | 36 | P4 | NOT STARTED | 0%
P4-060 | PEOPLE | M5 | Build | Course catalogue + enrolments | Growth squad | 2026-11-20 | 2026-12-31 | 41 | P4 | NOT STARTED | 0%
P4-061 | PEOPLE | M5 | Build | SCORM ingest + compliance tracking | Growth squad | 2026-12-01 | 2027-01-15 | 45 | P4 | NOT STARTED | 0%
P4-062 | PEOPLE | M2-M5 | QA | People-tier UAT scripts + gate review | QA + HR Ops | 2027-01-05 | 2027-01-15 | 10 | P4 | NOT STARTED | 0%
P4-063 | PEOPLE | M2-M5 | Change | People modules training for HR Ops | Change lead | 2027-01-01 | 2027-01-15 | 14 | P4 | NOT STARTED | 0%
P5-064 | INTELLIGENCE | M9 | Build | Semantic layer + dashboards v1 (12) | Insights squad | 2027-01-15 | 2027-02-10 | 26 | P5 | NOT STARTED | 0%
P5-065 | INTELLIGENCE | M9 | Build | Self-serve report builder | Insights squad | 2027-01-20 | 2027-02-15 | 26 | P5 | NOT STARTED | 0%
P5-066 | INTELLIGENCE | M9 | Build | Workforce-plan scenarios | Insights squad | 2027-01-25 | 2027-02-15 | 21 | P5 | NOT STARTED | 0%
P5-067 | ACCESS | M11 | Build | Mobile shell + biometric auth (iOS/Android) | Experience squad | 2027-01-15 | 2027-02-10 | 26 | P5 | NOT STARTED | 0%
P5-068 | ACCESS | M11 | Build | Payslip / leave / attendance flows | Experience squad | 2027-01-20 | 2027-02-15 | 26 | P5 | NOT STARTED | 0%
P5-069 | ACCESS | M11 | Build | Manager approvals + team view | Experience squad | 2027-01-25 | 2027-02-15 | 21 | P5 | NOT STARTED | 0%
P5-070 | ACCESS | M11 | Build | Arabic + field-worker mode | Experience squad | 2027-02-01 | 2027-02-15 | 14 | P5 | NOT STARTED | 0%
P5-071 | INTELLIGENCE | M9 | QA | Data-quality + dashboard UAT | QA | 2027-02-05 | 2027-02-15 | 10 | P5 | NOT STARTED | 0%
P5-072 | ACCESS | M11 | QA | Mobile UAT on iOS + Android | QA | 2027-02-05 | 2027-02-15 | 10 | P5 | NOT STARTED | 0%
P6-073 | FOUNDATION | ALL | UAT | Full UAT across 10 modules — HR + Finance + Ops | QA + HR + Fin | 2027-02-15 | 2027-03-05 | 18 | P6 | NOT STARTED | 0%
P6-074 | FOUNDATION | ALL | Security | External pen-test + remediation | CISO + Vendor | 2027-02-15 | 2027-03-05 | 18 | P6 | NOT STARTED | 0% | Report to CISO + board
P6-075 | FOUNDATION | ALL | Security | DPIA sign-off — Law 151/2020 | Legal + CISO | 2027-02-15 | 2027-02-28 | 13 | P6 | NOT STARTED | 0%
P6-076 | FOUNDATION | ALL | Load | Load test to 2x peak (payroll + ESS) | Platform squad | 2027-02-20 | 2027-03-05 | 13 | P6 | NOT STARTED | 0%
P6-077 | FOUNDATION | M1 | Data migration | Dry run 3 — full rehearsal + rollback drill | Data team | 2027-02-15 | 2027-02-25 | 10 | P6 | NOT STARTED | 0%
P6-078 | FOUNDATION | ALL | Cutover | Cutover runbook + rollback plan | PD + HRIS Lead | 2027-02-20 | 2027-03-05 | 13 | P6 | NOT STARTED | 0%
P6-079 | FOUNDATION | ALL | Change | Champions trained (1 per entity) | Change lead | 2027-02-15 | 2027-03-05 | 18 | P6 | NOT STARTED | 0%
P6-080 | FOUNDATION | ALL | Change | End-user comms + FAQ published | Change lead | 2027-02-20 | 2027-03-10 | 18 | P6 | NOT STARTED | 0%
P6-081 | FOUNDATION | ALL | Gate | P6 gate — steerco go/no-go | Steerco | 2027-03-10 | 2027-03-10 | 0 | P6 | NOT STARTED | 0%
P7-082 | FOUNDATION | ALL | Cutover | Go-live cutover weekend | All squads | 2027-03-13 | 2027-03-14 | 1 | P7 | NOT STARTED | 0%
P7-083 | FOUNDATION | ALL | Hypercare | Hypercare — 30 days post-launch | All squads | 2027-03-14 | 2027-04-13 | 30 | P7 | NOT STARTED | 0%
P7-084 | FOUNDATION | ALL | Warranty | Warranty — 30–60 days post-launch | Platform squad | 2027-04-13 | 2027-05-13 | 30 | P7 | NOT STARTED | 0%
P7-085 | FOUNDATION | ALL | Review | Post-launch review + lessons learned | PD | 2027-04-15 | 2027-04-30 | 15 | P7 | NOT STARTED | 0%
P7-086 | FOUNDATION | ALL | Review | Phase-2 planning kick-off | PD + Sponsor | 2027-05-01 | 2027-05-15 | 14 | P7 | NOT STARTED | 0%
TOTALS |  |  | Tasks: | 86
|  |  | Avg duration (d): | 26.7
|  |  | Total scheduled (d): | 2294
|  |  | % complete (overall): | 0%

## Gates
Phase-1 Gates — P0 to P7 | [5 empty] | PRX-TRK-P1-001 · v1.0
Gate criteria · target dates · status · owner | [5 empty] | Generated · 2026-04-19
Gate | Name | Window | Duration | Target | Criteria | Status | % comp
P0 | MOBILISE | Apr – May '26 | 4w | 15 May 2026 | Charter signed · RACI published · squads staffed · environments live | IN PROGRESS | 35%
P1 | DESIGN | May – Jul '26 | 8w | 15 Jul 2026 | Functional specs · data model · UX · NFRs complete for all modules | NOT STARTED | 0%
P2 | FOUNDATION | Jul – Sep '26 | 8w | 15 Sep 2026 | M1 Core HRIS + M10 System Admin + SSO live in UAT; 1st entity migrated | NOT STARTED | 0%
P3 | MONEY | Sep – Nov '26 | 8w | 15 Nov 2026 | M6 parallel run x3 reconciled · M7 benefits/expenses UAT · SIA/ETA/bank integrations | NOT STARTED | 0%
P4 | PEOPLE | Nov '26 – Jan '27 | 8w | 15 Jan 2027 | M2 ATS · M3 Onboarding · M4 Performance · M5 LMS live in UAT | NOT STARTED | 0%
P5 | ACCESS + INTEL | Jan – Feb '27 | 4w | 15 Feb 2027 | M11 Mobile ESS + M9 Analytics live in UAT · 12 dashboards · Arabic | NOT STARTED | 0%
P6 | HARDEN | Feb – Mar '27 | 3.5w | 10 Mar 2027 | UAT · pen-test · DPIA · load test · dry-run 3 · cutover runbook signed | NOT STARTED | 0%
P7 | GO-LIVE | 14 Mar 2027 | D-Day | 14 Mar 2027 | Cutover complete · hypercare 30d · warranty 30–60d · post-launch review | NOT STARTED | 0%

## RACI
RACI — Who owns what | [5 empty] | PRX-TRK-P1-001 · v1.0
Responsible · Accountable · Consulted · Informed | [5 empty] | Generated · 2026-04-19
Activity | Board | Sponsor/CEO | PD (Sabry) | HRIS Lead | Payroll Lead | Talent Lead | Ext
Charter & scope | A | R | R | C | C | C | I
Data migration | I | I | A | R | C | C | C
Payroll cut-over | I | A | A | C | R | I | R
Statutory filings | I | A | C | C | R | I | C
DPIA + security | I | A | A | C | C | C | R
SSO / identity | I | C | A | R | C | I | C
Module UAT | I | I | A | C | C | C | C
Training & change | I | A | A | C | C | R | C
Budget & burn | A | A | R | I | I | I | I
Steerco reporting | I | A | R | C | C | C | I
Vendor contracts | A | A | R | C | C | C | I
Architecture decisions | I | I | A | R | C | C | C
LEGEND
R | Responsible — does the work
A | Accountable — one per activity
C | Consulted — two-way input
I | Informed — one-way notification

## Dependencies
External Dependencies & Blockers | [5 empty] | PRX-TRK-P1-001 · v1.0
SIA · ETA · banks · pen-test · DPIA · vendor contracts | [5 empty] | Generated · 2026-04-19
System / dependency | Tier | Owner | Needed by | Status | Notes / risk | Severity | Mitigation
SIA API access | MONEY | Payroll Lead + Legal | 2026-09-30 | OPEN | SIA API beta — availability uncertain; fallback is manual upload | HIGH | Fallback upload + vendor escalation
ETA e-receipts schema | MONEY | Finance | 2026-10-15 | OPEN | Schema can shift; need formal liaison with tax authority | HIGH | Pin schema v1 · monitor changes
Banking file formats | MONEY | Finance | 2026-11-01 | OPEN | CIB + NBE + QNB each have own format · test files per bank | HIGH | Test files · bank champion per partner
PDP DPIA clearance | FOUNDATION | Legal + CISO | 2027-02-28 | OPEN | Law 151/2020 — DPIA must clear before go-live | HIGH | Legal kick-off in P1; external counsel on retainer
Pen-test vendor | FOUNDATION | CISO | 2027-02-15 | OPEN | External security assessment; slot contract by Q4 2026 | MEDIUM | Contract signed in P0; 2-wave test
SSO IdP (Azure AD) | FOUNDATION | CIO | 2026-08-31 | OPEN | Tenant + groups config must be ready before P2 | MEDIUM | CIO liaison weekly from P1
Job boards | PEOPLE | Talent Lead | 2026-11-01 | OPEN | LinkedIn + Wuzzuf API keys + agreements | LOW | Commercial agreement + sandbox
E-signature vendor | PEOPLE | Talent Lead | 2026-12-01 | OPEN | DocuSign or equivalent; must support Arabic | LOW | Procure in P1
SCORM content | PEOPLE | Talent Lead | 2027-01-15 | OPEN | External content library + license | LOW | Select vendor in P2
SMS / push gateway | ACCESS | Product | 2027-01-15 | OPEN | Notification channels; two providers for redundancy | LOW | Procure in P3
External auditor | MONEY | Finance | 2026-09-15 | OPEN | For parallel-run reconciliation + go-live sign-off | HIGH | Contracted in P0
Legal — labour law | PEOPLE | Legal | 2026-09-15 | OPEN | Egyptian labour-law review of contract + policy templates | MEDIUM | External counsel on retainer

## KPIs
Success KPIs — Phase-1 | [5 empty] | PRX-TRK-P1-001 · v1.0
Monthly targets · baseline · actuals · owner · tier | [5 empty] | Generated · 2026-04-19
KPI | Tier | Baseline | Target | Current | Gap to target | Trend | Owner
Payroll accuracy | MONEY | 97.5% | 99.9% | — | — | — | Payroll Lead
Payroll cycle time | MONEY | 6d | 1d | — | — | — | Payroll Lead
Statutory filings — late | MONEY | 1 / mo | 0 | — | — | — | Payroll Lead
Offer → Day-1 | PEOPLE | 15d | 7d | — | — | — | Talent Lead
Training — core role | PEOPLE | 72% | 95% | — | — | — | Talent Lead
Manager self-serve | PEOPLE | 40% | 75% | — | — | — | Talent Lead
ESS mobile activation | ACCESS | 0% | 85% | — | — | — | Product
Arabic usage (mobile) | ACCESS | — | 40% | — | — | — | Product + UX
Uptime — production | FOUNDATION | — | 99.9% | — | — | — | CISO
Pre-built dashboards live | INTELLIGENCE | 0 | 12 | — | — | — | Product + Data
Defect escape — P1 / mo | FOUNDATION | — | < 2 | — | — | — | QA
Scope completion | FOUNDATION | 0% | 100% | — | — | — | PD
MONTHLY TARGETS (by KPI)
KPI | Jun '26 | Aug '26 | Oct '26 | Dec '26 | Feb '27 | Apr '27
Scope completion | 8% | 25% | 45% | 65% | 90% | 100%
Modules in UAT | 0 | 2 | 4 | 8 | 10 | 10
Payroll accuracy (run) | — | — | 99.5% | 99.8% | 99.9% | 99.9%
ESS activation | 0% | 0% | 0% | 0% | 15% | 65%
Dashboards live | 0 | 2 | 6 | 8 | 12 | 12
Data cleansed (records) | 15% | 40% | 70% | 90% | 98% | 100%