## Cover
PRAXION HROS — ROADMAP
Implementation · Product · Technical ¦ Target Go-Live 14 March 2027
Document ID | PRX-ROAD-001
Version | 1.0 (Draft for Review)
Owner | Project Director — Praxion HROS
Last updated | 2026-04-10
Classification | Internal — Restricted
Companion docs | PRX-ARCH-001 Architecture · PRX-SEC-POL-001 Access Policy · PRX-SEC-MTX-001 Access Matrix
HOW TO READ THIS WORKBOOK
1. Milestones | Top-line schedule: phases, gates and the 14 Mar 2027 go-live.
2. Implementation | Phased delivery plan with workstreams, deliverables, owners and dates.
3. Product | Now / Next / Later product pillars — what the platform will DO for users.
4. Technical | Stack, infra and platform evolution — what we build it ON.
STATUS KEY
On Track | At Risk | Blocked | Not Started | Done

## 1. Milestones
1 · Milestones & Gates
Top-line schedule from kick-off to go-live and the first year of operation.
Phase | Gate / Milestone | Target date | Duration | Tier-1 deliverable | Exit criteria
P0 — Mobilise | Kick-off + team formed | 15 Apr 2026 | 2 w | Charter, RACI, governance | Steering committee approves charter
P1 — Discover | Requirements baseline | 15 Jun 2026 | 8 w | Functional spec, data model, NFRs, ADRs 1-10 | Spec signed off by business + tech
P2 — Foundations | Platform foundations ready | 15 Aug 2026 | 8 w | Identity, Auth, API Gateway, CI/CD, Observ. | Smoke test passes against dev cluster
P3 — Core build | Core HRIS + Payroll alpha | 30 Nov 2026 | 14 w | HRIS, Payroll, Onboarding, ESS web & mobile | End-to-end employee + payroll demo
P4 — Module build | Recruitment + Performance | 31 Jan 2027 | 8 w | ATS, Perf, Learning, Analytics v1 | All Tier-1 & Tier-2 modules feature-complete
P5 — Harden | UAT entry | 15 Feb 2027 | 2 w | Security test, perf test, DR drill | Pen-test findings closed, SLOs met
P6 — UAT | UAT exit / Go-No-Go | 07 Mar 2027 | 3 w | UAT sign-off, data migration rehearsal | Business sign-off, zero P1 defects
P7 — GO-LIVE | Production launch | 14 Mar 2027 | 1 w | Cut-over, hypercare begins | Payroll runs green in prod
P8 — Hypercare | 30-day stabilisation | 14 Apr 2027 | 4 w | Daily war-room, rapid-fix train | All P1/P2 incidents closed
P9 — Optimise | Q2 2027 retrospective | 30 Jun 2027 | 10 w | Performance tuning, UX polish, Analytics v2 | NPS > 40, SLO burn < 10%
P10 — Scale | Client Portal GA | 30 Sep 2027 | 13 w | Multi-tenant client onboarding at scale | 3 external clients live

## 2. Implementation
2 · Implementation Plan
Workstream × phase delivery plan. Owners are accountable; status updated weekly.
ID | Workstream | Phase | Deliverable / Epic | Owner | Start | End | Status | Dependencies | Notes
G-01 | Governance | P0 | Project charter & operating model | Project Director | 15 Apr 2026 | 30 Apr 2026 | Not Started | — | RACI, cadence, decision log
G-02 | Governance | P0 | Steering committee + escalation paths | Project Director | 22 Apr 2026 | 30 Apr 2026 | Not Started | G-01 | Bi-weekly steerco
G-03 | Governance | P1-P9 | Weekly status reports to exec | Project Director | 01 May 2026 | 30 Jun 2027 | Not Started | G-01 | Standard template
D-01 | Discovery | P1 | Functional requirements (13 modules) | HR Director / PM | 15 Apr 2026 | 31 May 2026 | Not Started | G-01 | Interviews + user stories
D-02 | Discovery | P1 | Data model & migration strategy | Tech Lead | 01 May 2026 | 15 Jun 2026 | Not Started | D-01 | Legacy system mapping
D-03 | Discovery | P1 | NFRs, SLAs, SLOs | CTO | 01 May 2026 | 31 May 2026 | Not Started | D-01 | Agreed with business
D-04 | Discovery | P1 | Architecture Decision Records v1 (1-10) | Tech Lead | 15 May 2026 | 15 Jun 2026 | Not Started | D-03 | Published in wiki
S-01 | Security | P1 | User Access Policy + Matrix v1 | CISO | 15 Apr 2026 | 15 May 2026 | Done | — | This deliverable set
S-02 | Security | P2 | IdP (Keycloak) configured | Security Eng | 01 Jul 2026 | 31 Jul 2026 | Not Started | P2 foundations | SSO + MFA
S-03 | Security | P2 | OPA policies for RBAC/SoD | Security Eng | 15 Jul 2026 | 15 Aug 2026 | Not Started | S-01, S-02 | Policy-as-code in Git
S-04 | Security | P5 | External penetration test | CISO + vendor | 01 Feb 2027 | 14 Feb 2027 | Not Started | P4 complete | Must close all High
S-05 | Security | P5 | DR drill (failover staging) | SRE | 08 Feb 2027 | 14 Feb 2027 | Not Started | P4 complete | RTO ≤ 2h verified
P-01 | Platform | P2 | Kubernetes clusters (dev/uat/stg/prod) | SRE | 15 Jun 2026 | 15 Jul 2026 | Not Started | D-04 | Terraform
P-02 | Platform | P2 | CI/CD pipelines + Argo CD | SRE | 01 Jul 2026 | 31 Jul 2026 | Not Started | P-01 | Trunk-based
P-03 | Platform | P2 | Observability stack (OTel, Grafana) | SRE | 15 Jul 2026 | 15 Aug 2026 | Not Started | P-01 | Golden signals
P-04 | Platform | P2 | API Gateway + service mesh | Platform Eng | 15 Jul 2026 | 15 Aug 2026 | Not Started | P-01 | Linkerd mTLS
P-05 | Platform | P2 | Shared libraries (auth, messaging, audit) | Platform Eng | 01 Jul 2026 | 15 Aug 2026 | Not Started | D-04 | Golden templates
C-01 | Core | P3 | Identity Service | Backend Lead | 16 Aug 2026 | 30 Sep 2026 | Not Started | P-02, S-02 | Keycloak façade
C-02 | Core | P3 | Authorization Service | Backend Lead | 01 Sep 2026 | 15 Oct 2026 | Not Started | S-03 | OPA-backed
C-03 | Core | P3 | Core HRIS Service | HRIS Squad | 16 Aug 2026 | 15 Nov 2026 | Not Started | C-01 | System of record
C-04 | Core | P3 | Onboarding Service + workflows | HRIS Squad | 01 Oct 2026 | 30 Nov 2026 | Not Started | C-03 | Temporal workflows
C-05 | Core | P3 | Payroll Service (calc engine) | Payroll Squad | 16 Aug 2026 | 30 Nov 2026 | Not Started | C-03 | Dual-run vs legacy
C-06 | Core | P3 | Employee Self-Service (web + mobile) | FE Squad | 15 Sep 2026 | 30 Nov 2026 | Not Started | C-03 | Leave, payslips, profile
M-01 | Modules | P4 | Recruitment / ATS | ATS Squad | 01 Dec 2026 | 31 Jan 2027 | Not Started | C-01, C-03 | Req → offer
M-02 | Modules | P4 | Performance & KPIs | Perf Squad | 01 Dec 2026 | 31 Jan 2027 | Not Started | C-03 | Goals, reviews
M-03 | Modules | P4 | Learning / LMS | Perf Squad | 01 Dec 2026 | 31 Jan 2027 | Not Started | C-03 | Catalogue + enrolments
M-04 | Modules | P4 | Benefits & Expenses | HRIS Squad | 01 Dec 2026 | 31 Jan 2027 | Not Started | C-03 | Claims + approvals
M-05 | Modules | P4 | Contractor Management | HRIS Squad | 01 Dec 2026 | 31 Jan 2027 | Not Started | C-03 | Rate cards, timesheets
M-06 | Modules | P4 | Analytics v1 + dashboards | Data Squad | 01 Dec 2026 | 31 Jan 2027 | Not Started | C-03, C-05 | ClickHouse + CDC
DM-01 | Data | P3-P6 | Data extraction from legacy systems | Data Squad | 01 Oct 2026 | 15 Feb 2027 | Not Started | D-02 | Staged, reconciled
DM-02 | Data | P6 | Data migration rehearsals ×3 | Data Squad | 01 Feb 2027 | 07 Mar 2027 | Not Started | DM-01 | Dress rehearsal #3 = cut-over
CE-01 | Change | P3-P7 | Comms plan + roadshow | HR Director | 01 Oct 2026 | 14 Mar 2027 | Not Started | G-01 | All-hands, Q&A sessions
CE-02 | Change | P5-P7 | Training: HR, Payroll, Managers | L&D | 15 Jan 2027 | 14 Mar 2027 | Not Started | M-02 | Role-based paths
CE-03 | Change | P7-P8 | Hypercare war-room | Project Director | 14 Mar 2027 | 14 Apr 2027 | Not Started | P7 | Daily standups
CO-01 | Compliance | P5 | ISO 27001 readiness review | CISO | 01 Feb 2027 | 14 Feb 2027 | Not Started | S-03, S-04 | Internal audit
CO-02 | Compliance | P6 | PDP Law 151/2020 DPIA | CISO + Legal | 15 Feb 2027 | 07 Mar 2027 | Not Started | S-01 | Data protection impact

## 3. Product
3 · Product Roadmap (Now / Next / Later)
What the platform will DO for users, by product pillar and time horizon.
Pillar | NOW · Apr 2026 → Mar 2027 | NEXT · Apr 2027 → Dec 2027 | LATER · 2028+
Core HR (HRIS) | • Employee system of record • Org chart, positions, contracts • Document vault with expiry tracking • Joiner-Mover-Leaver workflows | • Position budgeting • Workforce planning v1 • Career histories timeline • Bulk org restructuring tools | • AI-assisted org design • Predictive attrition • Skills graph integration
Recruitment & ATS | • Requisitions + approvals • Candidate sourcing & pipelines • Interview scheduling • Offer management | • Structured interview kits • Scorecards & calibrated hiring • Candidate portal v2 • Referral programme | • AI screening & ranking • Video-interview analytics • Market-pay benchmarking
Onboarding & Offboarding | • Guided onboarding journeys • Task checklists + approvals • Document collection • Exit interviews | • Buddy / mentor matching • 30-60-90 day plans • Knowledge-transfer templates | • Predictive first-year attrition • Personalised learning paths
Performance & Goals | • OKR / goal setting • 1:1 notes • Annual & quarterly reviews • 360° feedback basics | • Continuous check-ins • Calibration sessions • Competency frameworks • Manager coaching prompts | • AI-generated review drafts • Talent marketplace • Succession planning
Learning & Development | • Course catalogue • Enrolments & completions • Certifications tracking | • Learning paths • SCORM / xAPI support • Manager-assigned training | • Skills inventory • AI learning recommendations • External content marketplace
Payroll & Compensation | • Monthly pay runs (Egypt) • Statutory deductions & reports • Payslip PDFs • Disbursement files | • Multi-country payroll (GCC) • Variable pay / bonuses • Comp-review cycles • Salary bands | • Equity / LTI management • Predictive payroll anomalies • Total-rewards statements
Benefits & Expenses | • Benefits enrolment • Expense claims + approvals • Mileage & per-diem | • Self-serve benefits shopping • Corporate-card integration • Policy-violation detection | • Wellbeing marketplace • Mental-health benefits
Contractor Management | • Vendor & contractor registry • Rate cards • Timesheets & approvals | • Contractor portal • SoW management • Auto-generated purchase orders | • Global contractor payments • Compliance scoring
Analytics & Reporting | • Pre-built HR dashboards • Standard regulatory reports • CSV / Excel exports | • Self-serve report builder • Scheduled distribution • Cross-module drill-downs | • Predictive people analytics • Natural-language queries • Benchmarking datasets
Client Portal (HRaaS) | • Client tenant provisioning • Roster upload • Limited dashboards • Monthly invoices | • Client-branded experience • Self-serve user admin • Usage-based billing | • Multi-entity clients • Automated SLA reporting • Partner marketplace
Employee Experience | • ESS web + mobile • Leave, payslips, profile • In-app notifications | • Personalised home feed • In-app surveys & pulse • Mobile offline for core flows | • Voice assistant • Generative HR chatbot • Life-event journeys
Compliance & Audit | • Immutable audit log • Access reviews • Data export on request (DSAR) | • Automated evidence pack • Policy acceptance tracking • Regulator report templates | • Continuous control monitoring • SOC 2 Type II automation

## 4. Technical
4 · Technical Roadmap
Stack, infrastructure and platform evolution across Now / Next / Later.
Layer | Area | Now (to Mar 2027) | Next (Apr-Dec 2027) | Later (2028+) | Owner
Front-end | Web | Next.js 14 App Router · React 18 · TypeScript strict · Tailwind + Radix · React Query · React Hook Form + Zod · next-intl (en, ar) | Upgrade to React 19 · Turbopack prod · Module federation for admin console · Storybook + Chromatic visual regression | Next.js 15+ · RSC-first patterns across all surfaces · A11y bot in CI | FE Lead
Front-end | Mobile | React Native 0.74 · new arch (Fabric / TurboModules) · WatermelonDB · FCM / APNs | RN 0.76+ · Offline for timesheets and expenses · Biometric unlock · In-app survey SDK | Cross-platform share extensions · Wear OS / watchOS widgets | Mobile Lead
Front-end | Admin Console | Separate Next.js app · restricted auth scope · audited every action | SoD visualiser · Policy simulator (dry-run OPA) · Tenant clone tool | Low-code configurator for client-specific workflows | FE Lead
Back-end | Runtime | Node.js 20 LTS · NestJS 10 · Prisma 5 · strict TypeScript | Node 22 LTS · NestJS 11 · consider Bun for edge services | Evaluate Rust for the payroll calc engine hot path | Backend Lead
Back-end | Services | 17 domain services per ADR-001 · golden service template · shared libs (@praxion/*) | Extract hot modules into their own services (notifications, analytics ingest) · gRPC for internal hops | Service-per-subdomain refactor · contract tests across every hop | Backend Lead
Back-end | Workflow | Temporal for onboarding, payroll, approvals | Self-serve workflow designer (for HR admins) · SLA-aware retries | Workflow marketplace for client-specific automations | Platform Eng
Data | OLTP | PostgreSQL 16 · one DB per service · RLS · PITR 15 min | Read replicas per region · logical sharding for largest tenants | Postgres 17+ · distributed Postgres option for scale | DBA / SRE
Data | Analytics | Debezium CDC → ClickHouse · Metabase dashboards | dbt models · Semantic layer · Scheduled exports to client warehouses | Lakehouse (Iceberg) · ML feature store | Data Lead
Data | Search | Postgres trigram + OpenSearch for candidate & employee search | Vector search for semantic candidate match | Unified hybrid search across all modules | Data Lead
Messaging | Event bus | NATS JetStream · durable streams · schema registry · DLQ | Multi-region mirrored streams · ordered delivery guarantees for payroll events | Evaluate Kafka if throughput demands | Platform Eng
Identity | IdP | Keycloak · OIDC · social login · TOTP + WebAuthn | Federated SSO per client · passkeys default · step-up auth for sensitive ops | Decentralised identity / verifiable credentials pilot | Security Eng
Authorization | Policies | OPA sidecar · Rego policies versioned in Git · RBAC + scopes + SoD | ABAC attributes from HRIS (department, cost-centre) · policy simulator UI | ReBAC (Zanzibar-style) for cross-module relations | Security Eng
Infrastructure | Compute | Managed Kubernetes · 3 node pools · HPA + PDBs | Karpenter autoscaling · node-pool consolidation · ARM64 nodes for cost | Serverless for stateless BFF layers | SRE
Infrastructure | Network | Linkerd mTLS · WAF · private cluster · egress allow-list | Zero-trust network access for internal tools · DNS firewall | Service-mesh federation across regions | SRE
Infrastructure | IaC | Terraform (infra) + Helm (apps) · Argo CD GitOps | Crossplane for app-level provisioning · policy-as-code (OPA Gatekeeper) | Full self-service environment provisioning for teams | SRE
Observability | Telemetry | OTel everywhere · Prometheus · Loki · Tempo · Grafana | eBPF-based network observability · continuous profiling (Parca) | AI-driven anomaly detection on golden signals | SRE
Security | AppSec | Snyk · Semgrep · Trivy · ZAP · annual pen test | Runtime AppSec (Falco) · SBOM signing · SLSA level 3 build attestations | SLSA L4 · confidential computing for payroll calc | Security Eng
Security | Secrets & keys | HashiCorp Vault · KMS envelope encryption · 90-day secret rotation | Dynamic DB credentials · per-request secret injection · key ceremony automation | HSM-backed tenant keys · customer-managed keys (BYOK) | Security Eng
Delivery | CI/CD | GitHub Actions · Turborepo affected-graph · Argo CD · Argo Rollouts canary | Progressive delivery with automated metric analysis · hermetic builds | Remote build cache across the org · 100% trunk-based | Platform Eng
Delivery | Feature flags | Unleash self-hosted · front-end + back-end SDKs | Experimentation platform (A/B) · tenant-targeted rollouts | ML-driven rollout recommendations | Platform Eng
Reliability | SLOs & DR | Per-service SLOs · error budgets · quarterly DR drills · RPO 15m / RTO 2h | Multi-region warm standby for Tier-1 · game-day chaos tests | Active-active for Tier-1 · RPO ~0 / RTO < 15m | SRE
AI / ML | Capabilities | None in core (policy: no PII to 3rd-party LLMs) · internal prompt sandbox | On-prem LLM gateway · RAG over HR docs for employee Q&A · generative job descriptions | Agentic flows for recruitment ops · predictive attrition · automated comp analysis | AI Lead