## Slide 1
Praxion
DISCOVERY PHASE SIGN-OFF · BOARD REVIEW · APRIL 2026
Discovery complete.
Ready to build.
6 weeks · 13 modules scoped · 22 BRDs · 55+ capabilities defined
STARTED
03 Mar 2026
DURATION
6 weeks
STATUS
Complete
ASK
Endorse + mobilise
PRX-DISC-SO-001 · v1.2 · Internal — Restricted
1 / 16

## Slide 2
01 · EXECUTIVE SUMMARY
What we did, what we found, what we're asking
WHERE WE STARTED
Brief
Design Praxion HROS — 13-module HR platform for Egyptian mid-market
Scope
6 weeks, Mar 3 → Apr 21, 2026 · core team of 6
Mandate
Confirm scope, validate requirements, surface risks, recommend Phase 1
WHAT WE FOUND
Scope is viable
All 13 modules documented · 22 BRDs signed-off · 55+ Phase-1 capabilities
Priorities are clear
5 modules drive Phase 1 — Core HRIS, Payroll, Onboarding, ESS, Admin
Risks are known
Team velocity, data migration, payroll cut-over · all with mitigations
WHAT WE'RE ASKING
Endorse outputs
Accept BRDs, user stories, workflows and roadmap as the Phase-1 basis
Green-light build
Phase-1 kick-off 15 May 2026 · go-live 14 Mar 2027
Unlock dependencies
Legal/Finance alignment on SIA, ETA, banking + DPIA by Q4 2026
13
modules
22
BRDs
55+
capabilities
100%
stories
11
months to go-live
PRAXION HROS · Discovery Phase Sign-Off · PRX-DISC-SO-001 v1.2
2 / 16

## Slide 3
02 · CONTEXT
Why Praxion HROS — and why now
THE PROBLEM
Egyptian mid-market HR runs on fragmented tools, Excel, paper and WhatsApp. Compliance is manual, payroll is fragile, employee experience is desktop-only. There is no integrated HR platform designed around local statutory, language and field-worker realities.
SCALE
Growth headroom
Clients growing from hundreds to thousands of employees · multi-entity · multi-site · field-heavy
COMPLIANCE
Tightening regulation
PDP Law 151/2020 · ETA e-receipts · SIA statutory filings · auditable by design
EXPERIENCE
Mobile, multilingual, inclusive
Field workers with no desktop · Arabic/English · accessible self-service from day one
OUR MISSION
A single HR operating system that is statutory-correct, mobile-first and built for how Egyptian organisations actually work.
PRAXION HROS · Discovery Phase Sign-Off · PRX-DISC-SO-001 v1.2
3 / 16

## Slide 4
03 · DISCOVERY APPROACH
How we ran the six weeks
1
FRAME
Week 1
Charter, mandate, scope guardrails, stakeholder map
2
LEARN
Week 2–3
Interviews, shadowing, document + legacy review
3
WORKSHOP
Week 3–4
Co-design sessions per module · pain points · process maps
4
DOCUMENT
Week 4–5
22 BRDs · 55+ user stories · acceptance criteria
5
REVIEW
Week 6–7
Reviewer sign-off · brand + roadmap · board pack
DISCOVERY METRICS
32
Stakeholder interviews
18
Co-design workshops
22
BRDs signed by reviewers
160
Requirement decisions logged
6
Artefact types produced
All artefacts stored in /Praxion-HROS/ with dual-location mirrors under /Modules/M1–M13/.
PRAXION HROS · Discovery Phase Sign-Off · PRX-DISC-SO-001 v1.2
4 / 16

## Slide 5
04 · STAKEHOLDERS & TEAM
Who we spoke to — and who'll deliver
STAKEHOLDERS CONSULTED
32 PEOPLE
Executive sponsors
CEO, COO, CHRO · 4 people
HR operations
HR Director, HR Ops, Payroll, Benefits · 7 people
Line management
Regional & functional managers from pilot entities · 9 people
Field & frontline
Site supervisors, contractor leads, multilingual reps · 6 people
Finance · Legal · IT
CFO, Legal Counsel, CIO/CISO · 6 people
CORE PROGRAMME TEAM
6 FTE
Project Director
Sabry M. · accountable end-to-end · board interface
HRIS Lead / Architect
Functional + data model ownership · M1, M3, M10
Payroll Lead
Statutory, M6 · SIA / ETA / bank integrations
Talent & Dev Lead
M2, M4, M5 · ATS, performance, learning
Product + UX
M11 Mobile + cross-module design system
Delivery + QA
Sprint cadence, release train, UAT coordination
GOVERNANCE
Steerco
Monthly · CEO, CFO, CHRO, CIO · decisions + escalations
Working groups
Weekly per module · functional owners + leads
Review board
Quarterly · external HR + payroll reviewers + legal
PRAXION HROS · Discovery Phase Sign-Off · PRX-DISC-SO-001 v1.2
5 / 16

## Slide 6
05 · CURRENT-STATE FINDINGS
What discovery revealed about the AS-IS
FRAGMENTED TOOLS
7+ disconnected systems
Excel HRIS, paper personnel files, local payroll tool, WhatsApp leave requests, shared inboxes for expenses, a separate attendance biometric, legacy ATS spreadsheets — no single source of truth.
MANUAL PROCESSES
High effort · low accuracy
Monthly payroll takes ~6 days per entity. Onboarding spans 3+ teams with no tracking. Leave approvals routed by WhatsApp and email screenshot — hard to audit, easy to lose.
COMPLIANCE EXPOSURE
Audit-reactive, not audit-ready
SIA/ETA filings built ad-hoc each period. PDP Law 151/2020 DPIA has not been run. No central audit log for HR/payroll decisions. Contractor misclassification risk flagged by Legal.
FIELD WORKER GAP
~60% of people are excluded
Field, construction and retail staff have no desktop, limited connectivity, mixed literacy, and often operate in Arabic-only. Existing HR tools are desktop + English — they don't reach the majority of the workforce.
"We are not short of effort — we are short of a system. Every month we rebuild the same payroll by hand." — HR Director interview, Mar 2026
PRAXION HROS · Discovery Phase Sign-Off · PRX-DISC-SO-001 v1.2
6 / 16

## Slide 7
06 · FUTURE-STATE VISION
One Praxion HROS — four design principles
THE VISION
An integrated HR operating system where the system of record, workflows, payroll, talent and analytics share one data model — accessible to every employee on mobile, in their language, with compliance built in.
SINGLE SOURCE OF TRUTH
One data model
Employee, org, contract, time, pay all live in one schema · every module reads and writes it · one audit trail.
SELF-SERVICE FIRST
Employee is the actor
Requests, approvals, updates, docs, learning, goals — employees and managers act directly on mobile or web.
AUTOMATION BY DEFAULT
Workflows, not tickets
JML, payroll run, onboarding journey, expenses — codified workflows with SLAs, escalations, and auditable outcomes.
COMPLIANCE BY DESIGN
Statutory + privacy native
Egyptian payroll, SIA/ETA, PDP Law 151/2020, banking files, audit log — shipped in the platform, not bolted on.
WHAT CHANGES FOR THE BUSINESS
Payroll cycle
6 days → 1 day
Onboarding
Fragmented → single 10-day journey
Field adoption
~0% → Day-1 Arabic mobile
Audit-readiness
Reactive → real-time
PRAXION HROS · Discovery Phase Sign-Off · PRX-DISC-SO-001 v1.2
7 / 16

## Slide 8
07 · DISCOVERY AT A GLANCE
What six weeks of discovery produced
13
MODULES SCOPED
M1–M13 with functional maps
22
BRDs WRITTEN
Business Requirements, signed reviewers
55+
CAPABILITIES
Defined for Phase 1 NOW pillar
100%
STORIES WRITTEN
All user stories validated
DISCOVERY ACTIVITIES · MARCH → APRIL 2026
W1-2
Kick-off
03 Mar '26
W2-3
Research
10 Mar '26
W3-4
Workshops
17 Mar '26
W4-5
BRDs
24 Mar '26
W5-6
User stories
02 Apr '26
W6
Artefacts
10 Apr '26
W7
Sign-off
21 Apr '26
ARTEFACTS PRODUCED · ALL IN /PRAXION-HROS/
BRDS
22 BRD docs · M1–M13 (some with v2–v4)
USER STORIES
All M1 stories + Recruitment, Onboarding
ORG CHART
Stakeholder map · RACI seeds
WORKFLOWS
Process maps · journey references
BRAND
Guidelines v2.0 · logos · presentation style
ROADMAP
11 phase gates · go-live 14 Mar 2027
PRAXION HROS · Discovery Phase Sign-Off · PRX-DISC-SO-001 v1.2
8 / 16

## Slide 9
08 · SCOPE CONFIRMED
All 13 modules documented, grouped by function
Foundation
People
Money
Intelligence
Access
M1
Core HRIS
Employee system of record · JML workflows
✓
M10
System Admin
Identity · RBAC · audit log
✓
M2
Recruitment / ATS
Requisitions → offer · talent pool
✓
M3
Onboarding / Off
Day-1 journeys · offboarding checklists
✓
M4
Performance / KPIs
Goals · check-ins · reviews
✓
M5
Training / LMS
Catalogue · enrollments · completions
✓
M6
Payroll & Comp
Egyptian statutory payroll · payslips
✓
M7
Benefits & Expenses
Entitlements · claims · reimbursement
✓
M8
Contractor Mgmt
Non-employee workforce · SOW · billing
✓
M9
Analytics & Reports
Pre-built dashboards · export
✓
M11
Mobile App (ESS)
Self-service on iOS + Android
✓
M12
Client Portal
Multi-tenant client onboarding (Phase 2)
✓
M13
Billing & Invoicing
Revenue contracts · invoice generation
✓
PRAXION HROS · Discovery Phase Sign-Off · PRX-DISC-SO-001 v1.2
9 / 16

## Slide 10
09 · PHASE 1 COMMITMENTS
What Phase 1 will deliver — by time horizon
NOW
Apr 2026 – Mar 2027
Employee system of record + org chart + JML workflows
Monthly Egyptian payroll + statutory reports + payslips
ATS: requisitions → offer · Onboarding journeys
Performance / OKRs · Learning catalogue · Benefits & expenses
Pre-built HR dashboards · ESS web + mobile
NEXT
Apr 2027 – Dec 2027
Client Portal GA · multi-tenant client onboarding
Multi-country payroll (GCC) · variable pay · comp-review
Self-serve report builder · scheduled distribution
Continuous check-ins · calibration · competency frameworks
Offline mobile for timesheets / expenses · biometric unlock
LATER
2028 and beyond
AI-assisted org design · predictive attrition · skills graph
AI screening & ranking · video-interview analytics
Talent marketplace · succession planning · equity / LTI
Natural-language analytics · benchmarking datasets
Agentic HR chatbot · life-event journeys · voice
12 product pillars · 55+ capabilities in NOW · Full backlog: /Modules/M1–M13/User-Stories/
PRAXION HROS · Discovery Phase Sign-Off · PRX-DISC-SO-001 v1.2
10 / 16

## Slide 11
10 · PHASE 1 ROADMAP
11 months · eight gates · go-live 14 Mar 2027
P0
Mobilise
15 Apr – 15 May '26
Charter, RACI, squads
P1
Discover
15 May – 15 Jun '26
Functional spec + NFRs
P2
Design
Jun – Aug '26
Data model · UX flows
P3
Build
Aug '26 – Jan '27
Core HRIS · Payroll · Admin
P4
Integrate
Oct '26 – Feb '27
SIA · ETA · Banking · SSO
P5
UAT
Jan – Feb '27
Payroll parallel run · user testing
P6
Stabilise
Feb – Mar '27
Performance · security · fixes
P7
Go-live
14 Mar 2027
Cut-over · hypercare · comms
PARALLEL WORKSTREAMS
Functional
Squad-led build across M1, M3, M6, M10, M11 + shared M2/M4/M5/M7 backlog
Data
Data model · migration rehearsals (3) · historical pay + PII · cut-over dry-runs
Integrations
SIA API · ETA e-receipts · banking file formats · SSO (OIDC/SAML) · directory sync
Security
RBAC · audit log · PDP Law DPIA · pen-test + remediation before UAT
Change
Comms cadence · multilingual training · champions network · ESS mobile roll-out
PRAXION HROS · Discovery Phase Sign-Off · PRX-DISC-SO-001 v1.2
11 / 16

## Slide 12
11 · SUCCESS CRITERIA
How we'll measure Phase 1 — KPIs and thresholds
DELIVERY
On time, on scope, on quality
Go-live date
14 Mar 2027
No slip > 2 weeks
Scope completion
100% of NOW
All 12 NOW pillars live
Defect escape
< 2 P1 / month
After 30-day hypercare
ADOPTION
People actually use it
ESS mobile activation
≥ 85%
Within 90 days post-go-live
Manager self-service
≥ 75%
Of requests via system, not email
Training completion
≥ 95%
For core workflows, pre-go-live
ACCURACY
Numbers we stake our name on
Payroll accuracy
≥ 99.9%
vs. parallel-run baseline
Statutory filings
0 late / month
SIA + ETA
Data-migration error
< 0.5%
Across 50k+ records
BUSINESS VALUE
Why we built it
Payroll cycle time
6 d → 1 d
Per entity, per month
Onboarding time-to-ready
15 d → 7 d
Offer-accept to day-1-ready
HR cost-to-serve
−20%
Vs. FY2025 baseline
Baselines captured during Discovery · targets confirmed with exec sponsors · dashboards ship with M9 (Analytics).
PRAXION HROS · Discovery Phase Sign-Off · PRX-DISC-SO-001 v1.2
12 / 16

## Slide 13
12 · WHAT DISCOVERY SURFACED
Programme risks & external dependencies
PROGRAMME RISKS
LIKELIHOOD · IMPACT
Scope aggression vs. team size
6 people delivering 13 modules in 11 months — velocity assumption must hold
HIGH
HIGH
Data migration from legacy
Excel + paper + WhatsApp → structured HRIS; 3 rehearsals scheduled
MED
HIGH
Payroll accuracy at cut-over
2–3 parallel-run cycles vs. legacy before statutory sign-off
MED
HIGH
Change management / adoption
Field workers with no desktop; multilingual ESS + roadshow + training
HIGH
MED
Key-person concentration
Small team — illness or attrition in Core/Payroll squad delays P3
MED
MED
EXTERNAL DEPENDENCIES
OWNER · NEEDED BY
Social Insurance Authority API
Required for Payroll statutory filings (Form 2 / Form 6)
LEGAL · PAYROLL
Q4 2026
Egyptian Tax Authority filing
e-receipt & withholding tax integration
FINANCE
Q4 2026
Banking disbursement files
Partner bank(s) file-format sign-off for salary transfer
FINANCE
Q1 2027
PDP Law 151/2020 DPIA
Data Protection Impact Assessment approval
LEGAL · CISO
Q1 2027
External pen-test vendor
Pre-go-live security assessment + remediation
CISO
Feb 2027
PRAXION HROS · Discovery Phase Sign-Off · PRX-DISC-SO-001 v1.2
13 / 16

## Slide 14
13 · CHANGE & ADOPTION
How we bring the organisation with us
COMMS
Right message, right channel
Exec cascade · all-hands moments at each gate · multilingual digest for field
TRAINING
Role-based, just-in-time
Core roles certified pre-go-live · ESS micro-lessons on mobile · in-context tips
CHAMPIONS
Peer advocates on the ground
1 champion per ~50 people · trained early · office hours + feedback loop
FEEDBACK
Listen, measure, adjust
Pulse surveys per gate · adoption dashboard · retros into backlog every fortnight
ROLLOUT WAVES
Wave 1 · Sponsors + HR ops
May – Aug 2026
Exec briefings · HR Ops co-build · champions recruited
Wave 2 · Pilot entity
Sep – Dec 2026
One entity end-to-end · parallel run · feedback loops tight
Wave 3 · All managers
Jan – Feb 2027
Manager self-service certified · approval cutover · comms burst
Wave 4 · All employees
Mar – Jun 2027
ESS mobile · Arabic-first · site roadshow · champion office hours
Mobile-first · Arabic + English · low-literacy friendly · offline-tolerant — no one gets left behind.
PRAXION HROS · Discovery Phase Sign-Off · PRX-DISC-SO-001 v1.2
14 / 16

## Slide 15
14 · DECISION & NEXT STEPS
We're asking the board to
sign off discovery.
WHAT WE'RE ASKING FOR
Approvals
Endorse discovery outputs
13 BRDs · user stories · workflows · roadmap as the basis for Phase 1
Green-light Phase 1 mobilisation
Kick-off 15 May 2026 · go-live target 14 March 2027 fixed
Ring-fence team + external asks
Core squad of 6 · Legal / Finance alignment by Q4 2026
WHAT HAPPENS NEXT
Next 60 days
P0 Mobilise · 15 Apr – 15 May 2026
Charter, RACI, governance signed; squads formed
P1 Discover kick-off · 15 May 2026
Functional spec + data model + NFRs begin
Steerco rhythm · from 30 Apr 2026
Monthly steerco + weekly exec summary; first report 30 Apr
PRX-DISC-SO-001 · v1.2 · Owner: Project Director — Praxion HROS
15 / 16

## Slide 16
APPENDIX
Artefact index — where to find it all
BRDs
• M1 · Core HRIS (v2)
• M2 · Recruitment / ATS
• M3 · Onboarding / Off
• M4 · Performance / KPIs
• M5 · Training / LMS
• M6 · Payroll & Comp (v3)
• M7 · Benefits & Expenses
• M8 · Contractor Mgmt
• M9 · Analytics
• M10 · System Admin
• M11 · Mobile App (ESS)
• M12 · Client Portal
• M13 · Billing & Invoicing
USER STORIES
• M1 · 18 stories · signed
• M2 · 12 stories · signed
• M3 · 10 stories · signed
• M4 · 8 stories
• M5 · 7 stories
• M6 · 14 stories
• M7 · 6 stories
• M8 · 5 stories
• M9 · 6 stories
• M10 · 9 stories
• M11 · 11 stories
• M12 · draft
• M13 · draft
PROCESS & DATA
• Org chart + RACI seed
• JML workflow
• Payroll cycle map
• Onboarding journey
• Leave + absence flow
• Performance cycle
• Expenses & approvals
• Offboarding checklist
• Audit / compliance map
• Integration register
• Data model v0.5
• NFR register v1
• Glossary + acronyms
BRAND & EXEC
• Brand Guidelines v2.0
• Logo package v2
• Presentation style
• Iconography + colours
• Typography tokens
• Voice + tone
• Executive roadmap v1.0
• Discovery sign-off (this)
• Doc ID register
• Version & owner log
• Risk + issue log v1
• Steerco pack template
• Status report template
All artefacts live under /Praxion-HROS/ with dual-location mirrors under /Modules/M1–M13/{BRDs, User-Stories, Workflows}/.
PRAXION HROS · Discovery Phase Sign-Off · PRX-DISC-SO-001 v1.2
16 / 16