## Slide 1
PRAXION HROS
Discovery Phase
Complete
Executive Briefing | April 2026
Egybell · Praxion HR Operating System

## Slide 2
AGENDA
01
Project Overview
02
Discovery Phase Outcomes
03
User Stories & Backlog
04
Module Breakdown & Priority
05
System Architecture
06
Security & Access Framework
07
Timeline & Roadmap
08
Deliverables & Next Steps
Praxion HROS | Discovery Phase Completion

## Slide 3
PROJECT OVERVIEW
Praxion HROS is a comprehensive, multi-tenant Human Resource Operating System built for Egybell to deliver enterprise-grade HR management as a SaaS platform.
13
Functional Modules
195
User Stories
1,216
Story Points
TECHNOLOGY STACK
NestJS
Microservices
React
Next.js
PostgreSQL
Database
TypeScript
End-to-End
Redis &
RabbitMQ
Praxion HROS | Discovery Phase Completion

## Slide 4
DISCOVERY PHASE
Objectives & Outcomes
OBJECTIVES
✓
Define complete functional scope across all HR domains
✓
Capture & prioritise user stories with story point estimates
✓
Design system architecture for scale & multi-tenancy
✓
Establish security framework & role-based access
✓
Build detailed implementation roadmap with milestones
KEY OUTCOMES
13
BRDs Completed
195
User Stories Defined
14
User Personas Mapped
18
Security Roles Defined
11
Implementation Phases
Mar 2027
Target Go-Live
Praxion HROS | Discovery Phase Completion

## Slide 5
USER STORIES OVERVIEW
195 stories across 13 modules • 1,216 total story points
79
P0 — Must Have (40.5%)
71
P1 — Should Have (36.4%)
45
P2 — Nice to Have (23.1%)
14 user personas identified, covering HR Admins, Managers, Employees, Recruiters, Finance, IT, and Executive roles.
Chart: 
| M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13
Story Points | 95 | 88 | 80 | 84 | 95 | 120 | 81 | 75 | 102 | 128 | 70 | 78 | 120
Praxion HROS | Discovery Phase Completion

## Slide 6
MODULE BREAKDOWN
Module | Stories | Points | P0 | P1 | P2
M1 Core HRIS | 15 | 95 | 11 | 4 | 0
M2 Recruitment & ATS | 15 | 88 | 10 | 5 | 0
M3 Onboarding & Offboarding | 15 | 80 | 8 | 6 | 1
M4 Performance & KPIs | 15 | 84 | 5 | 7 | 3
M5 Training & LMS | 15 | 95 | 1 | 5 | 9
M6 Payroll & Compensation | 15 | 120 | 11 | 4 | 0
M7 Benefits & Expenses | 15 | 81 | 1 | 7 | 7
M8 Contractor Management | 15 | 75 | 3 | 7 | 5
M9 Analytics & Reporting | 15 | 102 | 2 | 6 | 7
M10 System Administration | 15 | 128 | 9 | 5 | 1
M11 Mobile App | 15 | 70 | 3 | 6 | 6
M12 Client Portal | 15 | 78 | 8 | 3 | 4
M13 Billing & Invoicing | 15 | 120 | 7 | 6 | 2
TOTAL | 195 | 1,216 | 79 | 71 | 45
Praxion HROS | Discovery Phase Completion

## Slide 7
PRIORITY & PHASE ALLOCATION
Chart: 
| P0 Must Have | P1 Should Have | P2 Nice to Have
Priority | 79 | 71 | 45
DELIVERY PHASES
Phase 1: Foundation
M1, M6, M10, M13 • 60 stories • 463 pts
Phase 2: Talent Acquisition
M2, M3, M12 • 45 stories • 246 pts
Phase 3: Performance & Growth
M4, M5, M7, M8 • 60 stories • 335 pts
Phase 4: Intelligence
M9, M11 • 30 stories • 172 pts
Praxion HROS | Discovery Phase Completion

## Slide 8
SYSTEM ARCHITECTURE
Modern, Scalable, Multi-Tenant
FRONTEND
React / Next.js
SSR + SPA Hybrid
Tailwind CSS
Responsive Design
BACKEND
NestJS Microservices
15 Domain Services
GraphQL + REST
Event-Driven
DATA LAYER
PostgreSQL
Row-Level Security
Redis Caching
TimescaleDB
INFRASTRUCTURE
Docker + K8s
CI/CD Pipeline
Observability
Multi-Tenant
10 Architecture Decision Records • 23 Containers • 14 External Actors

## Slide 9
SECURITY & ACCESS FRAMEWORK
18
Security Roles
13
Module Scopes
7
Action Types
8
SoD Conflicts
RBAC MODEL
• Role-based access with module-level granularity
• 7 actions: Create, Read, Update, Delete, Approve, Export, Configure
• Hierarchical role inheritance (Super Admin → User)
• Multi-tenant isolation with row-level security
GOVERNANCE
• 15-section Access Policy document
• Segregation of Duties (8 conflict rules)
• Joiner-Mover-Leaver lifecycle management
• Quarterly access review cadence
Praxion HROS | Discovery Phase Completion

## Slide 10
TIMELINE & MILESTONES
March 2026 → March 2027 • 11 Implementation Phases
P0
Mobilise
P1
Foundations
P2
Core HR
P3
Payroll Engine
P4
Recruitment & ATS
P5
Onboarding
P6
Performance
P7
Training & Benefits
P8
Analytics & Mobile
P9
Integration & UAT
P10
Scale & Go-Live
Quarter | Phases | Focus Areas
Q1 2026 | P0 – P1 | Mobilise, Platform Foundations, DevOps Setup
Q2 2026 | P2 – P3 | Core HR, Payroll Engine, Billing
Q3 2026 | P4 – P6 | Recruitment, Onboarding, Performance
Q4 2026 | P7 – P8 | Training, Benefits, Analytics, Mobile
Q1 2027 | P9 – P10 | Integration, UAT, Go-Live (14 March 2027)
Praxion HROS | Discovery Phase Completion

## Slide 11
DELIVERABLES COMPLETED
✓
Business Requirements Documents
13 modules
Detailed BRD per module
✓
User Stories Backlog
195 stories
Prioritised & estimated
✓
System Architecture
3-part spec
Executive + C4 + Technical
✓
User Access Matrix
18 roles
RBAC with SoD controls
✓
User Access Policy
15 sections
Governance framework
✓
Implementation Roadmap
11 phases
Week-by-week plan
Praxion HROS | Discovery Phase Completion

## Slide 12
KEY RISKS & MITIGATIONS
Risk | Severity | Mitigation Strategy
Scope Creep | High | Locked BRDs with formal change control; phased delivery de-risks scope expansion
Payroll Complexity | High | Dedicated payroll engine phase (P3); Egyptian labour law compliance built into BRD
Integration Dependencies | Medium | API-first architecture; dedicated integration phase (P9) with mock services
Resource Availability | Medium | Capacity planning in roadmap; cross-training to reduce key-person risk
Multi-Tenant Data Isolation | Medium | Row-level security in PostgreSQL; validated with ADR-003
Praxion HROS | Discovery Phase Completion

## Slide 13
NEXT STEPS
Transitioning from Discovery to Build
P0: Team Mobilisation
Onboard development team, set up environments, finalise tech stack tooling
Mar – Apr 2026
P1: Platform Foundations
Core infrastructure, CI/CD pipeline, authentication framework, base UI components
Apr – Jun 2026
Stakeholder Sign-Off
BRD approval from all department heads, architecture review board sign-off
Immediate
Sprint Planning
Break Phase 1 modules (M1, M6, M10, M13) into 2-week sprint cycles
Apr 2026
Praxion HROS | Discovery Phase Completion

## Slide 14
Thank You
Questions & Discussion
Sabry Mohamed • Project Director
Praxion HROS • Egybell
mohamed.sabry@praxionhr.com