## README
Praxion HROS — Phase-1 Jira Backlog v1.0
Project key: PRX · 22 × 2-week sprints · 2026-05-01 → 2027-03-18 · Team: 2 FE + 2 BE + 1 QA + TL + PO + Designer
HOW TO IMPORT INTO JIRA CLOUD
1. Create Jira project | In Jira Cloud → Create project → Scrum template → Name: Praxion HROS → Key: PRX
2. Configure components | Settings → Components → add: M1-Core-HRIS, M10-Sys-Admin, Platform, Integrations, Design, DevOps
3. Configure labels & priorities | Priorities already in Jira (P0-P4). Labels are free-text so they auto-create on import.
4. Import Epics first | System → External System Import → CSV. Upload Epics sheet (save as CSV). Map: Issue Type, Summary, Description, Priority, Components, Labels.
5. Import Stories | Same CSV import. Map: Issue Type, Summary, Description, Priority, Assignee, Epic Link, Sprint, Components, Labels, Story Points.
6. Import Sub-tasks | Same CSV import. Map: Issue Type, Summary, Parent, Assignee, Original Estimate.
7. Create sprints in Jira | Backlog view → Create Sprint → name + dates per Sprints sheet. Bulk-move stories into sprints by the Sprint field.
8. Set up Board filters | Board → Configure → quick-filters: FE (label=fe), BE (label=be), QA (label=qa), Design (label=design), Bugs (type=Bug).
SHEETS IN THIS WORKBOOK
Sprints | 22 sprints + Sprint 0 with dates, phase gate, goal, target SP budget.
Team | 8-seat roster with role, discipline, capacity per sprint, Jira labels.
Epics | 9 epics ready for Jira CSV import. Covers P0-P7 + Bug Tracker.
Stories | 219 stories across all phase gates. Jira CSV format with Epic Link + Sprint + SP.
Sub-tasks | 575 sub-tasks (representative patterns for stories ≥3 SP). Each has Parent link to its story.
Workload | SP per assignee per sprint. Formulas. Flags over-allocation.
Bug-Log | Empty Jira-CSV-ready bug template. Log defects as they arise, then bulk-import to Jira project PRX.
Capacity-Check | Sprint-by-sprint utilisation %. Target: ≤95%. Formulas.
FIELD MAPPING CHEAT-SHEET
Summary | Jira ‘Summary’ field. Keep ≤ 240 chars for readability.
Description | Jira ‘Description’ (wiki markup). Long-form context.
Priority | P0 Blocker · P1 Critical · P2 Major · P3 Minor · P4 Trivial.
Assignee (role) | Role placeholder: DEV-FE-1, DEV-BE-1, QA-1, TL, PO, DES-1. Replace with real user IDs after hiring.
Epic Link | PRX-E0 … PRX-E8. Must match Epic key in the Epics sheet.
Sprint | Sprint name from Sprints sheet (e.g., ‘Sprint 6 — P3 Core Build · Employee records CRUD’).
Components | One of: M1-Core-HRIS, M10-Sys-Admin, Platform, Integrations, Design, DevOps.
Labels | Comma-sep: fe/be/qa/devops/design/po/tl + foundation/platform/bug/security/a11y/uat/training/migration/cutover/go-live.
Story Points | Fibonacci: 1, 2, 3, 5, 8. Stories ≥8 SP should be split before sprint start.
Original Estimate (subtasks) | Hours. Rough guide for daily stand-up planning.
WHY THIS SHAPE
Discipline split (FE/BE/QA/DES/PO/TL) | Every feature surfaces at least one BE + one FE + one QA story so work is parallelisable across the 4 devs.
Epic per phase gate | P0-P7 + Bug Tracker. Lets you track burndown at gate level and maintain the rhythm set in the Executive Roadmap v2.0.
Ramp-up sprints (S1-S3 lower SP) | S0 20 SP, S1 35 SP, S2 45 SP, S3 50 SP. Team hits 56 SP steady state by S4.
Buffer epic (PRX-E8 Bugs) | 80 SP reserved across the project for bug work discovered mid-sprint. Prevents scope creep eroding feature delivery.
NEXT STEPS
KNOWN CAPACITY RISK (flagged for TL refinement)
Core-build sprints (S6-S10) run at 108-116% of dev capacity | With 2 BE + 2 FE devs (56 SP/sprint), honest scope to deliver M1 + M10 by 14-Mar needs ~64 SP/sprint in Core Build. Options: (a) add a 5th dev (3rd BE), (b) extend by 2 sprints, or (c) accept 15-16 SP/dev during hot phase. Decision needed at Sprint 0 planning.
A) Connect Atlassian Rovo MCP | If you enable the Atlassian connector in Cowork, I can push this backlog directly into Jira instead of CSV-import.
B) Hire the 5 roles (TL, FE×2, BE×2, QA, half-time Designer) | Plan assumes these seats are filled by 2026-05-01 (Sprint 0 start).
C) Lock the sprint calendar | Confirm the sprint dates in Sprints sheet fit statutory holidays + your fiscal calendar. Adjust before import.
D) Triage the backlog with TL | Once TL is onboarded, 2-hour refinement to confirm SP sizing + story order before Sprint 1.

## Sprints
Sprint calendar — Phase-1 (22 sprints, 2-week cadence)
Sprint # | Start date | End date | Phase gate | Sprint goal | Target SP | Notes
Sprint 0 | 2026-05-01 | 2026-05-14 | P0 close / Kick-off | Team onboarded, environments ready, CI/CD green, design system scaffold | 20 | Ramp sprint
Sprint 1 | 2026-05-15 | 2026-05-28 | P1 Discover | Discovery M1 — employee records & org structure flow | 35 | Ramp sprint
Sprint 2 | 2026-05-29 | 2026-06-11 | P1 Discover | Discovery M1 — positions & contracts + M10 discovery | 45 | Ramp sprint
Sprint 3 | 2026-06-12 | 2026-06-25 | P1→P2 Design | Design system complete + all M1 wireframes signed off | 50 | Ramp sprint
Sprint 4 | 2026-06-26 | 2026-07-09 | P2 Foundations | Tenancy model + SSO + RBAC scaffold | 56
Sprint 5 | 2026-07-10 | 2026-07-23 | P2 Foundations | Audit log + platform shell + nav | 56
Sprint 6 | 2026-07-24 | 2026-08-06 | P3 Core Build | Employee records CRUD + search + data model in place | 56
Sprint 7 | 2026-08-07 | 2026-08-20 | P3 Core Build | Org structure + positions + assignment | 56
Sprint 8 | 2026-08-21 | 2026-09-03 | P3 Core Build | Contracts + documents vault + signed URLs | 56
Sprint 9 | 2026-09-04 | 2026-09-17 | P3 Core Build | Lifecycle events + approvals engine + notifications | 56
Sprint 10 | 2026-09-18 | 2026-10-01 | P3→P4 | M1 polish + bulk import/export + M10 scaffold | 56
Sprint 11 | 2026-10-02 | 2026-10-15 | P4 Adjacent | M10 users, roles, permissions admin | 56
Sprint 12 | 2026-10-16 | 2026-10-29 | P4 Adjacent | M10 tenant config + org chart admin + holiday calendar | 56
Sprint 13 | 2026-10-30 | 2026-11-12 | P4 Adjacent | M10 audit dashboard + integrations + webhooks + API tokens | 56
Sprint 14 | 2026-11-13 | 2026-11-26 | P4→P5 | Feature-freeze — a11y + bundle + perf optimizations | 56
Sprint 15 | 2026-11-27 | 2026-12-10 | P5 Harden | Load test + security scan fixes + DR drill | 56
Sprint 16 | 2026-12-11 | 2026-12-24 | P5 Harden | Pen-test fixes + data migration dry-runs | 56
Sprint 17 | 2026-12-25 | 2027-01-07 | P5→P6 | Holiday-reduced · UAT prep — scenarios, test data, env | 35 | Holiday-reduced
Sprint 18 | 2027-01-08 | 2027-01-21 | P6 UAT | UAT round 1 + defect burndown | 56
Sprint 19 | 2027-01-22 | 2027-02-04 | P6 UAT | UAT round 2 + training content | 56
Sprint 20 | 2027-02-05 | 2027-02-18 | P6 UAT | UAT round 3 + cutover rehearsal | 56
Sprint 21 | 2027-02-19 | 2027-03-04 | P7 Cutover | Final fixes + go-live prep + rollback rehearsal | 56
Sprint 22 | 2027-03-05 | 2027-03-18 | P7 Go-Live | GO-LIVE 14-Mar-2027 + Day-1 hypercare | 56 | GO-LIVE sprint

## Team
Delivery team — Phase-1 (8 seats)
Jira User ID (placeholder) | Name | Role | Jira label | Capacity SP / sprint | Email
PRX-PO | Sabry M. (placeholder) | Project Director / PO | po | — | mohamed.sabry@praxionhr.com
PRX-TL | TL — to hire | Tech Lead | tl | 8 | tl@praxionhr.com
PRX-FE1 | DEV-FE-1 — to hire | Frontend Engineer | fe | 14 | fe1@praxionhr.com
PRX-FE2 | DEV-FE-2 — to hire | Frontend Engineer | fe | 14 | fe2@praxionhr.com
PRX-BE1 | DEV-BE-1 — to hire | Backend Engineer | be | 14 | be1@praxionhr.com
PRX-BE2 | DEV-BE-2 — to hire | Backend Engineer | be | 14 | be2@praxionhr.com
PRX-QA1 | QA-1 — to hire | QA Engineer | qa | 14 | qa1@praxionhr.com
PRX-DES | DES-1 — to hire (full-time S1-S3 · 50% from S4) | Product Designer | design | 14→7 | des1@praxionhr.com
|  |  | Team capacity / sprint → | 0

## Epics
Epics — Jira CSV import format (9 epics)
Issue Type | Issue Key (for import reference) | Summary | Description | Priority | Assignee (role) | Components | Labels
Epic | PRX-E0 | P0 — Mobilisation close-out | Close out mobilization: environments, CI/CD, team onboarding, design-system scaffold. Sprint range: S0-0. | P1 | PO | Platform | foundation,platform
Epic | PRX-E1 | P1 — Discover & Design | Functional discovery + visual design for M1 Core HRIS and M10 Sys Admin. Ends with Design Sign-Off. Sprint range: S1-3. | P1 | TL | M1-Core-HRIS | foundation
Epic | PRX-E2 | P2 — Platform Foundations | Tenancy, SSO, RBAC, audit log, platform shell — the chassis before functional modules. Sprint range: S4-5. | P1 | TL | Platform | foundation,platform
Epic | PRX-E3 | P3 — M1 Core HRIS Build | Employee records, org structure, positions, contracts, documents, lifecycle events, approvals. Sprint range: S6-10. | P1 | TL | M1-Core-HRIS | foundation
Epic | PRX-E4 | P4 — M10 System Admin Build | M10 Sys Admin: users, roles, permissions, tenant config, audit dashboard, integrations. Sprint range: S11-14. | P2 | TL | M10-Sys-Admin | foundation
Epic | PRX-E5 | P5 — Hardening & Security | Perf, load-test, security review, pen-test fixes, DR drill, data migration rehearsal. Sprint range: S15-17. | P1 | TL | Platform | platform,qa
Epic | PRX-E6 | P6 — UAT & Defect Burndown | 3 UAT rounds with stakeholders, defect triage, training content, cutover rehearsal. Sprint range: S18-20. | P1 | QA-1 | Platform | qa
Epic | PRX-E7 | P7 — Cutover & Go-Live | Production cutover 14-Mar-2027 + Day-1 hypercare support. Sprint range: S21-22. | P0 | TL | Platform | foundation,platform
Epic | PRX-E8 | Bug Tracker (cross-cutting) | Defects raised during any sprint. Workflow: Open→Triaged→In Progress→Ready QA→Verified→Closed. Sprint range: S0-22. | P1 | QA-1 | Platform | bug

## Stories
Stories — Jira CSV import format (219 stories)
Issue Type | Summary | Description | Priority | Assignee | Epic Link | Sprint | Components | Labels | Story Points | Reporter
Story | DEVOPS: Provision dev/stage/prod environments | Kubernetes clusters + managed Postgres + S3 buckets + Redis across 3 envs. Networking + secrets vault. | P1 | DEV-BE-1 | PRX-E0 | Sprint 0 — P0 close / Kick-off · Team onboarded, environments ready, CI/C | Platform | devops,platform | 5 | PO
Story | DEVOPS: Set up CI/CD pipeline (BE + FE) | GitHub Actions: lint → test → build → deploy. Branch protection rules. Preview envs on PR. | P1 | DEV-BE-2 | PRX-E0 | Sprint 0 — P0 close / Kick-off · Team onboarded, environments ready, CI/C | Platform | devops,platform | 5 | PO
Story | FE: Bootstrap FE repo + design system package | Vite + React + TS + Tailwind + routing. Shared @praxion/ui package scaffold. Storybook. | P1 | DEV-FE-1 | PRX-E0 | Sprint 0 — P0 close / Kick-off · Team onboarded, environments ready, CI/C | Platform | fe,platform | 3 | PO
Story | FE: Design system token package (colors/type/spacing) | Brand v2.0 tokens wired into @praxion/tokens. TS types + CSS vars. Tailwind plugin. | P1 | DEV-FE-2 | PRX-E0 | Sprint 0 — P0 close / Kick-off · Team onboarded, environments ready, CI/C | Platform | fe,platform,design | 3 | PO
Story | QA: Test framework + first smoke tests | Playwright for e2e, Vitest for unit, Pact for contract. Smoke test hits staging health endpoint. | P1 | QA-1 | PRX-E0 | Sprint 0 — P0 close / Kick-off · Team onboarded, environments ready, CI/C | Platform | qa,platform | 2 | PO
Story | DEVOPS: Observability — logging + metrics + tracing | Stack: Loki + Prometheus + Grafana + OTEL. Dashboards for p50/p95 latency + error rate. | P1 | DEV-BE-1 | PRX-E0 | Sprint 0 — P0 close / Kick-off · Team onboarded, environments ready, CI/C | Platform | devops,platform | 2 | PO
Story | PO: Stakeholder interviews — Records management | Interview HR Ops + People team. Document: attributes, lifecycle states, data sources. | P1 | PO | PRX-E1 | Sprint 1 — P1 Discover · Discovery M1 — employee records & org st | M1-Core-HRIS | po,foundation | 3 | PO
Story | PO: Stakeholder interviews — Org structure | Interview Finance + HR Ops. Document: cost-centre model, reporting lines, org depth. | P1 | PO | PRX-E1 | Sprint 1 — P1 Discover · Discovery M1 — employee records & org st | M1-Core-HRIS | po,foundation | 3 | PO
Story | TL: Spike — Auth provider comparison (Auth0/Keycloak/Cognito) | POC 3 providers against SSO req. Document trade-offs + cost. Recommend provider. | P1 | TL | PRX-E1 | Sprint 1 — P1 Discover · Discovery M1 — employee records & org st | Platform | tl,platform | 3 | PO
Story | TL: Spike — Multi-tenancy pattern selection | Evaluate: row-level-sec vs schema-per-tenant vs db-per-tenant. Benchmark + recommend. | P1 | TL | PRX-E1 | Sprint 1 — P1 Discover · Discovery M1 — employee records & org st | Platform | tl,platform | 3 | PO
Story | DES: UX research synthesis (existing materials) | Synthesize discovery docs, Meeting-Docs-Apr22, master layout feedback. Personas + journeys. | P1 | DES-1 | PRX-E1 | Sprint 1 — P1 Discover · Discovery M1 — employee records & org st | M1-Core-HRIS | design,foundation | 5 | PO
Story | BE: Data model design — Employees + audit fields | ERD draft: employees, addresses, emergency contacts, identifiers. Include audit/soft-delete. | P1 | DEV-BE-1 | PRX-E1 | Sprint 1 — P1 Discover · Discovery M1 — employee records & org st | M1-Core-HRIS | be,foundation | 5 | PO
Story | BE: Data model design — Org structure + positions | ERD draft: org_units, positions, position_assignments, reporting_lines. Hierarchical queries. | P1 | DEV-BE-2 | PRX-E1 | Sprint 1 — P1 Discover · Discovery M1 — employee records & org st | M1-Core-HRIS | be,foundation | 5 | PO
Story | QA: Test strategy document (M1 Phase-1) | Strategy: pyramid (unit/int/e2e), tools, coverage targets, automation-manual split. | P1 | QA-1 | PRX-E1 | Sprint 1 — P1 Discover · Discovery M1 — employee records & org st | Platform | qa,foundation | 3 | PO
Story | FE: UI architecture decision record (ADR) | ADR: state mgmt (Zustand vs Redux), forms lib, validation lib, routing patterns. | P1 | DEV-FE-1 | PRX-E1 | Sprint 1 — P1 Discover · Discovery M1 — employee records & org st | Platform | fe,platform | 3 | PO
Story | DES: Master layout — high-fidelity (from approved low-fi) | Polish approved master layout: spacing, a11y contrast, responsive breakpoints, tokens applied. | P1 | DES-1 | PRX-E1 | Sprint 1 — P1 Discover · Discovery M1 — employee records & org st | Platform | design,platform | 5 | PO
Story | PO: Stakeholder interviews — Contracts & documents | Interview Legal + HR Ops. Contract types, lifecycle events, document retention policy. | P1 | PO | PRX-E1 | Sprint 2 — P1 Discover · Discovery M1 — positions & contracts + M | M1-Core-HRIS | po,foundation | 3 | PO
Story | PO: Stakeholder interviews — Lifecycle events | Interview HR Ops. Hire/promote/transfer/terminate workflows + approval chains. | P1 | PO | PRX-E1 | Sprint 2 — P1 Discover · Discovery M1 — positions & contracts + M | M1-Core-HRIS | po,foundation | 3 | PO
Story | PO: Stakeholder interviews — M10 Sys Admin | Interview IT Ops + Sys Admin. Tenant config, audit reqs, integrations needed. | P1 | PO | PRX-E1 | Sprint 2 — P1 Discover · Discovery M1 — positions & contracts + M | M10-Sys-Admin | po,foundation | 3 | PO
Story | BE: Data model design — Contracts + documents | ERD: contracts, contract_versions, documents, document_acl. Signed URL pattern. | P1 | DEV-BE-1 | PRX-E1 | Sprint 2 — P1 Discover · Discovery M1 — positions & contracts + M | M1-Core-HRIS | be,foundation | 3 | PO
Story | BE: Data model design — Lifecycle events + approvals | ERD: lifecycle_events, approval_workflows, approval_steps, approval_history. | P1 | DEV-BE-2 | PRX-E1 | Sprint 2 — P1 Discover · Discovery M1 — positions & contracts + M | M1-Core-HRIS | be,foundation | 3 | PO
Story | TL: Integration contract — SSO (OIDC) | OIDC flow spec: scopes, claims mapping, tenant routing. IdP dry-run. | P1 | TL | PRX-E1 | Sprint 2 — P1 Discover · Discovery M1 — positions & contracts + M | Platform | tl,platform | 5 | PO
Story | TL: Integration contract — Data imports (CSV/API) | Spec for bulk import: CSV schema, API endpoints, validation rules, error reporting. | P1 | TL | PRX-E1 | Sprint 2 — P1 Discover · Discovery M1 — positions & contracts + M | Platform | tl,platform | 3 | PO
Story | DES: Component library — Forms (inputs, selects, datepickers) | Hi-fi Figma components: text, number, select, multi-select, date, date-range. States. | P1 | DES-1 | PRX-E1 | Sprint 2 — P1 Discover · Discovery M1 — positions & contracts + M | Platform | design,platform | 5 | PO
Story | DES: Component library — Data display (tables, cards) | Hi-fi Figma: tables (sortable/filterable), cards, tiles, stats. Empty + loading states. | P1 | DES-1 | PRX-E1 | Sprint 2 — P1 Discover · Discovery M1 — positions & contracts + M | Platform | design,platform | 5 | PO
Story | DES: M1 Employee records wireframes (list + detail + edit) | Hi-fi screens: list, filters, detail (tabs), create/edit, quick-view. | P1 | DES-1 | PRX-E1 | Sprint 2 — P1 Discover · Discovery M1 — positions & contracts + M | M1-Core-HRIS | design,foundation | 5 | PO
Story | DES: M1 Org structure + Positions wireframes | Hi-fi: org chart viz, position list, assignment UI, bulk reorganise. | P1 | DES-1 | PRX-E1 | Sprint 3 — P1→P2 Design · Design system complete + all M1 wirefram | M1-Core-HRIS | design,foundation | 5 | PO
Story | DES: M1 Contracts + documents wireframes | Hi-fi: contract list, detail, lifecycle actions, documents vault, upload widget. | P1 | DES-1 | PRX-E1 | Sprint 3 — P1→P2 Design · Design system complete + all M1 wirefram | M1-Core-HRIS | design,foundation | 5 | PO
Story | DES: M1 Lifecycle events + approvals wireframes | Hi-fi: timeline, event wizard, approvals inbox, approval detail, notifications. | P1 | DES-1 | PRX-E1 | Sprint 3 — P1→P2 Design · Design system complete + all M1 wirefram | M1-Core-HRIS | design,foundation | 5 | PO
Story | DES: M10 Admin wireframes | Hi-fi: users admin, roles/permissions matrix, tenant config, audit dashboard. | P1 | DES-1 | PRX-E1 | Sprint 4 — P2 Foundations · Tenancy model + SSO + RBAC scaffold | M10-Sys-Admin | design,foundation | 5 | PO
Story | DES: Component library — Navigation + shell | Hi-fi: app header, collapsible sidebar, breadcrumbs, user menu. Dark-mode vars. | P1 | DES-1 | PRX-E1 | Sprint 2 — P1 Discover · Discovery M1 — positions & contracts + M | Platform | design,platform | 5 | PO
Story | QA: Test environment setup (local + stage) | Docker compose for local. Stage seeded with anonymized prod-shape data. | P1 | QA-1 | PRX-E1 | Sprint 3 — P1→P2 Design · Design system complete + all M1 wirefram | Platform | qa,platform | 3 | PO
Story | QA: Automation framework scaffolding | Playwright config, Pact broker, CI wiring, reporting to Allure. | P1 | QA-1 | PRX-E1 | Sprint 3 — P1→P2 Design · Design system complete + all M1 wirefram | Platform | qa,platform | 5 | PO
Story | FE: Shared components — Button / Input / Select | Implement from design tokens. Storybook stories. Unit tests. | P1 | DEV-FE-1 | PRX-E1 | Sprint 3 — P1→P2 Design · Design system complete + all M1 wirefram | Platform | fe,platform | 5 | PO
Story | FE: Shared components — Table / Card / Badge | Implement from design tokens. Storybook stories. Unit tests. | P1 | DEV-FE-2 | PRX-E1 | Sprint 3 — P1→P2 Design · Design system complete + all M1 wirefram | Platform | fe,platform | 5 | PO
Story | BE: API convention doc + OpenAPI scaffolding | Endpoint naming, pagination, filtering, errors, versioning. OpenAPI spec in repo. | P1 | DEV-BE-1 | PRX-E1 | Sprint 3 — P1→P2 Design · Design system complete + all M1 wirefram | Platform | be,platform | 3 | PO
Story | BE: Database migration tooling + seed-data pattern | Choose migration tool, set up seeds for local/stage. Document rollback procedure. | P1 | DEV-BE-2 | PRX-E1 | Sprint 3 — P1→P2 Design · Design system complete + all M1 wirefram | Platform | be,platform | 3 | PO
Story | PO: Design sign-off review session | Review all wireframes + components with HR Ops, Sabry, TL. Capture sign-off. | P1 | PO | PRX-E1 | Sprint 3 — P1→P2 Design · Design system complete + all M1 wirefram | M1-Core-HRIS | po,foundation | 2 | PO
Story | BE: Tenancy data model + migrations | tenants table, tenant_id FK on all relevant tables. Middleware to inject tenant context. | P0 | DEV-BE-1 | PRX-E2 | Sprint 4 — P2 Foundations · Tenancy model + SSO + RBAC scaffold | Platform | be,platform,foundation | 8 | PO
Story | BE: Tenant-isolation middleware + query guards | Middleware rejects cross-tenant reads/writes. Query-builder guards + unit tests. | P0 | DEV-BE-1 | PRX-E2 | Sprint 4 — P2 Foundations · Tenancy model + SSO + RBAC scaffold | Platform | be,platform,foundation | 5 | PO
Story | BE: SSO integration — OIDC provider connection | Connect to chosen IdP. Callback, state, PKCE. Claim→user mapping. | P0 | DEV-BE-2 | PRX-E2 | Sprint 4 — P2 Foundations · Tenancy model + SSO + RBAC scaffold | Platform | be,platform,foundation | 8 | PO
Story | BE: SSO session handling + refresh tokens | JWT access + refresh pattern. Session storage. Logout flow + token revocation. | P0 | DEV-BE-2 | PRX-E2 | Sprint 4 — P2 Foundations · Tenancy model + SSO + RBAC scaffold | Platform | be,platform,foundation | 5 | PO
Story | BE: RBAC schema (roles, permissions, role_permissions) | Data model + migrations. Seed default roles (SysAdmin, HRAdmin, Manager, Employee). | P0 | DEV-BE-1 | PRX-E2 | Sprint 4 — P2 Foundations · Tenancy model + SSO + RBAC scaffold | Platform | be,platform,foundation | 5 | PO
Story | BE: RBAC enforcement middleware + decorators | Route-level + method-level permission checks. Returns 403 with permission name. | P0 | DEV-BE-2 | PRX-E2 | Sprint 4 — P2 Foundations · Tenancy model + SSO + RBAC scaffold | Platform | be,platform,foundation | 5 | PO
Story | FE: Login screen + SSO flow | Login screen (email capture), redirect to IdP, handle callback, error states. | P0 | DEV-FE-1 | PRX-E2 | Sprint 4 — P2 Foundations · Tenancy model + SSO + RBAC scaffold | Platform | fe,platform,foundation | 5 | PO
Story | FE: Tenant-aware routing + URL scheme | Tenant in subdomain or path prefix. Route guards. Redirect to tenant picker if multi-tenant user. | P0 | DEV-FE-1 | PRX-E2 | Sprint 4 — P2 Foundations · Tenancy model + SSO + RBAC scaffold | Platform | fe,platform,foundation | 3 | PO
Story | FE: Session management + auto-refresh + idle logout | Auto-refresh before expiry. Idle-timeout logout. Warning modal before logout. | P0 | DEV-FE-2 | PRX-E2 | Sprint 4 — P2 Foundations · Tenancy model + SSO + RBAC scaffold | Platform | fe,platform,foundation | 3 | PO
Story | QA: Auth + tenancy + RBAC test suite | E2E: login/logout/refresh. Cross-tenant access rejected. Permission gates verified. | P0 | QA-1 | PRX-E2 | Sprint 4 — P2 Foundations · Tenancy model + SSO + RBAC scaffold | Platform | qa,platform,foundation | 5 | PO
Story | BE: Audit log data model + write-path | audit_events table. Middleware hooks on every mutating endpoint. Actor, action, target, diff. | P1 | DEV-BE-1 | PRX-E2 | Sprint 5 — P2 Foundations · Audit log + platform shell + nav | Platform | be,platform | 5 | PO
Story | BE: Audit log query API (filters + pagination) | GET /audit with filters: date-range, actor, action, target-type. Paginated. | P1 | DEV-BE-1 | PRX-E2 | Sprint 5 — P2 Foundations · Audit log + platform shell + nav | Platform | be,platform | 3 | PO
Story | BE: Platform config endpoints (branding, locale) | Per-tenant config: logo URL, primary color, locale, timezone. Cached. | P1 | DEV-BE-2 | PRX-E2 | Sprint 5 — P2 Foundations · Audit log + platform shell + nav | Platform | be,platform | 3 | PO
Story | FE: App shell (header + content + footer) | Responsive app shell with skip-to-content, notification slot, user menu slot. | P0 | DEV-FE-1 | PRX-E2 | Sprint 5 — P2 Foundations · Audit log + platform shell + nav | Platform | fe,platform,design | 5 | PO
Story | FE: Collapsible sidebar with module navigation | Sidebar with module icons, active state, collapsible. Keyboard nav. Remember preference. | P0 | DEV-FE-2 | PRX-E2 | Sprint 5 — P2 Foundations · Audit log + platform shell + nav | Platform | fe,platform,design | 8 | PO
Story | FE: Brand tokens wired into runtime theme | CSS vars from @praxion/tokens applied at root. Per-tenant color override supported. | P1 | DEV-FE-1 | PRX-E2 | Sprint 5 — P2 Foundations · Audit log + platform shell + nav | Platform | fe,platform,design | 5 | PO
Story | FE: User menu + profile dropdown + logout | Dropdown: profile link, settings, switch tenant, sign out. | P1 | DEV-FE-2 | PRX-E2 | Sprint 5 — P2 Foundations · Audit log + platform shell + nav | Platform | fe,platform | 3 | PO
Story | FE: Error boundaries + empty states + loading shells | Shared error boundary, 404/500 pages, skeleton loaders, empty-state component. | P1 | DEV-FE-1 | PRX-E2 | Sprint 5 — P2 Foundations · Audit log + platform shell + nav | Platform | fe,platform | 3 | PO
Story | QA: Audit log + shell e2e + accessibility pass | E2E: audit events captured on CRUD. A11y: keyboard-only nav through shell. Screen-reader smoke. | P1 | QA-1 | PRX-E2 | Sprint 5 — P2 Foundations · Audit log + platform shell + nav | Platform | qa,platform,a11y | 5 | PO
Story | DEVOPS: Staging environment hardening | TLS, rate limits, WAF rules, backup job verified, log retention config. | P1 | DEV-BE-2 | PRX-E2 | Sprint 5 — P2 Foundations · Audit log + platform shell + nav | Platform | devops,platform | 3 | PO
Story | BE: employees table + migrations + seed | Full schema per data-model ADR. Soft-delete. Timestamps. Seed 50 anonymized employees. | P0 | DEV-BE-1 | PRX-E3 | Sprint 6 — P3 Core Build · Employee records CRUD + search + data mo | M1-Core-HRIS | be,foundation | 5 | PO
Story | BE: GET /employees (list + filter + paginate + sort) | List with query params: q, status, org_unit, sort, page. p95 < 200ms on seed. | P0 | DEV-BE-1 | PRX-E3 | Sprint 6 — P3 Core Build · Employee records CRUD + search + data mo | M1-Core-HRIS | be,foundation | 5 | PO
Story | BE: GET /employees/:id (full detail) | Full record with nested addresses, emergency contacts, current position. | P0 | DEV-BE-1 | PRX-E3 | Sprint 6 — P3 Core Build · Employee records CRUD + search + data mo | M1-Core-HRIS | be,foundation | 3 | PO
Story | BE: POST /employees (create + validation) | Create with full payload validation, uniqueness checks, audit event emitted. | P0 | DEV-BE-2 | PRX-E3 | Sprint 6 — P3 Core Build · Employee records CRUD + search + data mo | M1-Core-HRIS | be,foundation | 5 | PO
Story | BE: PUT /employees/:id (update + partial) | Full + PATCH semantics. Optimistic concurrency via updated_at. Audit diff emitted. | P0 | DEV-BE-2 | PRX-E3 | Sprint 6 — P3 Core Build · Employee records CRUD + search + data mo | M1-Core-HRIS | be,foundation | 3 | PO
Story | BE: DELETE /employees/:id (soft-delete + restore) | Soft-delete toggles deleted_at. Restore endpoint. Cascade considerations documented. | P1 | DEV-BE-2 | PRX-E3 | Sprint 6 — P3 Core Build · Employee records CRUD + search + data mo | M1-Core-HRIS | be,foundation | 3 | PO
Story | BE: Employee search (full-text) | Postgres tsvector on name+email+employee_id. Fallback to ILIKE for filters. | P1 | DEV-BE-2 | PRX-E3 | Sprint 6 — P3 Core Build · Employee records CRUD + search + data mo | M1-Core-HRIS | be,foundation | 5 | PO
Story | FE: Employees list page (table + filters + search) | Implements design. Server-side pagination, filter chips, keyword search, row click → detail. | P0 | DEV-FE-1 | PRX-E3 | Sprint 6 — P3 Core Build · Employee records CRUD + search + data mo | M1-Core-HRIS | fe,foundation | 8 | PO
Story | FE: Employee detail page (tabs: profile, employment, docs) | Tabs layout. Profile tab shows core info. Empty tabs for employment/docs (populated later). | P0 | DEV-FE-1 | PRX-E3 | Sprint 6 — P3 Core Build · Employee records CRUD + search + data mo | M1-Core-HRIS | fe,foundation | 5 | PO
Story | FE: Employee create form (multi-step wizard) | Steps: identity → contact → employment → review. Validation per step. Save-and-exit. | P0 | DEV-FE-2 | PRX-E3 | Sprint 6 — P3 Core Build · Employee records CRUD + search + data mo | M1-Core-HRIS | fe,foundation | 8 | PO
Story | FE: Employee edit form + inline-edit where appropriate | Edit form mirrors create. Inline-edit for name + job title on detail page. | P0 | DEV-FE-2 | PRX-E3 | Sprint 6 — P3 Core Build · Employee records CRUD + search + data mo | M1-Core-HRIS | fe,foundation | 5 | PO
Story | FE: Employee profile header component | Avatar + name + job title + status badge. Reused across pages. | P1 | DEV-FE-2 | PRX-E3 | Sprint 6 — P3 Core Build · Employee records CRUD + search + data mo | M1-Core-HRIS | fe,foundation | 3 | PO
Story | QA: Employee CRUD test cases + automation | Test plan: ~40 cases. Automate ~25 (smoke + regression). Cross-tenant isolation verified. | P0 | QA-1 | PRX-E3 | Sprint 6 — P3 Core Build · Employee records CRUD + search + data mo | M1-Core-HRIS | qa,foundation | 5 | PO
Story | QA: Employee search + filter test cases | Test plan: ~15 cases. Edge: unicode names, very long strings, empty results. | P0 | QA-1 | PRX-E3 | Sprint 6 — P3 Core Build · Employee records CRUD + search + data mo | M1-Core-HRIS | qa,foundation | 3 | PO
Story | BE: org_units table + migrations + tree queries | Nested set or adjacency + path column. Queries: ancestors, descendants, siblings. | P0 | DEV-BE-1 | PRX-E3 | Sprint 7 — P3 Core Build · Org structure + positions + assignment | M1-Core-HRIS | be,foundation | 5 | PO
Story | BE: Org units CRUD API | Create + move + rename + deactivate. Prevent cycles. Audit emitted. | P0 | DEV-BE-1 | PRX-E3 | Sprint 7 — P3 Core Build · Org structure + positions + assignment | M1-Core-HRIS | be,foundation | 5 | PO
Story | BE: Org tree query endpoint (full + subtree) | GET /org/tree, GET /org/tree/:unit_id. Returns JSON tree with counts. | P0 | DEV-BE-1 | PRX-E3 | Sprint 7 — P3 Core Build · Org structure + positions + assignment | M1-Core-HRIS | be,foundation | 5 | PO
Story | BE: positions table + CRUD API | Create position, link to org_unit, track headcount approved vs filled. | P0 | DEV-BE-2 | PRX-E3 | Sprint 7 — P3 Core Build · Org structure + positions + assignment | M1-Core-HRIS | be,foundation | 5 | PO
Story | BE: Position assignment API | Assign employee to position (with start/end dates). Historical assignments preserved. | P0 | DEV-BE-2 | PRX-E3 | Sprint 7 — P3 Core Build · Org structure + positions + assignment | M1-Core-HRIS | be,foundation | 5 | PO
Story | BE: Reporting-line query endpoint | Given an employee, return up-chain and down-chain. Used by approvals later. | P1 | DEV-BE-2 | PRX-E3 | Sprint 7 — P3 Core Build · Org structure + positions + assignment | M1-Core-HRIS | be,foundation | 3 | PO
Story | FE: Org chart visualization (interactive) | React-flow or d3. Pan/zoom, click-to-focus, expand/collapse branches. | P0 | DEV-FE-1 | PRX-E3 | Sprint 7 — P3 Core Build · Org structure + positions + assignment | M1-Core-HRIS | fe,foundation | 8 | PO
Story | FE: Org unit create/edit form + move dialog | Forms for create/rename. Drag-drop or move-dialog to relocate within tree. | P0 | DEV-FE-1 | PRX-E3 | Sprint 7 — P3 Core Build · Org structure + positions + assignment | M1-Core-HRIS | fe,foundation | 5 | PO
Story | FE: Positions list + detail pages | List filtered by org unit. Detail shows current holder + history. | P0 | DEV-FE-2 | PRX-E3 | Sprint 7 — P3 Core Build · Org structure + positions + assignment | M1-Core-HRIS | fe,foundation | 5 | PO
Story | FE: Position assignment UI (assign / unassign) | Modal with employee picker, date picker, confirm. Historical list below. | P0 | DEV-FE-2 | PRX-E3 | Sprint 7 — P3 Core Build · Org structure + positions + assignment | M1-Core-HRIS | fe,foundation | 5 | PO
Story | FE: Org unit picker component (shared) | Tree-select component for forms. Reused in employee create/edit + other modules later. | P1 | DEV-FE-2 | PRX-E3 | Sprint 7 — P3 Core Build · Org structure + positions + assignment | Platform | fe,platform | 5 | PO
Story | QA: Org structure + positions test cases | Cycle prevention, move-to-descendant blocked, historical assignments preserved. | P0 | QA-1 | PRX-E3 | Sprint 7 — P3 Core Build · Org structure + positions + assignment | M1-Core-HRIS | qa,foundation | 5 | PO
Story | BE: contracts + contract_versions tables + migrations | Versioned contracts. Types: permanent, fixed-term, probation, consultancy. Enums in lookup. | P0 | DEV-BE-1 | PRX-E3 | Sprint 8 — P3 Core Build · Contracts + documents vault + signed URL | M1-Core-HRIS | be,foundation | 5 | PO
Story | BE: Contracts CRUD API | Create new contract version. List per employee. Current-contract query. | P0 | DEV-BE-1 | PRX-E3 | Sprint 8 — P3 Core Build · Contracts + documents vault + signed URL | M1-Core-HRIS | be,foundation | 5 | PO
Story | BE: Contract lifecycle state machine | States: draft → active → renewed → terminated. Valid transitions enforced. | P0 | DEV-BE-1 | PRX-E3 | Sprint 8 — P3 Core Build · Contracts + documents vault + signed URL | M1-Core-HRIS | be,foundation | 5 | PO
Story | BE: documents + document_acl tables + S3 bucket | Per-tenant bucket or per-tenant prefix. ACL table for fine-grained access. | P0 | DEV-BE-2 | PRX-E3 | Sprint 8 — P3 Core Build · Contracts + documents vault + signed URL | M1-Core-HRIS | be,foundation | 5 | PO
Story | BE: Document upload (signed-URL + virus-scan) | Client gets signed URL, uploads direct to S3. Lambda/worker scans. Notify on clean. | P0 | DEV-BE-2 | PRX-E3 | Sprint 8 — P3 Core Build · Contracts + documents vault + signed URL | M1-Core-HRIS | be,foundation | 5 | PO
Story | BE: Document download/metadata endpoint | Signed URL on demand. Metadata (uploader, size, mime, tags) cached. | P1 | DEV-BE-2 | PRX-E3 | Sprint 8 — P3 Core Build · Contracts + documents vault + signed URL | M1-Core-HRIS | be,foundation | 3 | PO
Story | FE: Contracts list + detail pages | Filter by employee, type, status. Detail shows current version + history. | P0 | DEV-FE-1 | PRX-E3 | Sprint 8 — P3 Core Build · Contracts + documents vault + signed URL | M1-Core-HRIS | fe,foundation | 5 | PO
Story | FE: Contract create/edit form | Form with dynamic fields per contract type. Attach document at creation. | P0 | DEV-FE-1 | PRX-E3 | Sprint 8 — P3 Core Build · Contracts + documents vault + signed URL | M1-Core-HRIS | fe,foundation | 5 | PO
Story | FE: Contract lifecycle actions (renew / terminate / sign) | Action buttons with confirm modals. Terminate requires reason + date. | P0 | DEV-FE-1 | PRX-E3 | Sprint 8 — P3 Core Build · Contracts + documents vault + signed URL | M1-Core-HRIS | fe,foundation | 5 | PO
Story | FE: Documents vault page (per employee) | List of documents with tags, filters, bulk download. | P1 | DEV-FE-2 | PRX-E3 | Sprint 8 — P3 Core Build · Contracts + documents vault + signed URL | M1-Core-HRIS | fe,foundation | 5 | PO
Story | FE: Document upload widget (drag-drop + progress) | Reusable widget. Supports multiple files, shows per-file progress, retries failed. | P0 | DEV-FE-2 | PRX-E3 | Sprint 8 — P3 Core Build · Contracts + documents vault + signed URL | Platform | fe,platform | 5 | PO
Story | FE: Document viewer (PDF preview modal) | PDF.js-based viewer in modal. Download + print actions. Fallback for other types. | P1 | DEV-FE-2 | PRX-E3 | Sprint 8 — P3 Core Build · Contracts + documents vault + signed URL | M1-Core-HRIS | fe,foundation | 5 | PO
Story | QA: Contracts + documents test cases | Lifecycle state machine verified. Upload/download + ACL tested. Virus-scan mock. | P0 | QA-1 | PRX-E3 | Sprint 8 — P3 Core Build · Contracts + documents vault + signed URL | M1-Core-HRIS | qa,foundation | 5 | PO
Story | BE: lifecycle_events table + API (hire/promote/transfer/terminate) | Event types: hire, promote, transfer, salary-change, terminate. Immutable after creation. | P0 | DEV-BE-1 | PRX-E3 | Sprint 9 — P3 Core Build · Lifecycle events + approvals engine + no | M1-Core-HRIS | be,foundation | 5 | PO
Story | BE: Approvals data model (workflows, steps, history) | approval_workflows, approval_workflow_steps (order + approver_role), approval_history. | P0 | DEV-BE-2 | PRX-E3 | Sprint 9 — P3 Core Build · Lifecycle events + approvals engine + no | M1-Core-HRIS | be,foundation | 5 | PO
Story | BE: Approval engine — state transitions | States: pending → approved/rejected. Multi-step with parallel or sequential. Timeouts. | P0 | DEV-BE-1 | PRX-E3 | Sprint 9 — P3 Core Build · Lifecycle events + approvals engine + no | M1-Core-HRIS | be,foundation | 8 | PO
Story | BE: Notifications service + email templates | Pluggable provider (SES/SMTP). Templates: approval-requested, approved, rejected, reminder. | P0 | DEV-BE-2 | PRX-E3 | Sprint 9 — P3 Core Build · Lifecycle events + approvals engine + no | Platform | be,platform | 5 | PO
Story | BE: Approval audit trail + SLA metrics | Full trail per approval. Track time-to-approve. SLA thresholds in config. | P1 | DEV-BE-2 | PRX-E3 | Sprint 9 — P3 Core Build · Lifecycle events + approvals engine + no | M1-Core-HRIS | be,foundation | 3 | PO
Story | FE: Lifecycle event timeline component | Vertical timeline on employee detail. Icons per event type. Click → event detail. | P0 | DEV-FE-1 | PRX-E3 | Sprint 9 — P3 Core Build · Lifecycle events + approvals engine + no | M1-Core-HRIS | fe,foundation | 5 | PO
Story | FE: Lifecycle event create wizard (promote/transfer) | Multi-step wizard. Pre-fills from current state. Triggers approval workflow. | P0 | DEV-FE-1 | PRX-E3 | Sprint 9 — P3 Core Build · Lifecycle events + approvals engine + no | M1-Core-HRIS | fe,foundation | 8 | PO
Story | FE: Approvals inbox page (pending + completed) | List pending approvals for current user. Filter by type + age. | P0 | DEV-FE-2 | PRX-E3 | Sprint 9 — P3 Core Build · Lifecycle events + approvals engine + no | M1-Core-HRIS | fe,foundation | 5 | PO
Story | FE: Approval detail page + approve/reject action | Shows payload diff. Approve/Reject with comment. Confirmation modal. | P0 | DEV-FE-2 | PRX-E3 | Sprint 9 — P3 Core Build · Lifecycle events + approvals engine + no | M1-Core-HRIS | fe,foundation | 5 | PO
Story | FE: Notifications UI (bell icon + dropdown + mark-read) | Header bell with unread count. Dropdown with recent. Link to full notifications page. | P1 | DEV-FE-2 | PRX-E3 | Sprint 9 — P3 Core Build · Lifecycle events + approvals engine + no | Platform | fe,platform | 3 | PO
Story | QA: Lifecycle events test cases | Hire/promote/transfer/terminate flows. Audit verification. Edge cases. | P0 | QA-1 | PRX-E3 | Sprint 9 — P3 Core Build · Lifecycle events + approvals engine + no | M1-Core-HRIS | qa,foundation | 5 | PO
Story | QA: Approvals test cases + SLA scenarios | Multi-step approvals. Rejection reroute. Timeout/reminder. SLA breach. | P0 | QA-1 | PRX-E3 | Sprint 9 — P3 Core Build · Lifecycle events + approvals engine + no | M1-Core-HRIS | qa,foundation | 4 | PO
Story | BE: Query performance tuning + indexes review | Slow-query log analysis. Add missing indexes. Materialized views where warranted. | P1 | DEV-BE-1 | PRX-E3 | Sprint 10 — P3→P4 · M1 polish + bulk import/export + M10 sca | Platform | be,platform,tech-debt | 5 | PO
Story | BE: API rate limiting + throttling per tenant | Token bucket per tenant + per user. Configurable limits. 429 with retry-after. | P1 | DEV-BE-1 | PRX-E3 | Sprint 10 — P3→P4 · M1 polish + bulk import/export + M10 sca | Platform | be,platform | 3 | PO
Story | BE: Bulk import API (employees CSV) | Upload CSV, validate per-row, stream report. Dry-run mode. Transactional or row-by-row. | P1 | DEV-BE-2 | PRX-E3 | Sprint 10 — P3→P4 · M1 polish + bulk import/export + M10 sca | M1-Core-HRIS | be,foundation | 5 | PO
Story | BE: Export API (employees, contracts, org) | CSV/XLSX export with field selection. Streamed for large sets. | P1 | DEV-BE-2 | PRX-E3 | Sprint 10 — P3→P4 · M1 polish + bulk import/export + M10 sca | M1-Core-HRIS | be,foundation | 3 | PO
Story | BE: M10 admin scaffolding (users, roles, permissions routes) | Scaffold only — no full CRUD yet. Prep for Sprint 11. | P1 | DEV-BE-2 | PRX-E3 | Sprint 10 — P3→P4 · M1 polish + bulk import/export + M10 sca | M10-Sys-Admin | be,foundation | 5 | PO
Story | FE: Bulk import wizard UI (upload → map → validate → commit) | Four-step wizard. Column mapping UI. Validation errors inline. Commit with progress. | P1 | DEV-FE-1 | PRX-E3 | Sprint 10 — P3→P4 · M1 polish + bulk import/export + M10 sca | M1-Core-HRIS | fe,foundation | 5 | PO
Story | FE: Export UI (field selector + format picker) | Modal with field checkboxes + format radio + trigger. Download when ready. | P1 | DEV-FE-1 | PRX-E3 | Sprint 10 — P3→P4 · M1 polish + bulk import/export + M10 sca | M1-Core-HRIS | fe,foundation | 5 | PO
Story | FE: Employee profile enhancements (avatar upload + photo crop) | Upload + crop + save. Fallback initials avatar. Consistent across the app. | P2 | DEV-FE-2 | PRX-E3 | Sprint 10 — P3→P4 · M1 polish + bulk import/export + M10 sca | M1-Core-HRIS | fe,foundation | 5 | PO
Story | FE: Advanced search + saved filters | Builder UI for complex filters. Save named views. Shareable URLs. | P2 | DEV-FE-2 | PRX-E3 | Sprint 10 — P3→P4 · M1 polish + bulk import/export + M10 sca | M1-Core-HRIS | fe,foundation | 5 | PO
Story | FE: Home dashboard widgets (stats + recent events) | Dashboard page with 4-6 widgets. Employee count, upcoming anniversaries, pending approvals. | P1 | DEV-FE-1 | PRX-E3 | Sprint 10 — P3→P4 · M1 polish + bulk import/export + M10 sca | M1-Core-HRIS | fe,foundation | 5 | PO
Story | FE: M10 admin shell scaffolding (routes + empty pages) | Wires M10 routes + nav entry. Empty pages ready for Sprint 11 fill. | P1 | DEV-FE-2 | PRX-E3 | Sprint 10 — P3→P4 · M1 polish + bulk import/export + M10 sca | M10-Sys-Admin | fe,foundation | 3 | PO
Story | QA: M1 full regression test suite + automation run | Automate regression. 2-hour CI run. Fail-fast gate to block merge. | P0 | QA-1 | PRX-E3 | Sprint 10 — P3→P4 · M1 polish + bulk import/export + M10 sca | M1-Core-HRIS | qa,foundation | 8 | PO
Story | QA: Performance test baseline (k6 scenarios) | Define SLOs: list < 200ms p95, detail < 100ms p95, create < 300ms p95. Baseline run. | P1 | QA-1 | PRX-E3 | Sprint 10 — P3→P4 · M1 polish + bulk import/export + M10 sca | Platform | qa,platform | 5 | PO
Story | DES: M1 visual QA pass + polish tickets | Hi-fi vs implementation diff. Log polish tickets. Accessibility contrast verified. | P1 | DES-1 | PRX-E3 | Sprint 10 — P3→P4 · M1 polish + bulk import/export + M10 sca | M1-Core-HRIS | design,foundation | 3 | PO
Story | BE: Users admin CRUD API (invite/activate/deactivate) | Admin can create users, invite by email, activate, deactivate, reset password. | P0 | DEV-BE-1 | PRX-E4 | Sprint 11 — P4 Adjacent · M10 users, roles, permissions admin | M10-Sys-Admin | be,foundation | 5 | PO
Story | BE: Roles CRUD API + default roles seed | Admin can create custom roles. Seed ships SysAdmin, HRAdmin, Manager, Employee. | P0 | DEV-BE-1 | PRX-E4 | Sprint 11 — P4 Adjacent · M10 users, roles, permissions admin | M10-Sys-Admin | be,foundation | 5 | PO
Story | BE: Permissions matrix API (permissions × roles) | GET/PUT matrix. Granular: module.resource.action. Cached heavily. | P0 | DEV-BE-1 | PRX-E4 | Sprint 11 — P4 Adjacent · M10 users, roles, permissions admin | M10-Sys-Admin | be,foundation | 5 | PO
Story | BE: User-role assignment API (multi-role) | Assign/revoke roles. Permission resolution = union of role permissions. | P0 | DEV-BE-2 | PRX-E4 | Sprint 11 — P4 Adjacent · M10 users, roles, permissions admin | M10-Sys-Admin | be,foundation | 3 | PO
Story | FE: Users admin list + detail pages | List with filters (status, role). Detail shows assigned roles + activity. | P0 | DEV-FE-1 | PRX-E4 | Sprint 11 — P4 Adjacent · M10 users, roles, permissions admin | M10-Sys-Admin | fe,foundation | 5 | PO
Story | FE: Role editor (permissions matrix UI) | Matrix UI: rows = permissions, columns = roles. Tri-state checkboxes. Search + group. | P0 | DEV-FE-1 | PRX-E4 | Sprint 11 — P4 Adjacent · M10 users, roles, permissions admin | M10-Sys-Admin | fe,foundation | 8 | PO
Story | FE: User create/edit form + invite flow | Form with email, name, role picker. Send invite. Resend invite action. | P0 | DEV-FE-2 | PRX-E4 | Sprint 11 — P4 Adjacent · M10 users, roles, permissions admin | M10-Sys-Admin | fe,foundation | 5 | PO
Story | QA: Users/Roles/Permissions test cases | Permission resolution. Custom-role creation. Multi-role user. Deactivated-user access. | P0 | QA-1 | PRX-E4 | Sprint 11 — P4 Adjacent · M10 users, roles, permissions admin | M10-Sys-Admin | qa,foundation | 5 | PO
Story | QA: Permission enforcement across M1 endpoints | Validate that every M1 endpoint honours the permission matrix. ~50 check cases. | P0 | QA-1 | PRX-E4 | Sprint 11 — P4 Adjacent · M10 users, roles, permissions admin | M1-Core-HRIS | qa,foundation | 4 | PO
Story | BE: Tenant config endpoints (branding, locale, policies) | Per-tenant settings: logo URL, colors, locale, timezone, password policy, session timeout. | P1 | DEV-BE-1 | PRX-E4 | Sprint 12 — P4 Adjacent · M10 tenant config + org chart admin + ho | M10-Sys-Admin | be,foundation | 5 | PO
Story | BE: Org chart bulk-edit API (reorder + bulk-move) | Bulk operations with dry-run. Validation for cycles + permission. | P1 | DEV-BE-1 | PRX-E4 | Sprint 12 — P4 Adjacent · M10 tenant config + org chart admin + ho | M10-Sys-Admin | be,foundation | 5 | PO
Story | BE: Holiday calendar management API | Per-tenant + per-country calendars. CRUD holidays. Recurrence rules. | P1 | DEV-BE-2 | PRX-E4 | Sprint 12 — P4 Adjacent · M10 tenant config + org chart admin + ho | M10-Sys-Admin | be,foundation | 3 | PO
Story | BE: Notification template management API | Admin-editable templates per event type. Variables supported. Preview endpoint. | P1 | DEV-BE-2 | PRX-E4 | Sprint 12 — P4 Adjacent · M10 tenant config + org chart admin + ho | M10-Sys-Admin | be,foundation | 3 | PO
Story | FE: Tenant settings page (branding + locale + policies) | Sectioned settings. Preview applied branding. Save triggers config reload. | P1 | DEV-FE-2 | PRX-E4 | Sprint 12 — P4 Adjacent · M10 tenant config + org chart admin + ho | M10-Sys-Admin | fe,foundation | 8 | PO
Story | FE: Org chart admin UI (bulk edit + dry-run preview) | Admin-only view of org chart with drag-to-reorder + bulk-select. Preview before commit. | P1 | DEV-FE-1 | PRX-E4 | Sprint 12 — P4 Adjacent · M10 tenant config + org chart admin + ho | M10-Sys-Admin | fe,foundation | 8 | PO
Story | FE: Holiday calendar admin UI | Calendar view with add/edit/delete. Recurrence rule builder. | P1 | DEV-FE-1 | PRX-E4 | Sprint 12 — P4 Adjacent · M10 tenant config + org chart admin + ho | M10-Sys-Admin | fe,foundation | 5 | PO
Story | FE: Notification template editor (with variable picker) | Rich-text editor with variable tokens. Preview pane. | P1 | DEV-FE-2 | PRX-E4 | Sprint 12 — P4 Adjacent · M10 tenant config + org chart admin + ho | M10-Sys-Admin | fe,foundation | 5 | PO
Story | QA: Tenant config + org admin test cases | Branding roundtrip. Org bulk operations. Holiday calendar. Template preview. | P1 | QA-1 | PRX-E4 | Sprint 12 — P4 Adjacent · M10 tenant config + org chart admin + ho | M10-Sys-Admin | qa,foundation | 3 | PO
Story | BE: Audit log search + filter + full-text API | Advanced search: actor/action/target/date/keyword. Paginated. Export-safe. | P1 | DEV-BE-1 | PRX-E4 | Sprint 13 — P4 Adjacent · M10 audit dashboard + integrations + web | M10-Sys-Admin | be,foundation | 5 | PO
Story | BE: Audit log export API (CSV streaming) | Stream CSV for large ranges. Progress endpoint. Complete-notification email. | P1 | DEV-BE-1 | PRX-E4 | Sprint 13 — P4 Adjacent · M10 audit dashboard + integrations + web | M10-Sys-Admin | be,foundation | 3 | PO
Story | BE: Integration registry API (configured integrations) | List/enable/disable integrations. Per-integration config JSON stored encrypted. | P1 | DEV-BE-2 | PRX-E4 | Sprint 13 — P4 Adjacent · M10 audit dashboard + integrations + web | M10-Sys-Admin | be,foundation | 5 | PO
Story | BE: Webhook configuration API + dispatcher | Create webhooks for events. Signed payloads. Retry with backoff. Dead-letter queue. | P1 | DEV-BE-2 | PRX-E4 | Sprint 13 — P4 Adjacent · M10 audit dashboard + integrations + web | M10-Sys-Admin | be,foundation | 3 | PO
Story | BE: API token management (create/revoke/rotate) | Scoped tokens. Rotation + revoke. Tokens audit-logged. | P1 | DEV-BE-1 | PRX-E4 | Sprint 13 — P4 Adjacent · M10 audit dashboard + integrations + web | M10-Sys-Admin | be,foundation | 5 | PO
Story | FE: Audit log dashboard (filters + timeline + drill-down) | Filter panel + timeline + detail pane. Export action. Saved views. | P1 | DEV-FE-1 | PRX-E4 | Sprint 13 — P4 Adjacent · M10 audit dashboard + integrations + web | M10-Sys-Admin | fe,foundation | 8 | PO
Story | FE: Integrations config page | List of available integrations, per-integration connect flow, status chip. | P1 | DEV-FE-1 | PRX-E4 | Sprint 13 — P4 Adjacent · M10 audit dashboard + integrations + web | M10-Sys-Admin | fe,foundation | 5 | PO
Story | FE: Webhook configuration UI | Create webhook: event types, URL, signing key. Test-fire action. Delivery log. | P1 | DEV-FE-2 | PRX-E4 | Sprint 13 — P4 Adjacent · M10 audit dashboard + integrations + web | M10-Sys-Admin | fe,foundation | 5 | PO
Story | FE: API token management UI | List tokens with scope + last-used. Create modal shows token once. Revoke action. | P1 | DEV-FE-2 | PRX-E4 | Sprint 13 — P4 Adjacent · M10 audit dashboard + integrations + web | M10-Sys-Admin | fe,foundation | 3 | PO
Story | QA: Audit + integrations + webhooks test cases | Audit export integrity. Webhook delivery + retry. Token scope enforcement. | P1 | QA-1 | PRX-E4 | Sprint 13 — P4 Adjacent · M10 audit dashboard + integrations + web | M10-Sys-Admin | qa,foundation | 3 | PO
Story | BE: Security review fixes — round 1 (OWASP top 10) | Address findings from internal review. SQL-i, XSS, auth, crypto. | P0 | DEV-BE-1 | PRX-E4 | Sprint 14 — P4→P5 · Feature-freeze — a11y + bundle + perf op | Platform | be,platform,security | 8 | PO
Story | BE: Performance tuning — hot endpoints + caching | Cache layer for reads. Index tuning. p95 SLOs verified post-fix. | P1 | DEV-BE-2 | PRX-E4 | Sprint 14 — P4→P5 · Feature-freeze — a11y + bundle + perf op | Platform | be,platform,tech-debt | 8 | PO
Story | FE: Bundle size optimization + tree-shaking audit | Analyse bundle. Remove unused deps. Dynamic import heavy routes. | P1 | DEV-FE-1 | PRX-E4 | Sprint 14 — P4→P5 · Feature-freeze — a11y + bundle + perf op | Platform | fe,platform,tech-debt | 5 | PO
Story | FE: Lazy-loading + route-level code-splitting | Split M1 and M10 into separate bundles. Prefetch on idle. | P1 | DEV-FE-1 | PRX-E4 | Sprint 14 — P4→P5 · Feature-freeze — a11y + bundle + perf op | Platform | fe,platform | 5 | PO
Story | FE: Accessibility (a11y) pass — M1 | WCAG 2.1 AA: keyboard nav, screen reader, contrast. Log tickets. | P0 | DEV-FE-2 | PRX-E4 | Sprint 14 — P4→P5 · Feature-freeze — a11y + bundle + perf op | M1-Core-HRIS | fe,foundation,a11y | 5 | PO
Story | FE: Accessibility (a11y) pass — M10 | Same scope for M10. | P0 | DEV-FE-2 | PRX-E4 | Sprint 14 — P4→P5 · Feature-freeze — a11y + bundle + perf op | M10-Sys-Admin | fe,foundation,a11y | 5 | PO
Story | QA: Full regression run round 1 + defect report | Full automated + manual regression. Burn-down plan for any reds. | P0 | QA-1 | PRX-E4 | Sprint 14 — P4→P5 · Feature-freeze — a11y + bundle + perf op | Platform | qa,platform | 8 | PO
Story | DEVOPS: Staging perf baseline + SLO report | Run perf suite in staging. Compare to SLOs. Gate decision for P5. | P1 | DEV-BE-2 | PRX-E4 | Sprint 14 — P4→P5 · Feature-freeze — a11y + bundle + perf op | Platform | devops,platform | 3 | PO
Story | BE: Load testing scenarios + k6 scripts | Design: steady load, spike, soak, stress. Scripts per scenario. Baseline captured. | P0 | DEV-BE-1 | PRX-E5 | Sprint 15 — P5 Harden · Load test + security scan fixes + DR dri | Platform | be,platform,qa | 5 | PO
Story | BE: Load-test fixes + scaling policy tuning | Address bottlenecks from load run. HPA tuning. Connection-pool sizing. | P0 | DEV-BE-2 | PRX-E5 | Sprint 15 — P5 Harden · Load test + security scan fixes + DR dri | Platform | be,platform | 5 | PO
Story | BE: Security scan fixes (OWASP + CVE backlog) | All critical + high findings resolved. Report archived. | P0 | DEV-BE-1 | PRX-E5 | Sprint 15 — P5 Harden · Load test + security scan fixes + DR dri | Platform | be,platform,security | 8 | PO
Story | BE: Secrets rotation + vault setup | All secrets in vault. Rotation policy documented. No hardcoded secrets. | P0 | DEV-BE-2 | PRX-E5 | Sprint 15 — P5 Harden · Load test + security scan fixes + DR dri | Platform | be,platform,security | 5 | PO
Story | BE: DR backup + restore testing | Full restore drill from backup into clean env. Documented RTO/RPO. | P0 | DEV-BE-1 | PRX-E5 | Sprint 15 — P5 Harden · Load test + security scan fixes + DR dri | Platform | be,platform,devops | 5 | PO
Story | FE: XSS/CSRF hardening audit | Audit render paths. Content-Security-Policy + SameSite cookies + CSRF tokens. | P0 | DEV-FE-1 | PRX-E5 | Sprint 15 — P5 Harden · Load test + security scan fixes + DR dri | Platform | fe,platform,security | 5 | PO
Story | FE: CSP headers + SRI for external scripts | CSP tuned to production needs. SRI for any CDN-loaded scripts. | P1 | DEV-FE-2 | PRX-E5 | Sprint 15 — P5 Harden · Load test + security scan fixes + DR dri | Platform | fe,platform,security | 3 | PO
Story | DEVOPS: DR runbook + full DR drill | Runbook published. Full drill executed. Lessons captured. | P0 | DEV-BE-2 | PRX-E5 | Sprint 15 — P5 Harden · Load test + security scan fixes + DR dri | Platform | devops,platform | 5 | PO
Story | QA: Load-test results + signoff report | Report to TL+PO with SLO compliance. Sign-off gate. | P0 | QA-1 | PRX-E5 | Sprint 15 — P5 Harden · Load test + security scan fixes + DR dri | Platform | qa,platform | 3 | PO
Story | BE: Pen-test fixes — critical severity | Address all critical findings from pen-test report. Re-test gate. | P0 | DEV-BE-1 | PRX-E5 | Sprint 16 — P5 Harden · Pen-test fixes + data migration dry-runs | Platform | be,platform,security | 8 | PO
Story | BE: Pen-test fixes — major severity | Address all major findings. Re-test. | P0 | DEV-BE-2 | PRX-E5 | Sprint 16 — P5 Harden · Pen-test fixes + data migration dry-runs | Platform | be,platform,security | 5 | PO
Story | BE: Pen-test fixes — minor + hardening | Address minor findings + defence-in-depth extras. | P1 | DEV-BE-1 | PRX-E5 | Sprint 16 — P5 Harden · Pen-test fixes + data migration dry-runs | Platform | be,platform,security | 3 | PO
Story | BE: Data migration script — employees | Script ingest from legacy/source system. Dry-run mode. Validation report. | P0 | DEV-BE-2 | PRX-E5 | Sprint 16 — P5 Harden · Pen-test fixes + data migration dry-runs | M1-Core-HRIS | be,foundation,migration | 5 | PO
Story | BE: Data migration script — org structure + positions | Same as above for org/positions. Reference mapping preserved. | P0 | DEV-BE-2 | PRX-E5 | Sprint 16 — P5 Harden · Pen-test fixes + data migration dry-runs | M1-Core-HRIS | be,foundation,migration | 3 | PO
Story | BE: Data migration script — contracts + documents | Same as above. Document upload batching. ACL preserved. | P0 | DEV-BE-1 | PRX-E5 | Sprint 16 — P5 Harden · Pen-test fixes + data migration dry-runs | M1-Core-HRIS | be,foundation,migration | 3 | PO
Story | BE: Data migration dry-run 1 (staging) | Full dry-run in staging with anonymized prod extract. Defect list. | P0 | DEV-BE-2 | PRX-E5 | Sprint 16 — P5 Harden · Pen-test fixes + data migration dry-runs | Platform | be,platform,migration | 5 | PO
Story | BE: Data migration dry-run 2 (staging, post-fix) | Second dry-run after dry-run-1 fixes. Target: zero-defect. | P0 | DEV-BE-1 | PRX-E5 | Sprint 16 — P5 Harden · Pen-test fixes + data migration dry-runs | Platform | be,platform,migration | 5 | PO
Story | QA: Pen-test fix verification | Verify every pen-test finding is closed. Re-test in dry-run env. | P0 | QA-1 | PRX-E5 | Sprint 16 — P5 Harden · Pen-test fixes + data migration dry-runs | Platform | qa,platform,security | 5 | PO
Story | QA: Migration dry-run verification + checksums | Row counts, checksums, referential integrity. Report to PO. | P0 | QA-1 | PRX-E5 | Sprint 16 — P5 Harden · Pen-test fixes + data migration dry-runs | Platform | qa,platform,migration | 3 | PO
Story | PO: UAT scenarios drafted (happy + edge paths) | ~30 scenarios covering key workflows. Signed off with HR Ops. | P0 | PO | PRX-E5 | Sprint 17 — P5→P6 · Holiday-reduced · UAT prep — scenarios, | Platform | po,qa | 5 | PO
Story | PO: UAT test data prepared (anonymized + seeded) | Seeded accounts + test users + happy data. Credentials pack for UAT users. | P0 | PO | PRX-E5 | Sprint 17 — P5→P6 · Holiday-reduced · UAT prep — scenarios, | Platform | po,qa | 3 | PO
Story | PO: UAT stakeholder onboarding session | 1-hour session walking UAT users through scope + tools + defect reporting. | P0 | PO | PRX-E5 | Sprint 17 — P5→P6 · Holiday-reduced · UAT prep — scenarios, | Platform | po | 3 | PO
Story | QA: UAT test plan (scoring rubric + defect flow) | Plan: scope, entry/exit criteria, defect flow, reporting cadence. | P0 | QA-1 | PRX-E5 | Sprint 17 — P5→P6 · Holiday-reduced · UAT prep — scenarios, | Platform | qa,platform | 5 | PO
Story | QA: UAT environment smoke test + seeding | UAT env ready. All scenarios run smoke once. Fixtures loaded. | P0 | QA-1 | PRX-E5 | Sprint 17 — P5→P6 · Holiday-reduced · UAT prep — scenarios, | Platform | qa,platform | 3 | PO
Story | BE: Hotfix pipeline + feature-flag framework | Separate hotfix branch + pipeline. Feature flags for risky toggles. | P1 | DEV-BE-1 | PRX-E5 | Sprint 17 — P5→P6 · Holiday-reduced · UAT prep — scenarios, | Platform | be,platform,devops | 5 | PO
Story | FE: In-app help + user guide content (embedded) | Contextual help tooltips + link to guide page. Content drafted with PO. | P1 | DEV-FE-1 | PRX-E5 | Sprint 17 — P5→P6 · Holiday-reduced · UAT prep — scenarios, | Platform | fe,platform | 3 | PO
Story | DEVOPS: Production environment hardening | TLS + WAF + DDoS + WAF rules. Backup + monitoring + on-call paging. RTO/RPO verified. | P0 | DEV-BE-2 | PRX-E5 | Sprint 17 — P5→P6 · Holiday-reduced · UAT prep — scenarios, | Platform | devops,platform,security | 3 | PO
Story | QA: UAT round 1 — execution + defect intake | Run all scenarios with UAT users. Log defects daily. Triage twice-daily. | P0 | QA-1 | PRX-E6 | Sprint 18 — P6 UAT · UAT round 1 + defect burndown | Platform | qa,platform,uat | 5 | PO
Story | QA: UAT round 1 — defect triage + assignment | Triage with TL+PO. Severity + priority. Assign to sprint. | P0 | QA-1 | PRX-E6 | Sprint 18 — P6 UAT · UAT round 1 + defect burndown | Platform | qa,platform,uat | 5 | PO
Story | BE: UAT round 1 — fixes backlog burndown | Absorb top-priority defects into sprint. Fix + deploy hotfix pipeline. | P0 | DEV-BE-1 | PRX-E6 | Sprint 18 — P6 UAT · UAT round 1 + defect burndown | Platform | be,platform,uat | 8 | PO
Story | FE: UAT round 1 — fixes backlog burndown | Same for FE defects. | P0 | DEV-FE-1 | PRX-E6 | Sprint 18 — P6 UAT · UAT round 1 + defect burndown | Platform | fe,platform,uat | 8 | PO
Story | PO: Stakeholder feedback synthesis + go/no-go R1 | Synthesize qualitative feedback. Decision: proceed to R2 or pause. | P0 | PO | PRX-E6 | Sprint 18 — P6 UAT · UAT round 1 + defect burndown | Platform | po,uat | 3 | PO
Story | DES: UX tweaks from UAT — high-impact only | Urgent UX tweaks identified from R1. Capped at low-effort changes. | P1 | DES-1 | PRX-E6 | Sprint 18 — P6 UAT · UAT round 1 + defect burndown | Platform | design,uat | 1 | PO
Story | QA: UAT round 2 — execution + regression | Re-run scenarios post-R1 fixes. Add new scenarios identified in R1. | P0 | QA-1 | PRX-E6 | Sprint 19 — P6 UAT · UAT round 2 + training content | Platform | qa,platform,uat | 5 | PO
Story | BE: UAT round 2 — fixes | Absorb R2 defect backlog. | P0 | DEV-BE-2 | PRX-E6 | Sprint 19 — P6 UAT · UAT round 2 + training content | Platform | be,platform,uat | 5 | PO
Story | FE: UAT round 2 — fixes | Same for FE. | P0 | DEV-FE-2 | PRX-E6 | Sprint 19 — P6 UAT · UAT round 2 + training content | Platform | fe,platform,uat | 5 | PO
Story | PO: Training content — admin users (M10) | Admin training deck + video walkthroughs. Reviewed by Sabry + HR Ops. | P1 | PO | PRX-E6 | Sprint 19 — P6 UAT · UAT round 2 + training content | Platform | po,training | 5 | PO
Story | PO: Training content — end users (M1) | End-user quick-start + deep-dive content. Printable + web format. | P1 | PO | PRX-E6 | Sprint 19 — P6 UAT · UAT round 2 + training content | Platform | po,training | 5 | PO
Story | DES: Training visuals (screenshots + diagrams) | Brand-compliant visuals for training materials. | P1 | DES-1 | PRX-E6 | Sprint 19 — P6 UAT · UAT round 2 + training content | Platform | design,training | 3 | PO
Story | PO: Training pilot session (dry run) | Dry-run training with 5 pilot users. Feedback → content tweaks. | P1 | PO | PRX-E6 | Sprint 19 — P6 UAT · UAT round 2 + training content | Platform | po,training | 2 | PO
Story | QA: UAT round 3 — final regression + acceptance | Final regression. UAT sign-off gate. Residual-defect list. | P0 | QA-1 | PRX-E6 | Sprint 20 — P6 UAT · UAT round 3 + cutover rehearsal | Platform | qa,platform,uat | 5 | PO
Story | BE: UAT round 3 — final fixes | Only P0/P1 defects in scope. Everything else moves to backlog. | P0 | DEV-BE-1 | PRX-E6 | Sprint 20 — P6 UAT · UAT round 3 + cutover rehearsal | Platform | be,platform,uat | 5 | PO
Story | FE: UAT round 3 — final fixes | Same for FE. | P0 | DEV-FE-1 | PRX-E6 | Sprint 20 — P6 UAT · UAT round 3 + cutover rehearsal | Platform | fe,platform,uat | 5 | PO
Story | DEVOPS: Cutover rehearsal 1 (staging-as-prod) | Full rehearsal in staging mimicking prod scale. Timed. Runbook refined. | P0 | DEV-BE-2 | PRX-E6 | Sprint 20 — P6 UAT · UAT round 3 + cutover rehearsal | Platform | devops,platform,cutover | 5 | PO
Story | DEVOPS: Cutover rehearsal 2 (full team) | Second rehearsal with full team participation. Final runbook + rollback plan. | P0 | DEV-BE-2 | PRX-E6 | Sprint 20 — P6 UAT · UAT round 3 + cutover rehearsal | Platform | devops,platform,cutover | 5 | PO
Story | QA: Final regression run + exit-criteria report | Automated regression green. Manual smoke complete. Exit-criteria report to PO. | P0 | QA-1 | PRX-E6 | Sprint 20 — P6 UAT · UAT round 3 + cutover rehearsal | Platform | qa,platform | 3 | PO
Story | PO: Go/no-go readiness review | Review with steerco. Go/no-go decision for 14-Mar go-live. | P0 | PO | PRX-E6 | Sprint 20 — P6 UAT · UAT round 3 + cutover rehearsal | Platform | po | 2 | PO
Story | BE: Last-mile fixes + production config freeze | Final P0 bugs. Production config reviewed + frozen. | P0 | DEV-BE-1 | PRX-E7 | Sprint 21 — P7 Cutover · Final fixes + go-live prep + rollback re | Platform | be,platform,cutover | 5 | PO
Story | FE: Last-mile fixes + production build verified | Final P0 UI bugs. Production build tested end-to-end. | P0 | DEV-FE-1 | PRX-E7 | Sprint 21 — P7 Cutover · Final fixes + go-live prep + rollback re | Platform | fe,platform,cutover | 5 | PO
Story | DEVOPS: Production deployment checklist | Step-by-step deploy checklist. All owners named. Comms plan attached. | P0 | DEV-BE-2 | PRX-E7 | Sprint 21 — P7 Cutover · Final fixes + go-live prep + rollback re | Platform | devops,platform,cutover | 3 | PO
Story | DEVOPS: Rollback plan + rehearsal | Document rollback to previous state. Rehearse rollback in staging. Timed. | P0 | DEV-BE-2 | PRX-E7 | Sprint 21 — P7 Cutover · Final fixes + go-live prep + rollback re | Platform | devops,platform,cutover | 5 | PO
Story | PO: Go-live comms plan (internal + external) | Internal announcement + customer-facing comms. Scheduled sends. | P1 | PO | PRX-E7 | Sprint 21 — P7 Cutover · Final fixes + go-live prep + rollback re | Platform | po,cutover | 3 | PO
Story | PO: Day-1 support war-room setup (rota + channels) | On-call rota, war-room channel, escalation matrix, status-page plan. | P0 | PO | PRX-E7 | Sprint 21 — P7 Cutover · Final fixes + go-live prep + rollback re | Platform | po,cutover | 2 | PO
Story | QA: Final smoke test suite (go/no-go gate) | Critical-path smoke suite. Run against prod post-deploy. | P0 | QA-1 | PRX-E7 | Sprint 21 — P7 Cutover · Final fixes + go-live prep + rollback re | Platform | qa,platform,cutover | 2 | PO
Story | DEVOPS: Production cutover — execute deployment | Execute checklist on 14-Mar. All-hands war-room. Real-time comms. | P0 | DEV-BE-2 | PRX-E7 | Sprint 22 — P7 Go-Live · GO-LIVE 14-Mar-2027 + Day-1 hypercare | Platform | devops,platform,cutover,go-live | 8 | PO
Story | DEVOPS: DNS + traffic cutover | DNS flip + traffic verified. Cache warmed. Watch dashboards. | P0 | DEV-BE-1 | PRX-E7 | Sprint 22 — P7 Go-Live · GO-LIVE 14-Mar-2027 + Day-1 hypercare | Platform | devops,platform,cutover,go-live | 3 | PO
Story | QA: Post-cutover smoke tests (prod) | Full smoke in prod. Any red = immediate escalation. | P0 | QA-1 | PRX-E7 | Sprint 22 — P7 Go-Live · GO-LIVE 14-Mar-2027 + Day-1 hypercare | Platform | qa,platform,cutover,go-live | 3 | PO
Story | BE: Day-1 hotfix support (on-call) | On-call rota. Respond to P0 within 15 min, P1 within 2 h. | P0 | DEV-BE-1 | PRX-E7 | Sprint 22 — P7 Go-Live · GO-LIVE 14-Mar-2027 + Day-1 hypercare | Platform | be,platform,hypercare | 5 | PO
Story | FE: Day-1 hotfix support (on-call) | Same for FE. | P0 | DEV-FE-1 | PRX-E7 | Sprint 22 — P7 Go-Live · GO-LIVE 14-Mar-2027 + Day-1 hypercare | Platform | fe,platform,hypercare | 3 | PO
Story | PO: Go-live retrospective (what went well / improve) | Retro with full team + stakeholders. Lessons logged + fed into Phase-2 plan. | P1 | PO | PRX-E7 | Sprint 22 — P7 Go-Live · GO-LIVE 14-Mar-2027 + Day-1 hypercare | Platform | po,retro | 3 | PO

## Sub-tasks
Sub-tasks — representative patterns (575 sub-tasks)
Note — these are representative sub-tasks for ≥3 SP stories. Refine per story during sprint refinement in Jira.
Issue Type | Summary | Parent Summary | Assignee | Original Estimate (hrs) | Labels
Sub-task | Schema/migration — Provision dev/stage/prod environments | DEVOPS: Provision dev/stage/prod environments | DEV-BE-1 | 4 | sub
Sub-task | Implementation — Provision dev/stage/prod environments | DEVOPS: Provision dev/stage/prod environments | DEV-BE-1 | 10 | sub
Sub-task | Unit + integration tests — Provision dev/stage/prod environments | DEVOPS: Provision dev/stage/prod environments | DEV-BE-1 | 4 | sub
Sub-task | Schema/migration — Set up CI/CD pipeline (BE + FE) | DEVOPS: Set up CI/CD pipeline (BE + FE) | DEV-BE-2 | 4 | sub
Sub-task | Implementation — Set up CI/CD pipeline (BE + FE) | DEVOPS: Set up CI/CD pipeline (BE + FE) | DEV-BE-2 | 10 | sub
Sub-task | Unit + integration tests — Set up CI/CD pipeline (BE + FE) | DEVOPS: Set up CI/CD pipeline (BE + FE) | DEV-BE-2 | 4 | sub
Sub-task | Component/page build — Bootstrap FE repo + design system package | FE: Bootstrap FE repo + design system package | DEV-FE-1 | 8 | sub
Sub-task | State wiring + form validation — Bootstrap FE repo + design system package | FE: Bootstrap FE repo + design system package | DEV-FE-1 | 4 | sub
Sub-task | E2E + a11y pass — Bootstrap FE repo + design system package | FE: Bootstrap FE repo + design system package | DEV-FE-1 | 3 | sub
Sub-task | Component/page build — Design system token package (colors/type/spacing) | FE: Design system token package (colors/type/spacing) | DEV-FE-2 | 8 | sub
Sub-task | State wiring + form validation — Design system token package (colors/type/spacing) | FE: Design system token package (colors/type/spacing) | DEV-FE-2 | 4 | sub
Sub-task | E2E + a11y pass — Design system token package (colors/type/spacing) | FE: Design system token package (colors/type/spacing) | DEV-FE-2 | 3 | sub
Sub-task | Research / draft — Stakeholder interviews — Records management | PO: Stakeholder interviews — Records management | PO | 4 | sub
Sub-task | Review + finalize — Stakeholder interviews — Records management | PO: Stakeholder interviews — Records management | PO | 2 | sub
Sub-task | Research / draft — Stakeholder interviews — Org structure | PO: Stakeholder interviews — Org structure | PO | 4 | sub
Sub-task | Review + finalize — Stakeholder interviews — Org structure | PO: Stakeholder interviews — Org structure | PO | 2 | sub
Sub-task | Research / draft — Spike — Auth provider comparison (Auth0/Keycloak/Cognito) | TL: Spike — Auth provider comparison (Auth0/Keycloak/Cognito) | TL | 4 | sub
Sub-task | Review + finalize — Spike — Auth provider comparison (Auth0/Keycloak/Cognito) | TL: Spike — Auth provider comparison (Auth0/Keycloak/Cognito) | TL | 2 | sub
Sub-task | Research / draft — Spike — Multi-tenancy pattern selection | TL: Spike — Multi-tenancy pattern selection | TL | 4 | sub
Sub-task | Review + finalize — Spike — Multi-tenancy pattern selection | TL: Spike — Multi-tenancy pattern selection | TL | 2 | sub
Sub-task | Figma build — UX research synthesis (existing materials) | DES: UX research synthesis (existing materials) | DES-1 | 10 | sub
Sub-task | Review + handoff — UX research synthesis (existing materials) | DES: UX research synthesis (existing materials) | DES-1 | 2 | sub
Sub-task | Schema/migration — Data model design — Employees + audit fields | BE: Data model design — Employees + audit fields | DEV-BE-1 | 4 | sub
Sub-task | Implementation — Data model design — Employees + audit fields | BE: Data model design — Employees + audit fields | DEV-BE-1 | 10 | sub
Sub-task | Unit + integration tests — Data model design — Employees + audit fields | BE: Data model design — Employees + audit fields | DEV-BE-1 | 4 | sub
Sub-task | Schema/migration — Data model design — Org structure + positions | BE: Data model design — Org structure + positions | DEV-BE-2 | 4 | sub
Sub-task | Implementation — Data model design — Org structure + positions | BE: Data model design — Org structure + positions | DEV-BE-2 | 10 | sub
Sub-task | Unit + integration tests — Data model design — Org structure + positions | BE: Data model design — Org structure + positions | DEV-BE-2 | 4 | sub
Sub-task | Test plan + cases — Test strategy document (M1 Phase-1) | QA: Test strategy document (M1 Phase-1) | QA-1 | 4 | sub
Sub-task | Automation scripts — Test strategy document (M1 Phase-1) | QA: Test strategy document (M1 Phase-1) | QA-1 | 6 | sub
Sub-task | Component/page build — UI architecture decision record (ADR) | FE: UI architecture decision record (ADR) | DEV-FE-1 | 8 | sub
Sub-task | State wiring + form validation — UI architecture decision record (ADR) | FE: UI architecture decision record (ADR) | DEV-FE-1 | 4 | sub
Sub-task | E2E + a11y pass — UI architecture decision record (ADR) | FE: UI architecture decision record (ADR) | DEV-FE-1 | 3 | sub
Sub-task | Figma build — Master layout — high-fidelity (from approved low-fi) | DES: Master layout — high-fidelity (from approved low-fi) | DES-1 | 10 | sub
Sub-task | Review + handoff — Master layout — high-fidelity (from approved low-fi) | DES: Master layout — high-fidelity (from approved low-fi) | DES-1 | 2 | sub
Sub-task | Research / draft — Stakeholder interviews — Contracts & documents | PO: Stakeholder interviews — Contracts & documents | PO | 4 | sub
Sub-task | Review + finalize — Stakeholder interviews — Contracts & documents | PO: Stakeholder interviews — Contracts & documents | PO | 2 | sub
Sub-task | Research / draft — Stakeholder interviews — Lifecycle events | PO: Stakeholder interviews — Lifecycle events | PO | 4 | sub
Sub-task | Review + finalize — Stakeholder interviews — Lifecycle events | PO: Stakeholder interviews — Lifecycle events | PO | 2 | sub
Sub-task | Research / draft — Stakeholder interviews — M10 Sys Admin | PO: Stakeholder interviews — M10 Sys Admin | PO | 4 | sub
Sub-task | Review + finalize — Stakeholder interviews — M10 Sys Admin | PO: Stakeholder interviews — M10 Sys Admin | PO | 2 | sub
Sub-task | Schema/migration — Data model design — Contracts + documents | BE: Data model design — Contracts + documents | DEV-BE-1 | 4 | sub
Sub-task | Implementation — Data model design — Contracts + documents | BE: Data model design — Contracts + documents | DEV-BE-1 | 8 | sub
Sub-task | Unit + integration tests — Data model design — Contracts + documents | BE: Data model design — Contracts + documents | DEV-BE-1 | 4 | sub
Sub-task | Schema/migration — Data model design — Lifecycle events + approvals | BE: Data model design — Lifecycle events + approvals | DEV-BE-2 | 4 | sub
Sub-task | Implementation — Data model design — Lifecycle events + approvals | BE: Data model design — Lifecycle events + approvals | DEV-BE-2 | 8 | sub
Sub-task | Unit + integration tests — Data model design — Lifecycle events + approvals | BE: Data model design — Lifecycle events + approvals | DEV-BE-2 | 4 | sub
Sub-task | Research / draft — Integration contract — SSO (OIDC) | TL: Integration contract — SSO (OIDC) | TL | 4 | sub
Sub-task | Review + finalize — Integration contract — SSO (OIDC) | TL: Integration contract — SSO (OIDC) | TL | 2 | sub
Sub-task | Research / draft — Integration contract — Data imports (CSV/API) | TL: Integration contract — Data imports (CSV/API) | TL | 4 | sub
Sub-task | Review + finalize — Integration contract — Data imports (CSV/API) | TL: Integration contract — Data imports (CSV/API) | TL | 2 | sub
Sub-task | Figma build — Component library — Forms (inputs, selects, datepickers) | DES: Component library — Forms (inputs, selects, datepickers) | DES-1 | 10 | sub
Sub-task | Review + handoff — Component library — Forms (inputs, selects, datepickers) | DES: Component library — Forms (inputs, selects, datepickers) | DES-1 | 2 | sub
Sub-task | Figma build — Component library — Data display (tables, cards) | DES: Component library — Data display (tables, cards) | DES-1 | 10 | sub
Sub-task | Review + handoff — Component library — Data display (tables, cards) | DES: Component library — Data display (tables, cards) | DES-1 | 2 | sub
Sub-task | Figma build — M1 Employee records wireframes (list + detail + edit) | DES: M1 Employee records wireframes (list + detail + edit) | DES-1 | 10 | sub
Sub-task | Review + handoff — M1 Employee records wireframes (list + detail + edit) | DES: M1 Employee records wireframes (list + detail + edit) | DES-1 | 2 | sub
Sub-task | Figma build — M1 Org structure + Positions wireframes | DES: M1 Org structure + Positions wireframes | DES-1 | 10 | sub
Sub-task | Review + handoff — M1 Org structure + Positions wireframes | DES: M1 Org structure + Positions wireframes | DES-1 | 2 | sub
Sub-task | Figma build — M1 Contracts + documents wireframes | DES: M1 Contracts + documents wireframes | DES-1 | 10 | sub
Sub-task | Review + handoff — M1 Contracts + documents wireframes | DES: M1 Contracts + documents wireframes | DES-1 | 2 | sub
Sub-task | Figma build — M1 Lifecycle events + approvals wireframes | DES: M1 Lifecycle events + approvals wireframes | DES-1 | 10 | sub
Sub-task | Review + handoff — M1 Lifecycle events + approvals wireframes | DES: M1 Lifecycle events + approvals wireframes | DES-1 | 2 | sub
Sub-task | Figma build — M10 Admin wireframes | DES: M10 Admin wireframes | DES-1 | 10 | sub
Sub-task | Review + handoff — M10 Admin wireframes | DES: M10 Admin wireframes | DES-1 | 2 | sub
Sub-task | Figma build — Component library — Navigation + shell | DES: Component library — Navigation + shell | DES-1 | 10 | sub
Sub-task | Review + handoff — Component library — Navigation + shell | DES: Component library — Navigation + shell | DES-1 | 2 | sub
Sub-task | Test plan + cases — Test environment setup (local + stage) | QA: Test environment setup (local + stage) | QA-1 | 4 | sub
Sub-task | Automation scripts — Test environment setup (local + stage) | QA: Test environment setup (local + stage) | QA-1 | 6 | sub
Sub-task | Test plan + cases — Automation framework scaffolding | QA: Automation framework scaffolding | QA-1 | 4 | sub
Sub-task | Automation scripts — Automation framework scaffolding | QA: Automation framework scaffolding | QA-1 | 10 | sub
Sub-task | Component/page build — Shared components — Button / Input / Select | FE: Shared components — Button / Input / Select | DEV-FE-1 | 10 | sub
Sub-task | State wiring + form validation — Shared components — Button / Input / Select | FE: Shared components — Button / Input / Select | DEV-FE-1 | 4 | sub
Sub-task | E2E + a11y pass — Shared components — Button / Input / Select | FE: Shared components — Button / Input / Select | DEV-FE-1 | 3 | sub
Sub-task | Component/page build — Shared components — Table / Card / Badge | FE: Shared components — Table / Card / Badge | DEV-FE-2 | 10 | sub
Sub-task | State wiring + form validation — Shared components — Table / Card / Badge | FE: Shared components — Table / Card / Badge | DEV-FE-2 | 4 | sub
Sub-task | E2E + a11y pass — Shared components — Table / Card / Badge | FE: Shared components — Table / Card / Badge | DEV-FE-2 | 3 | sub
Sub-task | Schema/migration — API convention doc + OpenAPI scaffolding | BE: API convention doc + OpenAPI scaffolding | DEV-BE-1 | 4 | sub
Sub-task | Implementation — API convention doc + OpenAPI scaffolding | BE: API convention doc + OpenAPI scaffolding | DEV-BE-1 | 8 | sub
Sub-task | Unit + integration tests — API convention doc + OpenAPI scaffolding | BE: API convention doc + OpenAPI scaffolding | DEV-BE-1 | 4 | sub
Sub-task | Schema/migration — Database migration tooling + seed-data pattern | BE: Database migration tooling + seed-data pattern | DEV-BE-2 | 4 | sub
Sub-task | Implementation — Database migration tooling + seed-data pattern | BE: Database migration tooling + seed-data pattern | DEV-BE-2 | 8 | sub
Sub-task | Unit + integration tests — Database migration tooling + seed-data pattern | BE: Database migration tooling + seed-data pattern | DEV-BE-2 | 4 | sub
Sub-task | Schema/migration — Tenancy data model + migrations | BE: Tenancy data model + migrations | DEV-BE-1 | 4 | sub
Sub-task | Implementation — Tenancy data model + migrations | BE: Tenancy data model + migrations | DEV-BE-1 | 16 | sub
Sub-task | Unit + integration tests — Tenancy data model + migrations | BE: Tenancy data model + migrations | DEV-BE-1 | 4 | sub
Sub-task | Schema/migration — Tenant-isolation middleware + query guards | BE: Tenant-isolation middleware + query guards | DEV-BE-1 | 4 | sub
Sub-task | Implementation — Tenant-isolation middleware + query guards | BE: Tenant-isolation middleware + query guards | DEV-BE-1 | 10 | sub
Sub-task | Unit + integration tests — Tenant-isolation middleware + query guards | BE: Tenant-isolation middleware + query guards | DEV-BE-1 | 4 | sub
Sub-task | Schema/migration — SSO integration — OIDC provider connection | BE: SSO integration — OIDC provider connection | DEV-BE-2 | 4 | sub
Sub-task | Implementation — SSO integration — OIDC provider connection | BE: SSO integration — OIDC provider connection | DEV-BE-2 | 16 | sub
Sub-task | Unit + integration tests — SSO integration — OIDC provider connection | BE: SSO integration — OIDC provider connection | DEV-BE-2 | 4 | sub
Sub-task | Schema/migration — SSO session handling + refresh tokens | BE: SSO session handling + refresh tokens | DEV-BE-2 | 4 | sub
Sub-task | Implementation — SSO session handling + refresh tokens | BE: SSO session handling + refresh tokens | DEV-BE-2 | 10 | sub
Sub-task | Unit + integration tests — SSO session handling + refresh tokens | BE: SSO session handling + refresh tokens | DEV-BE-2 | 4 | sub
Sub-task | Schema/migration — RBAC schema (roles, permissions, role_permissions) | BE: RBAC schema (roles, permissions, role_permissions) | DEV-BE-1 | 4 | sub
Sub-task | Implementation — RBAC schema (roles, permissions, role_permissions) | BE: RBAC schema (roles, permissions, role_permissions) | DEV-BE-1 | 10 | sub
Sub-task | Unit + integration tests — RBAC schema (roles, permissions, role_permissions) | BE: RBAC schema (roles, permissions, role_permissions) | DEV-BE-1 | 4 | sub
Sub-task | Schema/migration — RBAC enforcement middleware + decorators | BE: RBAC enforcement middleware + decorators | DEV-BE-2 | 4 | sub
Sub-task | Implementation — RBAC enforcement middleware + decorators | BE: RBAC enforcement middleware + decorators | DEV-BE-2 | 10 | sub
Sub-task | Unit + integration tests — RBAC enforcement middleware + decorators | BE: RBAC enforcement middleware + decorators | DEV-BE-2 | 4 | sub
Sub-task | Component/page build — Login screen + SSO flow | FE: Login screen + SSO flow | DEV-FE-1 | 10 | sub
Sub-task | State wiring + form validation — Login screen + SSO flow | FE: Login screen + SSO flow | DEV-FE-1 | 4 | sub
Sub-task | E2E + a11y pass — Login screen + SSO flow | FE: Login screen + SSO flow | DEV-FE-1 | 3 | sub
Sub-task | Component/page build — Tenant-aware routing + URL scheme | FE: Tenant-aware routing + URL scheme | DEV-FE-1 | 8 | sub
Sub-task | State wiring + form validation — Tenant-aware routing + URL scheme | FE: Tenant-aware routing + URL scheme | DEV-FE-1 | 4 | sub
Sub-task | E2E + a11y pass — Tenant-aware routing + URL scheme | FE: Tenant-aware routing + URL scheme | DEV-FE-1 | 3 | sub
Sub-task | Component/page build — Session management + auto-refresh + idle logout | FE: Session management + auto-refresh + idle logout | DEV-FE-2 | 8 | sub
Sub-task | State wiring + form validation — Session management + auto-refresh + idle logout | FE: Session management + auto-refresh + idle logout | DEV-FE-2 | 4 | sub
Sub-task | E2E + a11y pass — Session management + auto-refresh + idle logout | FE: Session management + auto-refresh + idle logout | DEV-FE-2 | 3 | sub
Sub-task | Test plan + cases — Auth + tenancy + RBAC test suite | QA: Auth + tenancy + RBAC test suite | QA-1 | 4 | sub
Sub-task | Automation scripts — Auth + tenancy + RBAC test suite | QA: Auth + tenancy + RBAC test suite | QA-1 | 10 | sub
Sub-task | Schema/migration — Audit log data model + write-path | BE: Audit log data model + write-path | DEV-BE-1 | 4 | sub
Sub-task | Implementation — Audit log data model + write-path | BE: Audit log data model + write-path | DEV-BE-1 | 10 | sub
Sub-task | Unit + integration tests — Audit log data model + write-path | BE: Audit log data model + write-path | DEV-BE-1 | 4 | sub
Sub-task | Schema/migration — Audit log query API (filters + pagination) | BE: Audit log query API (filters + pagination) | DEV-BE-1 | 4 | sub
Sub-task | Implementation — Audit log query API (filters + pagination) | BE: Audit log query API (filters + pagination) | DEV-BE-1 | 8 | sub
Sub-task | Unit + integration tests — Audit log query API (filters + pagination) | BE: Audit log query API (filters + pagination) | DEV-BE-1 | 4 | sub
Sub-task | Schema/migration — Platform config endpoints (branding, locale) | BE: Platform config endpoints (branding, locale) | DEV-BE-2 | 4 | sub
Sub-task | Implementation — Platform config endpoints (branding, locale) | BE: Platform config endpoints (branding, locale) | DEV-BE-2 | 8 | sub
Sub-task | Unit + integration tests — Platform config endpoints (branding, locale) | BE: Platform config endpoints (branding, locale) | DEV-BE-2 | 4 | sub
Sub-task | Component/page build — App shell (header + content + footer) | FE: App shell (header + content + footer) | DEV-FE-1 | 10 | sub
Sub-task | State wiring + form validation — App shell (header + content + footer) | FE: App shell (header + content + footer) | DEV-FE-1 | 4 | sub
Sub-task | E2E + a11y pass — App shell (header + content + footer) | FE: App shell (header + content + footer) | DEV-FE-1 | 3 | sub
Sub-task | Component/page build — Collapsible sidebar with module navigation | FE: Collapsible sidebar with module navigation | DEV-FE-2 | 16 | sub
Sub-task | State wiring + form validation — Collapsible sidebar with module navigation | FE: Collapsible sidebar with module navigation | DEV-FE-2 | 4 | sub
Sub-task | E2E + a11y pass — Collapsible sidebar with module navigation | FE: Collapsible sidebar with module navigation | DEV-FE-2 | 3 | sub
Sub-task | Component/page build — Brand tokens wired into runtime theme | FE: Brand tokens wired into runtime theme | DEV-FE-1 | 10 | sub
Sub-task | State wiring + form validation — Brand tokens wired into runtime theme | FE: Brand tokens wired into runtime theme | DEV-FE-1 | 4 | sub
Sub-task | E2E + a11y pass — Brand tokens wired into runtime theme | FE: Brand tokens wired into runtime theme | DEV-FE-1 | 3 | sub
Sub-task | Component/page build — User menu + profile dropdown + logout | FE: User menu + profile dropdown + logout | DEV-FE-2 | 8 | sub
Sub-task | State wiring + form validation — User menu + profile dropdown + logout | FE: User menu + profile dropdown + logout | DEV-FE-2 | 4 | sub
Sub-task | E2E + a11y pass — User menu + profile dropdown + logout | FE: User menu + profile dropdown + logout | DEV-FE-2 | 3 | sub
Sub-task | Component/page build — Error boundaries + empty states + loading shells | FE: Error boundaries + empty states + loading shells | DEV-FE-1 | 8 | sub
Sub-task | State wiring + form validation — Error boundaries + empty states + loading shells | FE: Error boundaries + empty states + loading shells | DEV-FE-1 | 4 | sub
Sub-task | E2E + a11y pass — Error boundaries + empty states + loading shells | FE: Error boundaries + empty states + loading shells | DEV-FE-1 | 3 | sub
Sub-task | Test plan + cases — Audit log + shell e2e + accessibility pass | QA: Audit log + shell e2e + accessibility pass | QA-1 | 4 | sub
Sub-task | Automation scripts — Audit log + shell e2e + accessibility pass | QA: Audit log + shell e2e + accessibility pass | QA-1 | 10 | sub
Sub-task | Schema/migration — Staging environment hardening | DEVOPS: Staging environment hardening | DEV-BE-2 | 4 | sub
Sub-task | Implementation — Staging environment hardening | DEVOPS: Staging environment hardening | DEV-BE-2 | 8 | sub
Sub-task | Unit + integration tests — Staging environment hardening | DEVOPS: Staging environment hardening | DEV-BE-2 | 4 | sub
Sub-task | Schema/migration — employees table + migrations + seed | BE: employees table + migrations + seed | DEV-BE-1 | 4 | sub
Sub-task | Implementation — employees table + migrations + seed | BE: employees table + migrations + seed | DEV-BE-1 | 10 | sub
Sub-task | Unit + integration tests — employees table + migrations + seed | BE: employees table + migrations + seed | DEV-BE-1 | 4 | sub
Sub-task | Schema/migration — GET /employees (list + filter + paginate + sort) | BE: GET /employees (list + filter + paginate + sort) | DEV-BE-1 | 4 | sub
Sub-task | Implementation — GET /employees (list + filter + paginate + sort) | BE: GET /employees (list + filter + paginate + sort) | DEV-BE-1 | 10 | sub
Sub-task | Unit + integration tests — GET /employees (list + filter + paginate + sort) | BE: GET /employees (list + filter + paginate + sort) | DEV-BE-1 | 4 | sub
Sub-task | Schema/migration — GET /employees/:id (full detail) | BE: GET /employees/:id (full detail) | DEV-BE-1 | 4 | sub
Sub-task | Implementation — GET /employees/:id (full detail) | BE: GET /employees/:id (full detail) | DEV-BE-1 | 8 | sub
Sub-task | Unit + integration tests — GET /employees/:id (full detail) | BE: GET /employees/:id (full detail) | DEV-BE-1 | 4 | sub
Sub-task | Schema/migration — POST /employees (create + validation) | BE: POST /employees (create + validation) | DEV-BE-2 | 4 | sub
Sub-task | Implementation — POST /employees (create + validation) | BE: POST /employees (create + validation) | DEV-BE-2 | 10 | sub
Sub-task | Unit + integration tests — POST /employees (create + validation) | BE: POST /employees (create + validation) | DEV-BE-2 | 4 | sub
Sub-task | Schema/migration — PUT /employees/:id (update + partial) | BE: PUT /employees/:id (update + partial) | DEV-BE-2 | 4 | sub
Sub-task | Implementation — PUT /employees/:id (update + partial) | BE: PUT /employees/:id (update + partial) | DEV-BE-2 | 8 | sub
Sub-task | Unit + integration tests — PUT /employees/:id (update + partial) | BE: PUT /employees/:id (update + partial) | DEV-BE-2 | 4 | sub
Sub-task | Schema/migration — DELETE /employees/:id (soft-delete + restore) | BE: DELETE /employees/:id (soft-delete + restore) | DEV-BE-2 | 4 | sub
Sub-task | Implementation — DELETE /employees/:id (soft-delete + restore) | BE: DELETE /employees/:id (soft-delete + restore) | DEV-BE-2 | 8 | sub
Sub-task | Unit + integration tests — DELETE /employees/:id (soft-delete + restore) | BE: DELETE /employees/:id (soft-delete + restore) | DEV-BE-2 | 4 | sub
Sub-task | Schema/migration — Employee search (full-text) | BE: Employee search (full-text) | DEV-BE-2 | 4 | sub
Sub-task | Implementation — Employee search (full-text) | BE: Employee search (full-text) | DEV-BE-2 | 10 | sub
Sub-task | Unit + integration tests — Employee search (full-text) | BE: Employee search (full-text) | DEV-BE-2 | 4 | sub
Sub-task | Component/page build — Employees list page (table + filters + search) | FE: Employees list page (table + filters + search) | DEV-FE-1 | 16 | sub
Sub-task | State wiring + form validation — Employees list page (table + filters + search) | FE: Employees list page (table + filters + search) | DEV-FE-1 | 4 | sub
Sub-task | E2E + a11y pass — Employees list page (table + filters + search) | FE: Employees list page (table + filters + search) | DEV-FE-1 | 3 | sub
Sub-task | Component/page build — Employee detail page (tabs: profile, employment, docs) | FE: Employee detail page (tabs: profile, employment, docs) | DEV-FE-1 | 10 | sub
Sub-task | State wiring + form validation — Employee detail page (tabs: profile, employment, docs) | FE: Employee detail page (tabs: profile, employment, docs) | DEV-FE-1 | 4 | sub
Sub-task | E2E + a11y pass — Employee detail page (tabs: profile, employment, docs) | FE: Employee detail page (tabs: profile, employment, docs) | DEV-FE-1 | 3 | sub
Sub-task | Component/page build — Employee create form (multi-step wizard) | FE: Employee create form (multi-step wizard) | DEV-FE-2 | 16 | sub
Sub-task | State wiring + form validation — Employee create form (multi-step wizard) | FE: Employee create form (multi-step wizard) | DEV-FE-2 | 4 | sub
Sub-task | E2E + a11y pass — Employee create form (multi-step wizard) | FE: Employee create form (multi-step wizard) | DEV-FE-2 | 3 | sub
Sub-task | Component/page build — Employee edit form + inline-edit where appropriate | FE: Employee edit form + inline-edit where appropriate | DEV-FE-2 | 10 | sub
Sub-task | State wiring + form validation — Employee edit form + inline-edit where appropriate | FE: Employee edit form + inline-edit where appropriate | DEV-FE-2 | 4 | sub
Sub-task | E2E + a11y pass — Employee edit form + inline-edit where appropriate | FE: Employee edit form + inline-edit where appropriate | DEV-FE-2 | 3 | sub
Sub-task | Component/page build — Employee profile header component | FE: Employee profile header component | DEV-FE-2 | 8 | sub
Sub-task | State wiring + form validation — Employee profile header component | FE: Employee profile header component | DEV-FE-2 | 4 | sub
Sub-task | E2E + a11y pass — Employee profile header component | FE: Employee profile header component | DEV-FE-2 | 3 | sub
Sub-task | Test plan + cases — Employee CRUD test cases + automation | QA: Employee CRUD test cases + automation | QA-1 | 4 | sub
Sub-task | Automation scripts — Employee CRUD test cases + automation | QA: Employee CRUD test cases + automation | QA-1 | 10 | sub
Sub-task | Test plan + cases — Employee search + filter test cases | QA: Employee search + filter test cases | QA-1 | 4 | sub
Sub-task | Automation scripts — Employee search + filter test cases | QA: Employee search + filter test cases | QA-1 | 6 | sub
Sub-task | Schema/migration — org_units table + migrations + tree queries | BE: org_units table + migrations + tree queries | DEV-BE-1 | 4 | sub
Sub-task | Implementation — org_units table + migrations + tree queries | BE: org_units table + migrations + tree queries | DEV-BE-1 | 10 | sub
Sub-task | Unit + integration tests — org_units table + migrations + tree queries | BE: org_units table + migrations + tree queries | DEV-BE-1 | 4 | sub
Sub-task | Schema/migration — Org units CRUD API | BE: Org units CRUD API | DEV-BE-1 | 4 | sub
Sub-task | Implementation — Org units CRUD API | BE: Org units CRUD API | DEV-BE-1 | 10 | sub
Sub-task | Unit + integration tests — Org units CRUD API | BE: Org units CRUD API | DEV-BE-1 | 4 | sub
Sub-task | Schema/migration — Org tree query endpoint (full + subtree) | BE: Org tree query endpoint (full + subtree) | DEV-BE-1 | 4 | sub
Sub-task | Implementation — Org tree query endpoint (full + subtree) | BE: Org tree query endpoint (full + subtree) | DEV-BE-1 | 10 | sub
Sub-task | Unit + integration tests — Org tree query endpoint (full + subtree) | BE: Org tree query endpoint (full + subtree) | DEV-BE-1 | 4 | sub
Sub-task | Schema/migration — positions table + CRUD API | BE: positions table + CRUD API | DEV-BE-2 | 4 | sub
Sub-task | Implementation — positions table + CRUD API | BE: positions table + CRUD API | DEV-BE-2 | 10 | sub
Sub-task | Unit + integration tests — positions table + CRUD API | BE: positions table + CRUD API | DEV-BE-2 | 4 | sub
Sub-task | Schema/migration — Position assignment API | BE: Position assignment API | DEV-BE-2 | 4 | sub
Sub-task | Implementation — Position assignment API | BE: Position assignment API | DEV-BE-2 | 10 | sub
Sub-task | Unit + integration tests — Position assignment API | BE: Position assignment API | DEV-BE-2 | 4 | sub
Sub-task | Schema/migration — Reporting-line query endpoint | BE: Reporting-line query endpoint | DEV-BE-2 | 4 | sub
Sub-task | Implementation — Reporting-line query endpoint | BE: Reporting-line query endpoint | DEV-BE-2 | 8 | sub
Sub-task | Unit + integration tests — Reporting-line query endpoint | BE: Reporting-line query endpoint | DEV-BE-2 | 4 | sub
Sub-task | Component/page build — Org chart visualization (interactive) | FE: Org chart visualization (interactive) | DEV-FE-1 | 16 | sub
Sub-task | State wiring + form validation — Org chart visualization (interactive) | FE: Org chart visualization (interactive) | DEV-FE-1 | 4 | sub
Sub-task | E2E + a11y pass — Org chart visualization (interactive) | FE: Org chart visualization (interactive) | DEV-FE-1 | 3 | sub
Sub-task | Component/page build — Org unit create/edit form + move dialog | FE: Org unit create/edit form + move dialog | DEV-FE-1 | 10 | sub
Sub-task | State wiring + form validation — Org unit create/edit form + move dialog | FE: Org unit create/edit form + move dialog | DEV-FE-1 | 4 | sub
Sub-task | E2E + a11y pass — Org unit create/edit form + move dialog | FE: Org unit create/edit form + move dialog | DEV-FE-1 | 3 | sub
Sub-task | Component/page build — Positions list + detail pages | FE: Positions list + detail pages | DEV-FE-2 | 10 | sub
Sub-task | State wiring + form validation — Positions list + detail pages | FE: Positions list + detail pages | DEV-FE-2 | 4 | sub
Sub-task | E2E + a11y pass — Positions list + detail pages | FE: Positions list + detail pages | DEV-FE-2 | 3 | sub
Sub-task | Component/page build — Position assignment UI (assign / unassign) | FE: Position assignment UI (assign / unassign) | DEV-FE-2 | 10 | sub
Sub-task | State wiring + form validation — Position assignment UI (assign / unassign) | FE: Position assignment UI (assign / unassign) | DEV-FE-2 | 4 | sub
Sub-task | E2E + a11y pass — Position assignment UI (assign / unassign) | FE: Position assignment UI (assign / unassign) | DEV-FE-2 | 3 | sub
Sub-task | Component/page build — Org unit picker component (shared) | FE: Org unit picker component (shared) | DEV-FE-2 | 10 | sub
Sub-task | State wiring + form validation — Org unit picker component (shared) | FE: Org unit picker component (shared) | DEV-FE-2 | 4 | sub
Sub-task | E2E + a11y pass — Org unit picker component (shared) | FE: Org unit picker component (shared) | DEV-FE-2 | 3 | sub
Sub-task | Test plan + cases — Org structure + positions test cases | QA: Org structure + positions test cases | QA-1 | 4 | sub
Sub-task | Automation scripts — Org structure + positions test cases | QA: Org structure + positions test cases | QA-1 | 10 | sub
Sub-task | Schema/migration — contracts + contract_versions tables + migrations | BE: contracts + contract_versions tables + migrations | DEV-BE-1 | 4 | sub
Sub-task | Implementation — contracts + contract_versions tables + migrations | BE: contracts + contract_versions tables + migrations | DEV-BE-1 | 10 | sub
Sub-task | Unit + integration tests — contracts + contract_versions tables + migrations | BE: contracts + contract_versions tables + migrations | DEV-BE-1 | 4 | sub
Sub-task | Schema/migration — Contracts CRUD API | BE: Contracts CRUD API | DEV-BE-1 | 4 | sub
Sub-task | Implementation — Contracts CRUD API | BE: Contracts CRUD API | DEV-BE-1 | 10 | sub
Sub-task | Unit + integration tests — Contracts CRUD API | BE: Contracts CRUD API | DEV-BE-1 | 4 | sub
Sub-task | Schema/migration — Contract lifecycle state machine | BE: Contract lifecycle state machine | DEV-BE-1 | 4 | sub
Sub-task | Implementation — Contract lifecycle state machine | BE: Contract lifecycle state machine | DEV-BE-1 | 10 | sub
Sub-task | Unit + integration tests — Contract lifecycle state machine | BE: Contract lifecycle state machine | DEV-BE-1 | 4 | sub
Sub-task | Schema/migration — documents + document_acl tables + S3 bucket | BE: documents + document_acl tables + S3 bucket | DEV-BE-2 | 4 | sub
Sub-task | Implementation — documents + document_acl tables + S3 bucket | BE: documents + document_acl tables + S3 bucket | DEV-BE-2 | 10 | sub
Sub-task | Unit + integration tests — documents + document_acl tables + S3 bucket | BE: documents + document_acl tables + S3 bucket | DEV-BE-2 | 4 | sub
Sub-task | Schema/migration — Document upload (signed-URL + virus-scan) | BE: Document upload (signed-URL + virus-scan) | DEV-BE-2 | 4 | sub
Sub-task | Implementation — Document upload (signed-URL + virus-scan) | BE: Document upload (signed-URL + virus-scan) | DEV-BE-2 | 10 | sub
Sub-task | Unit + integration tests — Document upload (signed-URL + virus-scan) | BE: Document upload (signed-URL + virus-scan) | DEV-BE-2 | 4 | sub
Sub-task | Schema/migration — Document download/metadata endpoint | BE: Document download/metadata endpoint | DEV-BE-2 | 4 | sub
Sub-task | Implementation — Document download/metadata endpoint | BE: Document download/metadata endpoint | DEV-BE-2 | 8 | sub
Sub-task | Unit + integration tests — Document download/metadata endpoint | BE: Document download/metadata endpoint | DEV-BE-2 | 4 | sub
Sub-task | Component/page build — Contracts list + detail pages | FE: Contracts list + detail pages | DEV-FE-1 | 10 | sub
Sub-task | State wiring + form validation — Contracts list + detail pages | FE: Contracts list + detail pages | DEV-FE-1 | 4 | sub
Sub-task | E2E + a11y pass — Contracts list + detail pages | FE: Contracts list + detail pages | DEV-FE-1 | 3 | sub
Sub-task | Component/page build — Contract create/edit form | FE: Contract create/edit form | DEV-FE-1 | 10 | sub
Sub-task | State wiring + form validation — Contract create/edit form | FE: Contract create/edit form | DEV-FE-1 | 4 | sub
Sub-task | E2E + a11y pass — Contract create/edit form | FE: Contract create/edit form | DEV-FE-1 | 3 | sub
Sub-task | Component/page build — Contract lifecycle actions (renew / terminate / sign) | FE: Contract lifecycle actions (renew / terminate / sign) | DEV-FE-1 | 10 | sub
Sub-task | State wiring + form validation — Contract lifecycle actions (renew / terminate / sign) | FE: Contract lifecycle actions (renew / terminate / sign) | DEV-FE-1 | 4 | sub
Sub-task | E2E + a11y pass — Contract lifecycle actions (renew / terminate / sign) | FE: Contract lifecycle actions (renew / terminate / sign) | DEV-FE-1 | 3 | sub
Sub-task | Component/page build — Documents vault page (per employee) | FE: Documents vault page (per employee) | DEV-FE-2 | 10 | sub
Sub-task | State wiring + form validation — Documents vault page (per employee) | FE: Documents vault page (per employee) | DEV-FE-2 | 4 | sub
Sub-task | E2E + a11y pass — Documents vault page (per employee) | FE: Documents vault page (per employee) | DEV-FE-2 | 3 | sub
Sub-task | Component/page build — Document upload widget (drag-drop + progress) | FE: Document upload widget (drag-drop + progress) | DEV-FE-2 | 10 | sub
Sub-task | State wiring + form validation — Document upload widget (drag-drop + progress) | FE: Document upload widget (drag-drop + progress) | DEV-FE-2 | 4 | sub
Sub-task | E2E + a11y pass — Document upload widget (drag-drop + progress) | FE: Document upload widget (drag-drop + progress) | DEV-FE-2 | 3 | sub
Sub-task | Component/page build — Document viewer (PDF preview modal) | FE: Document viewer (PDF preview modal) | DEV-FE-2 | 10 | sub
Sub-task | State wiring + form validation — Document viewer (PDF preview modal) | FE: Document viewer (PDF preview modal) | DEV-FE-2 | 4 | sub
Sub-task | E2E + a11y pass — Document viewer (PDF preview modal) | FE: Document viewer (PDF preview modal) | DEV-FE-2 | 3 | sub
Sub-task | Test plan + cases — Contracts + documents test cases | QA: Contracts + documents test cases | QA-1 | 4 | sub
Sub-task | Automation scripts — Contracts + documents test cases | QA: Contracts + documents test cases | QA-1 | 10 | sub
Sub-task | Schema/migration — lifecycle_events table + API (hire/promote/transfer/terminat | BE: lifecycle_events table + API (hire/promote/transfer/terminate) | DEV-BE-1 | 4 | sub
Sub-task | Implementation — lifecycle_events table + API (hire/promote/transfer/terminat | BE: lifecycle_events table + API (hire/promote/transfer/terminate) | DEV-BE-1 | 10 | sub
Sub-task | Unit + integration tests — lifecycle_events table + API (hire/promote/transfer/terminat | BE: lifecycle_events table + API (hire/promote/transfer/terminate) | DEV-BE-1 | 4 | sub
Sub-task | Schema/migration — Approvals data model (workflows, steps, history) | BE: Approvals data model (workflows, steps, history) | DEV-BE-2 | 4 | sub
Sub-task | Implementation — Approvals data model (workflows, steps, history) | BE: Approvals data model (workflows, steps, history) | DEV-BE-2 | 10 | sub
Sub-task | Unit + integration tests — Approvals data model (workflows, steps, history) | BE: Approvals data model (workflows, steps, history) | DEV-BE-2 | 4 | sub
Sub-task | Schema/migration — Approval engine — state transitions | BE: Approval engine — state transitions | DEV-BE-1 | 4 | sub
Sub-task | Implementation — Approval engine — state transitions | BE: Approval engine — state transitions | DEV-BE-1 | 16 | sub
Sub-task | Unit + integration tests — Approval engine — state transitions | BE: Approval engine — state transitions | DEV-BE-1 | 4 | sub
Sub-task | Schema/migration — Notifications service + email templates | BE: Notifications service + email templates | DEV-BE-2 | 4 | sub
Sub-task | Implementation — Notifications service + email templates | BE: Notifications service + email templates | DEV-BE-2 | 10 | sub
Sub-task | Unit + integration tests — Notifications service + email templates | BE: Notifications service + email templates | DEV-BE-2 | 4 | sub
Sub-task | Schema/migration — Approval audit trail + SLA metrics | BE: Approval audit trail + SLA metrics | DEV-BE-2 | 4 | sub
Sub-task | Implementation — Approval audit trail + SLA metrics | BE: Approval audit trail + SLA metrics | DEV-BE-2 | 8 | sub
Sub-task | Unit + integration tests — Approval audit trail + SLA metrics | BE: Approval audit trail + SLA metrics | DEV-BE-2 | 4 | sub
Sub-task | Component/page build — Lifecycle event timeline component | FE: Lifecycle event timeline component | DEV-FE-1 | 10 | sub
Sub-task | State wiring + form validation — Lifecycle event timeline component | FE: Lifecycle event timeline component | DEV-FE-1 | 4 | sub
Sub-task | E2E + a11y pass — Lifecycle event timeline component | FE: Lifecycle event timeline component | DEV-FE-1 | 3 | sub
Sub-task | Component/page build — Lifecycle event create wizard (promote/transfer) | FE: Lifecycle event create wizard (promote/transfer) | DEV-FE-1 | 16 | sub
Sub-task | State wiring + form validation — Lifecycle event create wizard (promote/transfer) | FE: Lifecycle event create wizard (promote/transfer) | DEV-FE-1 | 4 | sub
Sub-task | E2E + a11y pass — Lifecycle event create wizard (promote/transfer) | FE: Lifecycle event create wizard (promote/transfer) | DEV-FE-1 | 3 | sub
Sub-task | Component/page build — Approvals inbox page (pending + completed) | FE: Approvals inbox page (pending + completed) | DEV-FE-2 | 10 | sub
Sub-task | State wiring + form validation — Approvals inbox page (pending + completed) | FE: Approvals inbox page (pending + completed) | DEV-FE-2 | 4 | sub
Sub-task | E2E + a11y pass — Approvals inbox page (pending + completed) | FE: Approvals inbox page (pending + completed) | DEV-FE-2 | 3 | sub
Sub-task | Component/page build — Approval detail page + approve/reject action | FE: Approval detail page + approve/reject action | DEV-FE-2 | 10 | sub
Sub-task | State wiring + form validation — Approval detail page + approve/reject action | FE: Approval detail page + approve/reject action | DEV-FE-2 | 4 | sub
Sub-task | E2E + a11y pass — Approval detail page + approve/reject action | FE: Approval detail page + approve/reject action | DEV-FE-2 | 3 | sub
Sub-task | Component/page build — Notifications UI (bell icon + dropdown + mark-read) | FE: Notifications UI (bell icon + dropdown + mark-read) | DEV-FE-2 | 8 | sub
Sub-task | State wiring + form validation — Notifications UI (bell icon + dropdown + mark-read) | FE: Notifications UI (bell icon + dropdown + mark-read) | DEV-FE-2 | 4 | sub
Sub-task | E2E + a11y pass — Notifications UI (bell icon + dropdown + mark-read) | FE: Notifications UI (bell icon + dropdown + mark-read) | DEV-FE-2 | 3 | sub
Sub-task | Test plan + cases — Lifecycle events test cases | QA: Lifecycle events test cases | QA-1 | 4 | sub
Sub-task | Automation scripts — Lifecycle events test cases | QA: Lifecycle events test cases | QA-1 | 10 | sub
Sub-task | Test plan + cases — Approvals test cases + SLA scenarios | QA: Approvals test cases + SLA scenarios | QA-1 | 4 | sub
Sub-task | Automation scripts — Approvals test cases + SLA scenarios | QA: Approvals test cases + SLA scenarios | QA-1 | 8 | sub
Sub-task | Schema/migration — Query performance tuning + indexes review | BE: Query performance tuning + indexes review | DEV-BE-1 | 4 | sub
Sub-task | Implementation — Query performance tuning + indexes review | BE: Query performance tuning + indexes review | DEV-BE-1 | 10 | sub
Sub-task | Unit + integration tests — Query performance tuning + indexes review | BE: Query performance tuning + indexes review | DEV-BE-1 | 4 | sub
Sub-task | Schema/migration — API rate limiting + throttling per tenant | BE: API rate limiting + throttling per tenant | DEV-BE-1 | 4 | sub
Sub-task | Implementation — API rate limiting + throttling per tenant | BE: API rate limiting + throttling per tenant | DEV-BE-1 | 8 | sub
Sub-task | Unit + integration tests — API rate limiting + throttling per tenant | BE: API rate limiting + throttling per tenant | DEV-BE-1 | 4 | sub
Sub-task | Schema/migration — Bulk import API (employees CSV) | BE: Bulk import API (employees CSV) | DEV-BE-2 | 4 | sub
Sub-task | Implementation — Bulk import API (employees CSV) | BE: Bulk import API (employees CSV) | DEV-BE-2 | 10 | sub
Sub-task | Unit + integration tests — Bulk import API (employees CSV) | BE: Bulk import API (employees CSV) | DEV-BE-2 | 4 | sub
Sub-task | Schema/migration — Export API (employees, contracts, org) | BE: Export API (employees, contracts, org) | DEV-BE-2 | 4 | sub
Sub-task | Implementation — Export API (employees, contracts, org) | BE: Export API (employees, contracts, org) | DEV-BE-2 | 8 | sub
Sub-task | Unit + integration tests — Export API (employees, contracts, org) | BE: Export API (employees, contracts, org) | DEV-BE-2 | 4 | sub
Sub-task | Schema/migration — M10 admin scaffolding (users, roles, permissions routes) | BE: M10 admin scaffolding (users, roles, permissions routes) | DEV-BE-2 | 4 | sub
Sub-task | Implementation — M10 admin scaffolding (users, roles, permissions routes) | BE: M10 admin scaffolding (users, roles, permissions routes) | DEV-BE-2 | 10 | sub
Sub-task | Unit + integration tests — M10 admin scaffolding (users, roles, permissions routes) | BE: M10 admin scaffolding (users, roles, permissions routes) | DEV-BE-2 | 4 | sub
Sub-task | Component/page build — Bulk import wizard UI (upload → map → validate → commit) | FE: Bulk import wizard UI (upload → map → validate → commit) | DEV-FE-1 | 10 | sub
Sub-task | State wiring + form validation — Bulk import wizard UI (upload → map → validate → commit) | FE: Bulk import wizard UI (upload → map → validate → commit) | DEV-FE-1 | 4 | sub
Sub-task | E2E + a11y pass — Bulk import wizard UI (upload → map → validate → commit) | FE: Bulk import wizard UI (upload → map → validate → commit) | DEV-FE-1 | 3 | sub
Sub-task | Component/page build — Export UI (field selector + format picker) | FE: Export UI (field selector + format picker) | DEV-FE-1 | 10 | sub
Sub-task | State wiring + form validation — Export UI (field selector + format picker) | FE: Export UI (field selector + format picker) | DEV-FE-1 | 4 | sub
Sub-task | E2E + a11y pass — Export UI (field selector + format picker) | FE: Export UI (field selector + format picker) | DEV-FE-1 | 3 | sub
Sub-task | Component/page build — Employee profile enhancements (avatar upload + photo crop) | FE: Employee profile enhancements (avatar upload + photo crop) | DEV-FE-2 | 10 | sub
Sub-task | State wiring + form validation — Employee profile enhancements (avatar upload + photo crop) | FE: Employee profile enhancements (avatar upload + photo crop) | DEV-FE-2 | 4 | sub
Sub-task | E2E + a11y pass — Employee profile enhancements (avatar upload + photo crop) | FE: Employee profile enhancements (avatar upload + photo crop) | DEV-FE-2 | 3 | sub
Sub-task | Component/page build — Advanced search + saved filters | FE: Advanced search + saved filters | DEV-FE-2 | 10 | sub
Sub-task | State wiring + form validation — Advanced search + saved filters | FE: Advanced search + saved filters | DEV-FE-2 | 4 | sub
Sub-task | E2E + a11y pass — Advanced search + saved filters | FE: Advanced search + saved filters | DEV-FE-2 | 3 | sub
Sub-task | Component/page build — Home dashboard widgets (stats + recent events) | FE: Home dashboard widgets (stats + recent events) | DEV-FE-1 | 10 | sub
Sub-task | State wiring + form validation — Home dashboard widgets (stats + recent events) | FE: Home dashboard widgets (stats + recent events) | DEV-FE-1 | 4 | sub
Sub-task | E2E + a11y pass — Home dashboard widgets (stats + recent events) | FE: Home dashboard widgets (stats + recent events) | DEV-FE-1 | 3 | sub
Sub-task | Component/page build — M10 admin shell scaffolding (routes + empty pages) | FE: M10 admin shell scaffolding (routes + empty pages) | DEV-FE-2 | 8 | sub
Sub-task | State wiring + form validation — M10 admin shell scaffolding (routes + empty pages) | FE: M10 admin shell scaffolding (routes + empty pages) | DEV-FE-2 | 4 | sub
Sub-task | E2E + a11y pass — M10 admin shell scaffolding (routes + empty pages) | FE: M10 admin shell scaffolding (routes + empty pages) | DEV-FE-2 | 3 | sub
Sub-task | Test plan + cases — M1 full regression test suite + automation run | QA: M1 full regression test suite + automation run | QA-1 | 4 | sub
Sub-task | Automation scripts — M1 full regression test suite + automation run | QA: M1 full regression test suite + automation run | QA-1 | 16 | sub
Sub-task | Test plan + cases — Performance test baseline (k6 scenarios) | QA: Performance test baseline (k6 scenarios) | QA-1 | 4 | sub
Sub-task | Automation scripts — Performance test baseline (k6 scenarios) | QA: Performance test baseline (k6 scenarios) | QA-1 | 10 | sub
Sub-task | Figma build — M1 visual QA pass + polish tickets | DES: M1 visual QA pass + polish tickets | DES-1 | 6 | sub
Sub-task | Review + handoff — M1 visual QA pass + polish tickets | DES: M1 visual QA pass + polish tickets | DES-1 | 2 | sub
Sub-task | Schema/migration — Users admin CRUD API (invite/activate/deactivate) | BE: Users admin CRUD API (invite/activate/deactivate) | DEV-BE-1 | 4 | sub
Sub-task | Implementation — Users admin CRUD API (invite/activate/deactivate) | BE: Users admin CRUD API (invite/activate/deactivate) | DEV-BE-1 | 10 | sub
Sub-task | Unit + integration tests — Users admin CRUD API (invite/activate/deactivate) | BE: Users admin CRUD API (invite/activate/deactivate) | DEV-BE-1 | 4 | sub
Sub-task | Schema/migration — Roles CRUD API + default roles seed | BE: Roles CRUD API + default roles seed | DEV-BE-1 | 4 | sub
Sub-task | Implementation — Roles CRUD API + default roles seed | BE: Roles CRUD API + default roles seed | DEV-BE-1 | 10 | sub
Sub-task | Unit + integration tests — Roles CRUD API + default roles seed | BE: Roles CRUD API + default roles seed | DEV-BE-1 | 4 | sub
Sub-task | Schema/migration — Permissions matrix API (permissions × roles) | BE: Permissions matrix API (permissions × roles) | DEV-BE-1 | 4 | sub
Sub-task | Implementation — Permissions matrix API (permissions × roles) | BE: Permissions matrix API (permissions × roles) | DEV-BE-1 | 10 | sub
Sub-task | Unit + integration tests — Permissions matrix API (permissions × roles) | BE: Permissions matrix API (permissions × roles) | DEV-BE-1 | 4 | sub
Sub-task | Schema/migration — User-role assignment API (multi-role) | BE: User-role assignment API (multi-role) | DEV-BE-2 | 4 | sub
Sub-task | Implementation — User-role assignment API (multi-role) | BE: User-role assignment API (multi-role) | DEV-BE-2 | 8 | sub
Sub-task | Unit + integration tests — User-role assignment API (multi-role) | BE: User-role assignment API (multi-role) | DEV-BE-2 | 4 | sub
Sub-task | Component/page build — Users admin list + detail pages | FE: Users admin list + detail pages | DEV-FE-1 | 10 | sub
Sub-task | State wiring + form validation — Users admin list + detail pages | FE: Users admin list + detail pages | DEV-FE-1 | 4 | sub
Sub-task | E2E + a11y pass — Users admin list + detail pages | FE: Users admin list + detail pages | DEV-FE-1 | 3 | sub
Sub-task | Component/page build — Role editor (permissions matrix UI) | FE: Role editor (permissions matrix UI) | DEV-FE-1 | 16 | sub
Sub-task | State wiring + form validation — Role editor (permissions matrix UI) | FE: Role editor (permissions matrix UI) | DEV-FE-1 | 4 | sub
Sub-task | E2E + a11y pass — Role editor (permissions matrix UI) | FE: Role editor (permissions matrix UI) | DEV-FE-1 | 3 | sub
Sub-task | Component/page build — User create/edit form + invite flow | FE: User create/edit form + invite flow | DEV-FE-2 | 10 | sub
Sub-task | State wiring + form validation — User create/edit form + invite flow | FE: User create/edit form + invite flow | DEV-FE-2 | 4 | sub
Sub-task | E2E + a11y pass — User create/edit form + invite flow | FE: User create/edit form + invite flow | DEV-FE-2 | 3 | sub
Sub-task | Test plan + cases — Users/Roles/Permissions test cases | QA: Users/Roles/Permissions test cases | QA-1 | 4 | sub
Sub-task | Automation scripts — Users/Roles/Permissions test cases | QA: Users/Roles/Permissions test cases | QA-1 | 10 | sub
Sub-task | Test plan + cases — Permission enforcement across M1 endpoints | QA: Permission enforcement across M1 endpoints | QA-1 | 4 | sub
Sub-task | Automation scripts — Permission enforcement across M1 endpoints | QA: Permission enforcement across M1 endpoints | QA-1 | 8 | sub
Sub-task | Schema/migration — Tenant config endpoints (branding, locale, policies) | BE: Tenant config endpoints (branding, locale, policies) | DEV-BE-1 | 4 | sub
Sub-task | Implementation — Tenant config endpoints (branding, locale, policies) | BE: Tenant config endpoints (branding, locale, policies) | DEV-BE-1 | 10 | sub
Sub-task | Unit + integration tests — Tenant config endpoints (branding, locale, policies) | BE: Tenant config endpoints (branding, locale, policies) | DEV-BE-1 | 4 | sub
Sub-task | Schema/migration — Org chart bulk-edit API (reorder + bulk-move) | BE: Org chart bulk-edit API (reorder + bulk-move) | DEV-BE-1 | 4 | sub
Sub-task | Implementation — Org chart bulk-edit API (reorder + bulk-move) | BE: Org chart bulk-edit API (reorder + bulk-move) | DEV-BE-1 | 10 | sub
Sub-task | Unit + integration tests — Org chart bulk-edit API (reorder + bulk-move) | BE: Org chart bulk-edit API (reorder + bulk-move) | DEV-BE-1 | 4 | sub
Sub-task | Schema/migration — Holiday calendar management API | BE: Holiday calendar management API | DEV-BE-2 | 4 | sub
Sub-task | Implementation — Holiday calendar management API | BE: Holiday calendar management API | DEV-BE-2 | 8 | sub
Sub-task | Unit + integration tests — Holiday calendar management API | BE: Holiday calendar management API | DEV-BE-2 | 4 | sub
Sub-task | Schema/migration — Notification template management API | BE: Notification template management API | DEV-BE-2 | 4 | sub
Sub-task | Implementation — Notification template management API | BE: Notification template management API | DEV-BE-2 | 8 | sub
Sub-task | Unit + integration tests — Notification template management API | BE: Notification template management API | DEV-BE-2 | 4 | sub
Sub-task | Component/page build — Tenant settings page (branding + locale + policies) | FE: Tenant settings page (branding + locale + policies) | DEV-FE-2 | 16 | sub
Sub-task | State wiring + form validation — Tenant settings page (branding + locale + policies) | FE: Tenant settings page (branding + locale + policies) | DEV-FE-2 | 4 | sub
Sub-task | E2E + a11y pass — Tenant settings page (branding + locale + policies) | FE: Tenant settings page (branding + locale + policies) | DEV-FE-2 | 3 | sub
Sub-task | Component/page build — Org chart admin UI (bulk edit + dry-run preview) | FE: Org chart admin UI (bulk edit + dry-run preview) | DEV-FE-1 | 16 | sub
Sub-task | State wiring + form validation — Org chart admin UI (bulk edit + dry-run preview) | FE: Org chart admin UI (bulk edit + dry-run preview) | DEV-FE-1 | 4 | sub
Sub-task | E2E + a11y pass — Org chart admin UI (bulk edit + dry-run preview) | FE: Org chart admin UI (bulk edit + dry-run preview) | DEV-FE-1 | 3 | sub
Sub-task | Component/page build — Holiday calendar admin UI | FE: Holiday calendar admin UI | DEV-FE-1 | 10 | sub
Sub-task | State wiring + form validation — Holiday calendar admin UI | FE: Holiday calendar admin UI | DEV-FE-1 | 4 | sub
Sub-task | E2E + a11y pass — Holiday calendar admin UI | FE: Holiday calendar admin UI | DEV-FE-1 | 3 | sub
Sub-task | Component/page build — Notification template editor (with variable picker) | FE: Notification template editor (with variable picker) | DEV-FE-2 | 10 | sub
Sub-task | State wiring + form validation — Notification template editor (with variable picker) | FE: Notification template editor (with variable picker) | DEV-FE-2 | 4 | sub
Sub-task | E2E + a11y pass — Notification template editor (with variable picker) | FE: Notification template editor (with variable picker) | DEV-FE-2 | 3 | sub
Sub-task | Test plan + cases — Tenant config + org admin test cases | QA: Tenant config + org admin test cases | QA-1 | 4 | sub
Sub-task | Automation scripts — Tenant config + org admin test cases | QA: Tenant config + org admin test cases | QA-1 | 6 | sub
Sub-task | Schema/migration — Audit log search + filter + full-text API | BE: Audit log search + filter + full-text API | DEV-BE-1 | 4 | sub
Sub-task | Implementation — Audit log search + filter + full-text API | BE: Audit log search + filter + full-text API | DEV-BE-1 | 10 | sub
Sub-task | Unit + integration tests — Audit log search + filter + full-text API | BE: Audit log search + filter + full-text API | DEV-BE-1 | 4 | sub
Sub-task | Schema/migration — Audit log export API (CSV streaming) | BE: Audit log export API (CSV streaming) | DEV-BE-1 | 4 | sub
Sub-task | Implementation — Audit log export API (CSV streaming) | BE: Audit log export API (CSV streaming) | DEV-BE-1 | 8 | sub
Sub-task | Unit + integration tests — Audit log export API (CSV streaming) | BE: Audit log export API (CSV streaming) | DEV-BE-1 | 4 | sub
Sub-task | Schema/migration — Integration registry API (configured integrations) | BE: Integration registry API (configured integrations) | DEV-BE-2 | 4 | sub
Sub-task | Implementation — Integration registry API (configured integrations) | BE: Integration registry API (configured integrations) | DEV-BE-2 | 10 | sub
Sub-task | Unit + integration tests — Integration registry API (configured integrations) | BE: Integration registry API (configured integrations) | DEV-BE-2 | 4 | sub
Sub-task | Schema/migration — Webhook configuration API + dispatcher | BE: Webhook configuration API + dispatcher | DEV-BE-2 | 4 | sub
Sub-task | Implementation — Webhook configuration API + dispatcher | BE: Webhook configuration API + dispatcher | DEV-BE-2 | 8 | sub
Sub-task | Unit + integration tests — Webhook configuration API + dispatcher | BE: Webhook configuration API + dispatcher | DEV-BE-2 | 4 | sub
Sub-task | Schema/migration — API token management (create/revoke/rotate) | BE: API token management (create/revoke/rotate) | DEV-BE-1 | 4 | sub
Sub-task | Implementation — API token management (create/revoke/rotate) | BE: API token management (create/revoke/rotate) | DEV-BE-1 | 10 | sub
Sub-task | Unit + integration tests — API token management (create/revoke/rotate) | BE: API token management (create/revoke/rotate) | DEV-BE-1 | 4 | sub
Sub-task | Component/page build — Audit log dashboard (filters + timeline + drill-down) | FE: Audit log dashboard (filters + timeline + drill-down) | DEV-FE-1 | 16 | sub
Sub-task | State wiring + form validation — Audit log dashboard (filters + timeline + drill-down) | FE: Audit log dashboard (filters + timeline + drill-down) | DEV-FE-1 | 4 | sub
Sub-task | E2E + a11y pass — Audit log dashboard (filters + timeline + drill-down) | FE: Audit log dashboard (filters + timeline + drill-down) | DEV-FE-1 | 3 | sub
Sub-task | Component/page build — Integrations config page | FE: Integrations config page | DEV-FE-1 | 10 | sub
Sub-task | State wiring + form validation — Integrations config page | FE: Integrations config page | DEV-FE-1 | 4 | sub
Sub-task | E2E + a11y pass — Integrations config page | FE: Integrations config page | DEV-FE-1 | 3 | sub
Sub-task | Component/page build — Webhook configuration UI | FE: Webhook configuration UI | DEV-FE-2 | 10 | sub
Sub-task | State wiring + form validation — Webhook configuration UI | FE: Webhook configuration UI | DEV-FE-2 | 4 | sub
Sub-task | E2E + a11y pass — Webhook configuration UI | FE: Webhook configuration UI | DEV-FE-2 | 3 | sub
Sub-task | Component/page build — API token management UI | FE: API token management UI | DEV-FE-2 | 8 | sub
Sub-task | State wiring + form validation — API token management UI | FE: API token management UI | DEV-FE-2 | 4 | sub
Sub-task | E2E + a11y pass — API token management UI | FE: API token management UI | DEV-FE-2 | 3 | sub
Sub-task | Test plan + cases — Audit + integrations + webhooks test cases | QA: Audit + integrations + webhooks test cases | QA-1 | 4 | sub
Sub-task | Automation scripts — Audit + integrations + webhooks test cases | QA: Audit + integrations + webhooks test cases | QA-1 | 6 | sub
Sub-task | Schema/migration — Security review fixes — round 1 (OWASP top 10) | BE: Security review fixes — round 1 (OWASP top 10) | DEV-BE-1 | 4 | sub
Sub-task | Implementation — Security review fixes — round 1 (OWASP top 10) | BE: Security review fixes — round 1 (OWASP top 10) | DEV-BE-1 | 16 | sub
Sub-task | Unit + integration tests — Security review fixes — round 1 (OWASP top 10) | BE: Security review fixes — round 1 (OWASP top 10) | DEV-BE-1 | 4 | sub
Sub-task | Schema/migration — Performance tuning — hot endpoints + caching | BE: Performance tuning — hot endpoints + caching | DEV-BE-2 | 4 | sub
Sub-task | Implementation — Performance tuning — hot endpoints + caching | BE: Performance tuning — hot endpoints + caching | DEV-BE-2 | 16 | sub
Sub-task | Unit + integration tests — Performance tuning — hot endpoints + caching | BE: Performance tuning — hot endpoints + caching | DEV-BE-2 | 4 | sub
Sub-task | Component/page build — Bundle size optimization + tree-shaking audit | FE: Bundle size optimization + tree-shaking audit | DEV-FE-1 | 10 | sub
Sub-task | State wiring + form validation — Bundle size optimization + tree-shaking audit | FE: Bundle size optimization + tree-shaking audit | DEV-FE-1 | 4 | sub
Sub-task | E2E + a11y pass — Bundle size optimization + tree-shaking audit | FE: Bundle size optimization + tree-shaking audit | DEV-FE-1 | 3 | sub
Sub-task | Component/page build — Lazy-loading + route-level code-splitting | FE: Lazy-loading + route-level code-splitting | DEV-FE-1 | 10 | sub
Sub-task | State wiring + form validation — Lazy-loading + route-level code-splitting | FE: Lazy-loading + route-level code-splitting | DEV-FE-1 | 4 | sub
Sub-task | E2E + a11y pass — Lazy-loading + route-level code-splitting | FE: Lazy-loading + route-level code-splitting | DEV-FE-1 | 3 | sub
Sub-task | Component/page build — Accessibility (a11y) pass — M1 | FE: Accessibility (a11y) pass — M1 | DEV-FE-2 | 10 | sub
Sub-task | State wiring + form validation — Accessibility (a11y) pass — M1 | FE: Accessibility (a11y) pass — M1 | DEV-FE-2 | 4 | sub
Sub-task | E2E + a11y pass — Accessibility (a11y) pass — M1 | FE: Accessibility (a11y) pass — M1 | DEV-FE-2 | 3 | sub
Sub-task | Component/page build — Accessibility (a11y) pass — M10 | FE: Accessibility (a11y) pass — M10 | DEV-FE-2 | 10 | sub
Sub-task | State wiring + form validation — Accessibility (a11y) pass — M10 | FE: Accessibility (a11y) pass — M10 | DEV-FE-2 | 4 | sub
Sub-task | E2E + a11y pass — Accessibility (a11y) pass — M10 | FE: Accessibility (a11y) pass — M10 | DEV-FE-2 | 3 | sub
Sub-task | Test plan + cases — Full regression run round 1 + defect report | QA: Full regression run round 1 + defect report | QA-1 | 4 | sub
Sub-task | Automation scripts — Full regression run round 1 + defect report | QA: Full regression run round 1 + defect report | QA-1 | 16 | sub
Sub-task | Schema/migration — Staging perf baseline + SLO report | DEVOPS: Staging perf baseline + SLO report | DEV-BE-2 | 4 | sub
Sub-task | Implementation — Staging perf baseline + SLO report | DEVOPS: Staging perf baseline + SLO report | DEV-BE-2 | 8 | sub
Sub-task | Unit + integration tests — Staging perf baseline + SLO report | DEVOPS: Staging perf baseline + SLO report | DEV-BE-2 | 4 | sub
Sub-task | Schema/migration — Load testing scenarios + k6 scripts | BE: Load testing scenarios + k6 scripts | DEV-BE-1 | 4 | sub
Sub-task | Implementation — Load testing scenarios + k6 scripts | BE: Load testing scenarios + k6 scripts | DEV-BE-1 | 10 | sub
Sub-task | Unit + integration tests — Load testing scenarios + k6 scripts | BE: Load testing scenarios + k6 scripts | DEV-BE-1 | 4 | sub
Sub-task | Schema/migration — Load-test fixes + scaling policy tuning | BE: Load-test fixes + scaling policy tuning | DEV-BE-2 | 4 | sub
Sub-task | Implementation — Load-test fixes + scaling policy tuning | BE: Load-test fixes + scaling policy tuning | DEV-BE-2 | 10 | sub
Sub-task | Unit + integration tests — Load-test fixes + scaling policy tuning | BE: Load-test fixes + scaling policy tuning | DEV-BE-2 | 4 | sub
Sub-task | Schema/migration — Security scan fixes (OWASP + CVE backlog) | BE: Security scan fixes (OWASP + CVE backlog) | DEV-BE-1 | 4 | sub
Sub-task | Implementation — Security scan fixes (OWASP + CVE backlog) | BE: Security scan fixes (OWASP + CVE backlog) | DEV-BE-1 | 16 | sub
Sub-task | Unit + integration tests — Security scan fixes (OWASP + CVE backlog) | BE: Security scan fixes (OWASP + CVE backlog) | DEV-BE-1 | 4 | sub
Sub-task | Schema/migration — Secrets rotation + vault setup | BE: Secrets rotation + vault setup | DEV-BE-2 | 4 | sub
Sub-task | Implementation — Secrets rotation + vault setup | BE: Secrets rotation + vault setup | DEV-BE-2 | 10 | sub
Sub-task | Unit + integration tests — Secrets rotation + vault setup | BE: Secrets rotation + vault setup | DEV-BE-2 | 4 | sub
Sub-task | Schema/migration — DR backup + restore testing | BE: DR backup + restore testing | DEV-BE-1 | 4 | sub
Sub-task | Implementation — DR backup + restore testing | BE: DR backup + restore testing | DEV-BE-1 | 10 | sub
Sub-task | Unit + integration tests — DR backup + restore testing | BE: DR backup + restore testing | DEV-BE-1 | 4 | sub
Sub-task | Component/page build — XSS/CSRF hardening audit | FE: XSS/CSRF hardening audit | DEV-FE-1 | 10 | sub
Sub-task | State wiring + form validation — XSS/CSRF hardening audit | FE: XSS/CSRF hardening audit | DEV-FE-1 | 4 | sub
Sub-task | E2E + a11y pass — XSS/CSRF hardening audit | FE: XSS/CSRF hardening audit | DEV-FE-1 | 3 | sub
Sub-task | Component/page build — CSP headers + SRI for external scripts | FE: CSP headers + SRI for external scripts | DEV-FE-2 | 8 | sub
Sub-task | State wiring + form validation — CSP headers + SRI for external scripts | FE: CSP headers + SRI for external scripts | DEV-FE-2 | 4 | sub
Sub-task | E2E + a11y pass — CSP headers + SRI for external scripts | FE: CSP headers + SRI for external scripts | DEV-FE-2 | 3 | sub
Sub-task | Schema/migration — DR runbook + full DR drill | DEVOPS: DR runbook + full DR drill | DEV-BE-2 | 4 | sub
Sub-task | Implementation — DR runbook + full DR drill | DEVOPS: DR runbook + full DR drill | DEV-BE-2 | 10 | sub
Sub-task | Unit + integration tests — DR runbook + full DR drill | DEVOPS: DR runbook + full DR drill | DEV-BE-2 | 4 | sub
Sub-task | Test plan + cases — Load-test results + signoff report | QA: Load-test results + signoff report | QA-1 | 4 | sub
Sub-task | Automation scripts — Load-test results + signoff report | QA: Load-test results + signoff report | QA-1 | 6 | sub
Sub-task | Schema/migration — Pen-test fixes — critical severity | BE: Pen-test fixes — critical severity | DEV-BE-1 | 4 | sub
Sub-task | Implementation — Pen-test fixes — critical severity | BE: Pen-test fixes — critical severity | DEV-BE-1 | 16 | sub
Sub-task | Unit + integration tests — Pen-test fixes — critical severity | BE: Pen-test fixes — critical severity | DEV-BE-1 | 4 | sub
Sub-task | Schema/migration — Pen-test fixes — major severity | BE: Pen-test fixes — major severity | DEV-BE-2 | 4 | sub
Sub-task | Implementation — Pen-test fixes — major severity | BE: Pen-test fixes — major severity | DEV-BE-2 | 10 | sub
Sub-task | Unit + integration tests — Pen-test fixes — major severity | BE: Pen-test fixes — major severity | DEV-BE-2 | 4 | sub
Sub-task | Schema/migration — Pen-test fixes — minor + hardening | BE: Pen-test fixes — minor + hardening | DEV-BE-1 | 4 | sub
Sub-task | Implementation — Pen-test fixes — minor + hardening | BE: Pen-test fixes — minor + hardening | DEV-BE-1 | 8 | sub
Sub-task | Unit + integration tests — Pen-test fixes — minor + hardening | BE: Pen-test fixes — minor + hardening | DEV-BE-1 | 4 | sub
Sub-task | Schema/migration — Data migration script — employees | BE: Data migration script — employees | DEV-BE-2 | 4 | sub
Sub-task | Implementation — Data migration script — employees | BE: Data migration script — employees | DEV-BE-2 | 10 | sub
Sub-task | Unit + integration tests — Data migration script — employees | BE: Data migration script — employees | DEV-BE-2 | 4 | sub
Sub-task | Schema/migration — Data migration script — org structure + positions | BE: Data migration script — org structure + positions | DEV-BE-2 | 4 | sub
Sub-task | Implementation — Data migration script — org structure + positions | BE: Data migration script — org structure + positions | DEV-BE-2 | 8 | sub
Sub-task | Unit + integration tests — Data migration script — org structure + positions | BE: Data migration script — org structure + positions | DEV-BE-2 | 4 | sub
Sub-task | Schema/migration — Data migration script — contracts + documents | BE: Data migration script — contracts + documents | DEV-BE-1 | 4 | sub
Sub-task | Implementation — Data migration script — contracts + documents | BE: Data migration script — contracts + documents | DEV-BE-1 | 8 | sub
Sub-task | Unit + integration tests — Data migration script — contracts + documents | BE: Data migration script — contracts + documents | DEV-BE-1 | 4 | sub
Sub-task | Schema/migration — Data migration dry-run 1 (staging) | BE: Data migration dry-run 1 (staging) | DEV-BE-2 | 4 | sub
Sub-task | Implementation — Data migration dry-run 1 (staging) | BE: Data migration dry-run 1 (staging) | DEV-BE-2 | 10 | sub
Sub-task | Unit + integration tests — Data migration dry-run 1 (staging) | BE: Data migration dry-run 1 (staging) | DEV-BE-2 | 4 | sub
Sub-task | Schema/migration — Data migration dry-run 2 (staging, post-fix) | BE: Data migration dry-run 2 (staging, post-fix) | DEV-BE-1 | 4 | sub
Sub-task | Implementation — Data migration dry-run 2 (staging, post-fix) | BE: Data migration dry-run 2 (staging, post-fix) | DEV-BE-1 | 10 | sub
Sub-task | Unit + integration tests — Data migration dry-run 2 (staging, post-fix) | BE: Data migration dry-run 2 (staging, post-fix) | DEV-BE-1 | 4 | sub
Sub-task | Test plan + cases — Pen-test fix verification | QA: Pen-test fix verification | QA-1 | 4 | sub
Sub-task | Automation scripts — Pen-test fix verification | QA: Pen-test fix verification | QA-1 | 10 | sub
Sub-task | Test plan + cases — Migration dry-run verification + checksums | QA: Migration dry-run verification + checksums | QA-1 | 4 | sub
Sub-task | Automation scripts — Migration dry-run verification + checksums | QA: Migration dry-run verification + checksums | QA-1 | 6 | sub
Sub-task | Research / draft — UAT scenarios drafted (happy + edge paths) | PO: UAT scenarios drafted (happy + edge paths) | PO | 4 | sub
Sub-task | Review + finalize — UAT scenarios drafted (happy + edge paths) | PO: UAT scenarios drafted (happy + edge paths) | PO | 2 | sub
Sub-task | Research / draft — UAT test data prepared (anonymized + seeded) | PO: UAT test data prepared (anonymized + seeded) | PO | 4 | sub
Sub-task | Review + finalize — UAT test data prepared (anonymized + seeded) | PO: UAT test data prepared (anonymized + seeded) | PO | 2 | sub
Sub-task | Research / draft — UAT stakeholder onboarding session | PO: UAT stakeholder onboarding session | PO | 4 | sub
Sub-task | Review + finalize — UAT stakeholder onboarding session | PO: UAT stakeholder onboarding session | PO | 2 | sub
Sub-task | Test plan + cases — UAT test plan (scoring rubric + defect flow) | QA: UAT test plan (scoring rubric + defect flow) | QA-1 | 4 | sub
Sub-task | Automation scripts — UAT test plan (scoring rubric + defect flow) | QA: UAT test plan (scoring rubric + defect flow) | QA-1 | 10 | sub
Sub-task | Test plan + cases — UAT environment smoke test + seeding | QA: UAT environment smoke test + seeding | QA-1 | 4 | sub
Sub-task | Automation scripts — UAT environment smoke test + seeding | QA: UAT environment smoke test + seeding | QA-1 | 6 | sub
Sub-task | Schema/migration — Hotfix pipeline + feature-flag framework | BE: Hotfix pipeline + feature-flag framework | DEV-BE-1 | 4 | sub
Sub-task | Implementation — Hotfix pipeline + feature-flag framework | BE: Hotfix pipeline + feature-flag framework | DEV-BE-1 | 10 | sub
Sub-task | Unit + integration tests — Hotfix pipeline + feature-flag framework | BE: Hotfix pipeline + feature-flag framework | DEV-BE-1 | 4 | sub
Sub-task | Component/page build — In-app help + user guide content (embedded) | FE: In-app help + user guide content (embedded) | DEV-FE-1 | 8 | sub
Sub-task | State wiring + form validation — In-app help + user guide content (embedded) | FE: In-app help + user guide content (embedded) | DEV-FE-1 | 4 | sub
Sub-task | E2E + a11y pass — In-app help + user guide content (embedded) | FE: In-app help + user guide content (embedded) | DEV-FE-1 | 3 | sub
Sub-task | Schema/migration — Production environment hardening | DEVOPS: Production environment hardening | DEV-BE-2 | 4 | sub
Sub-task | Implementation — Production environment hardening | DEVOPS: Production environment hardening | DEV-BE-2 | 8 | sub
Sub-task | Unit + integration tests — Production environment hardening | DEVOPS: Production environment hardening | DEV-BE-2 | 4 | sub
Sub-task | Test plan + cases — UAT round 1 — execution + defect intake | QA: UAT round 1 — execution + defect intake | QA-1 | 4 | sub
Sub-task | Automation scripts — UAT round 1 — execution + defect intake | QA: UAT round 1 — execution + defect intake | QA-1 | 10 | sub
Sub-task | Test plan + cases — UAT round 1 — defect triage + assignment | QA: UAT round 1 — defect triage + assignment | QA-1 | 4 | sub
Sub-task | Automation scripts — UAT round 1 — defect triage + assignment | QA: UAT round 1 — defect triage + assignment | QA-1 | 10 | sub
Sub-task | Schema/migration — UAT round 1 — fixes backlog burndown | BE: UAT round 1 — fixes backlog burndown | DEV-BE-1 | 4 | sub
Sub-task | Implementation — UAT round 1 — fixes backlog burndown | BE: UAT round 1 — fixes backlog burndown | DEV-BE-1 | 16 | sub
Sub-task | Unit + integration tests — UAT round 1 — fixes backlog burndown | BE: UAT round 1 — fixes backlog burndown | DEV-BE-1 | 4 | sub
Sub-task | Component/page build — UAT round 1 — fixes backlog burndown | FE: UAT round 1 — fixes backlog burndown | DEV-FE-1 | 16 | sub
Sub-task | State wiring + form validation — UAT round 1 — fixes backlog burndown | FE: UAT round 1 — fixes backlog burndown | DEV-FE-1 | 4 | sub
Sub-task | E2E + a11y pass — UAT round 1 — fixes backlog burndown | FE: UAT round 1 — fixes backlog burndown | DEV-FE-1 | 3 | sub
Sub-task | Research / draft — Stakeholder feedback synthesis + go/no-go R1 | PO: Stakeholder feedback synthesis + go/no-go R1 | PO | 4 | sub
Sub-task | Review + finalize — Stakeholder feedback synthesis + go/no-go R1 | PO: Stakeholder feedback synthesis + go/no-go R1 | PO | 2 | sub
Sub-task | Test plan + cases — UAT round 2 — execution + regression | QA: UAT round 2 — execution + regression | QA-1 | 4 | sub
Sub-task | Automation scripts — UAT round 2 — execution + regression | QA: UAT round 2 — execution + regression | QA-1 | 10 | sub
Sub-task | Schema/migration — UAT round 2 — fixes | BE: UAT round 2 — fixes | DEV-BE-2 | 4 | sub
Sub-task | Implementation — UAT round 2 — fixes | BE: UAT round 2 — fixes | DEV-BE-2 | 10 | sub
Sub-task | Unit + integration tests — UAT round 2 — fixes | BE: UAT round 2 — fixes | DEV-BE-2 | 4 | sub
Sub-task | Component/page build — UAT round 2 — fixes | FE: UAT round 2 — fixes | DEV-FE-2 | 10 | sub
Sub-task | State wiring + form validation — UAT round 2 — fixes | FE: UAT round 2 — fixes | DEV-FE-2 | 4 | sub
Sub-task | E2E + a11y pass — UAT round 2 — fixes | FE: UAT round 2 — fixes | DEV-FE-2 | 3 | sub
Sub-task | Research / draft — Training content — admin users (M10) | PO: Training content — admin users (M10) | PO | 4 | sub
Sub-task | Review + finalize — Training content — admin users (M10) | PO: Training content — admin users (M10) | PO | 2 | sub
Sub-task | Research / draft — Training content — end users (M1) | PO: Training content — end users (M1) | PO | 4 | sub
Sub-task | Review + finalize — Training content — end users (M1) | PO: Training content — end users (M1) | PO | 2 | sub
Sub-task | Figma build — Training visuals (screenshots + diagrams) | DES: Training visuals (screenshots + diagrams) | DES-1 | 6 | sub
Sub-task | Review + handoff — Training visuals (screenshots + diagrams) | DES: Training visuals (screenshots + diagrams) | DES-1 | 2 | sub
Sub-task | Test plan + cases — UAT round 3 — final regression + acceptance | QA: UAT round 3 — final regression + acceptance | QA-1 | 4 | sub
Sub-task | Automation scripts — UAT round 3 — final regression + acceptance | QA: UAT round 3 — final regression + acceptance | QA-1 | 10 | sub
Sub-task | Schema/migration — UAT round 3 — final fixes | BE: UAT round 3 — final fixes | DEV-BE-1 | 4 | sub
Sub-task | Implementation — UAT round 3 — final fixes | BE: UAT round 3 — final fixes | DEV-BE-1 | 10 | sub
Sub-task | Unit + integration tests — UAT round 3 — final fixes | BE: UAT round 3 — final fixes | DEV-BE-1 | 4 | sub
Sub-task | Component/page build — UAT round 3 — final fixes | FE: UAT round 3 — final fixes | DEV-FE-1 | 10 | sub
Sub-task | State wiring + form validation — UAT round 3 — final fixes | FE: UAT round 3 — final fixes | DEV-FE-1 | 4 | sub
Sub-task | E2E + a11y pass — UAT round 3 — final fixes | FE: UAT round 3 — final fixes | DEV-FE-1 | 3 | sub
Sub-task | Schema/migration — Cutover rehearsal 1 (staging-as-prod) | DEVOPS: Cutover rehearsal 1 (staging-as-prod) | DEV-BE-2 | 4 | sub
Sub-task | Implementation — Cutover rehearsal 1 (staging-as-prod) | DEVOPS: Cutover rehearsal 1 (staging-as-prod) | DEV-BE-2 | 10 | sub
Sub-task | Unit + integration tests — Cutover rehearsal 1 (staging-as-prod) | DEVOPS: Cutover rehearsal 1 (staging-as-prod) | DEV-BE-2 | 4 | sub
Sub-task | Schema/migration — Cutover rehearsal 2 (full team) | DEVOPS: Cutover rehearsal 2 (full team) | DEV-BE-2 | 4 | sub
Sub-task | Implementation — Cutover rehearsal 2 (full team) | DEVOPS: Cutover rehearsal 2 (full team) | DEV-BE-2 | 10 | sub
Sub-task | Unit + integration tests — Cutover rehearsal 2 (full team) | DEVOPS: Cutover rehearsal 2 (full team) | DEV-BE-2 | 4 | sub
Sub-task | Test plan + cases — Final regression run + exit-criteria report | QA: Final regression run + exit-criteria report | QA-1 | 4 | sub
Sub-task | Automation scripts — Final regression run + exit-criteria report | QA: Final regression run + exit-criteria report | QA-1 | 6 | sub
Sub-task | Schema/migration — Last-mile fixes + production config freeze | BE: Last-mile fixes + production config freeze | DEV-BE-1 | 4 | sub
Sub-task | Implementation — Last-mile fixes + production config freeze | BE: Last-mile fixes + production config freeze | DEV-BE-1 | 10 | sub
Sub-task | Unit + integration tests — Last-mile fixes + production config freeze | BE: Last-mile fixes + production config freeze | DEV-BE-1 | 4 | sub
Sub-task | Component/page build — Last-mile fixes + production build verified | FE: Last-mile fixes + production build verified | DEV-FE-1 | 10 | sub
Sub-task | State wiring + form validation — Last-mile fixes + production build verified | FE: Last-mile fixes + production build verified | DEV-FE-1 | 4 | sub
Sub-task | E2E + a11y pass — Last-mile fixes + production build verified | FE: Last-mile fixes + production build verified | DEV-FE-1 | 3 | sub
Sub-task | Schema/migration — Production deployment checklist | DEVOPS: Production deployment checklist | DEV-BE-2 | 4 | sub
Sub-task | Implementation — Production deployment checklist | DEVOPS: Production deployment checklist | DEV-BE-2 | 8 | sub
Sub-task | Unit + integration tests — Production deployment checklist | DEVOPS: Production deployment checklist | DEV-BE-2 | 4 | sub
Sub-task | Schema/migration — Rollback plan + rehearsal | DEVOPS: Rollback plan + rehearsal | DEV-BE-2 | 4 | sub
Sub-task | Implementation — Rollback plan + rehearsal | DEVOPS: Rollback plan + rehearsal | DEV-BE-2 | 10 | sub
Sub-task | Unit + integration tests — Rollback plan + rehearsal | DEVOPS: Rollback plan + rehearsal | DEV-BE-2 | 4 | sub
Sub-task | Research / draft — Go-live comms plan (internal + external) | PO: Go-live comms plan (internal + external) | PO | 4 | sub
Sub-task | Review + finalize — Go-live comms plan (internal + external) | PO: Go-live comms plan (internal + external) | PO | 2 | sub
Sub-task | Schema/migration — Production cutover — execute deployment | DEVOPS: Production cutover — execute deployment | DEV-BE-2 | 4 | sub
Sub-task | Implementation — Production cutover — execute deployment | DEVOPS: Production cutover — execute deployment | DEV-BE-2 | 16 | sub
Sub-task | Unit + integration tests — Production cutover — execute deployment | DEVOPS: Production cutover — execute deployment | DEV-BE-2 | 4 | sub
Sub-task | Schema/migration — DNS + traffic cutover | DEVOPS: DNS + traffic cutover | DEV-BE-1 | 4 | sub
Sub-task | Implementation — DNS + traffic cutover | DEVOPS: DNS + traffic cutover | DEV-BE-1 | 8 | sub
Sub-task | Unit + integration tests — DNS + traffic cutover | DEVOPS: DNS + traffic cutover | DEV-BE-1 | 4 | sub
Sub-task | Test plan + cases — Post-cutover smoke tests (prod) | QA: Post-cutover smoke tests (prod) | QA-1 | 4 | sub
Sub-task | Automation scripts — Post-cutover smoke tests (prod) | QA: Post-cutover smoke tests (prod) | QA-1 | 6 | sub
Sub-task | Schema/migration — Day-1 hotfix support (on-call) | BE: Day-1 hotfix support (on-call) | DEV-BE-1 | 4 | sub
Sub-task | Implementation — Day-1 hotfix support (on-call) | BE: Day-1 hotfix support (on-call) | DEV-BE-1 | 10 | sub
Sub-task | Unit + integration tests — Day-1 hotfix support (on-call) | BE: Day-1 hotfix support (on-call) | DEV-BE-1 | 4 | sub
Sub-task | Component/page build — Day-1 hotfix support (on-call) | FE: Day-1 hotfix support (on-call) | DEV-FE-1 | 8 | sub
Sub-task | State wiring + form validation — Day-1 hotfix support (on-call) | FE: Day-1 hotfix support (on-call) | DEV-FE-1 | 4 | sub
Sub-task | E2E + a11y pass — Day-1 hotfix support (on-call) | FE: Day-1 hotfix support (on-call) | DEV-FE-1 | 3 | sub
Sub-task | Research / draft — Go-live retrospective (what went well / improve) | PO: Go-live retrospective (what went well / improve) | PO | 4 | sub
Sub-task | Review + finalize — Go-live retrospective (what went well / improve) | PO: Go-live retrospective (what went well / improve) | PO | 2 | sub

## Workload
Workload — Story Points per person per sprint (formula-driven from Stories sheet)
Formulas use SUMIFS on Stories sheet. Target: ≤14 SP per dev per sprint; DES ≤7 (50% FTE).
Assignee / Sprint | S0 | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | Total
DEV-FE-1 | 3 | 3 | 0 | 5 | 8 | 13 | 13 | 13 | 15 | 13 | 15 | 13 | 13 | 13 | 10 | 5 | 0 | 3 | 8 | 0 | 5 | 5 | 3 | 179
DEV-FE-2 | 3 | 0 | 0 | 5 | 3 | 11 | 16 | 15 | 15 | 13 | 13 | 5 | 13 | 8 | 10 | 3 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 138
DEV-BE-1 | 7 | 5 | 3 | 3 | 18 | 8 | 13 | 15 | 15 | 13 | 8 | 15 | 10 | 13 | 8 | 18 | 19 | 5 | 8 | 0 | 5 | 5 | 8 | 222
DEV-BE-2 | 5 | 5 | 3 | 3 | 18 | 6 | 16 | 13 | 13 | 13 | 13 | 3 | 6 | 8 | 11 | 15 | 18 | 3 | 0 | 5 | 10 | 8 | 8 | 203
QA-1 | 2 | 3 | 0 | 8 | 5 | 5 | 8 | 5 | 5 | 9 | 13 | 9 | 3 | 3 | 8 | 3 | 8 | 8 | 10 | 5 | 8 | 2 | 3 | 133
TL | 0 | 6 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14
DES-1 | 0 | 10 | 20 | 15 | 5 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 0 | 0 | 0 | 57
PO | 0 | 6 | 9 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 3 | 12 | 2 | 5 | 3 | 53
TEAM TOTAL | 20 | 38 | 43 | 41 | 57 | 43 | 66 | 61 | 63 | 61 | 65 | 45 | 45 | 45 | 47 | 44 | 45 | 30 | 30 | 30 | 30 | 25 | 25 | 999

## Bug-Log
Bug log — Jira CSV-ready bug tracker (log defects here; bulk-import into PRX)
Workflow: Open → Triaged → In Progress → In Review → Ready QA → Verified → Closed. SLA: P0 same-day · P1 within sprint · P2 next sprint · P3 quarterly · P4 backlog.
Issue Type | Summary | Environment | Steps to reproduce | Expected | Actual | Severity | Priority | Component | Labels | Linked Story (Epic Link or Story key) | Reporter
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug
Bug | [8 empty] | bug

## Capacity-Check
Capacity check — sprint-by-sprint utilisation vs target
Planned SP = sum from Stories sheet. Capacity SP = Sprints sheet target. Utilisation = planned ÷ capacity. Target ≤95%. Over 100% = over-allocated.
Sprint | Phase gate | Goal | Planned SP | Capacity SP | Utilisation %
S0 | P0 close / Kick-off | Team onboarded, environments ready, CI/CD green, design system scaffold | 20 | 20 | 100%
S1 | P1 Discover | Discovery M1 — employee records & org structure flow | 38 | 35 | 108.6%
S2 | P1 Discover | Discovery M1 — positions & contracts + M10 discovery | 43 | 45 | 95.56%
S3 | P1→P2 Design | Design system complete + all M1 wireframes signed off | 41 | 50 | 82%
S4 | P2 Foundations | Tenancy model + SSO + RBAC scaffold | 57 | 56 | 101.8%
S5 | P2 Foundations | Audit log + platform shell + nav | 43 | 56 | 76.79%
S6 | P3 Core Build | Employee records CRUD + search + data model in place | 66 | 56 | 117.9%
S7 | P3 Core Build | Org structure + positions + assignment | 61 | 56 | 108.9%
S8 | P3 Core Build | Contracts + documents vault + signed URLs | 63 | 56 | 112.5%
S9 | P3 Core Build | Lifecycle events + approvals engine + notifications | 61 | 56 | 108.9%
S10 | P3→P4 | M1 polish + bulk import/export + M10 scaffold | 65 | 56 | 116.1%
S11 | P4 Adjacent | M10 users, roles, permissions admin | 45 | 56 | 80.36%
S12 | P4 Adjacent | M10 tenant config + org chart admin + holiday calendar | 45 | 56 | 80.36%
S13 | P4 Adjacent | M10 audit dashboard + integrations + webhooks + API tokens | 45 | 56 | 80.36%
S14 | P4→P5 | Feature-freeze — a11y + bundle + perf optimizations | 47 | 56 | 83.93%
S15 | P5 Harden | Load test + security scan fixes + DR drill | 44 | 56 | 78.57%
S16 | P5 Harden | Pen-test fixes + data migration dry-runs | 45 | 56 | 80.36%
S17 | P5→P6 | Holiday-reduced · UAT prep — scenarios, test data, env | 30 | 35 | 85.71%
S18 | P6 UAT | UAT round 1 + defect burndown | 30 | 56 | 53.57%
S19 | P6 UAT | UAT round 2 + training content | 30 | 56 | 53.57%
S20 | P6 UAT | UAT round 3 + cutover rehearsal | 30 | 56 | 53.57%
S21 | P7 Cutover | Final fixes + go-live prep + rollback rehearsal | 25 | 56 | 44.64%
S22 | P7 Go-Live | GO-LIVE 14-Mar-2027 + Day-1 hypercare | 25 | 56 | 44.64%